INTRODUCTION

Since inception, NRHM has made a leap in health delivery system in Peren District. This year the District Health Action Plan is to fill in the main gaps which have not been redressed.

There has been an improvement in the peripheral/sub-centre level. VHSNCs have been formed in 70 villages and are actively participating in improving the health delivery system in the village level. Peren District by virtue of its topography is a “difficult to access” area. Health Centers have improved but the need to have functional 24X7 health care delivery facilities is sorely felt. Institutional delivery is still low in the district. At present many of the Obstetrical cases are being referred to the nearest district hospital that is Dimapur.

The thrust this year is to make the District Hospital and CHC Jalukie fully operational FRUs, and Tening PHC which was upgraded to CHC vide Government Order No.HFW-5(B)2007(pt)Kohima Dated the 18th Feb 2020 to be provided with additional manpower posting as per CHC guidelines & infrastructural development to make it functional fully as a CHC. Athibung PHC upgraded to CHC, Nsong sc and Bongkolong SC upgraded to PHC, District mortuary attached to CHC Jalukie and to make Jalukie Zandi SC a delivery point. The maximum focus of DHAP 2021-22 will be on Tening and Athibung Block for all services.

Peren district with an area of 2300sq.kms consist of 88 recognized and 18 unrecognized villages with a population of 95,219(2011 census).

| Sl.no | Health units | No of facility |
| --- | --- | --- |
| 1. | District Hospital | 1 |
| 2. | Community Health centre | 2 |
| 3. | Primary Health centre | 7 |
| 4. | HWC-SC | 10 |
| 5. | Health Sub-Centre | 8 |

Basic demographic profile of the district

| Sl.no | Background characteristics |  |
| --- | --- | --- |
| 1. | Geographical area in sq.km | 23000 sq.km |
| 2. | No of blocks | 4 |
| 3. | Sex ratio | 917 |
| 4. | Literacy rate | 79% |
| 5. | Estimated pregnant women | Jalukie -674, Athibung -141, Peren -164, Tening -218. Total= 1197 |
| 6. | Total eligible couple | Jalukie -4676, Athibung -955, Peren -1002, Tening -799 =7432 |
| 7. | Estimated under 1 population | Jalukie -577, Athibung -114, Peren -150, Tening -141. Total =982 |
| 8. | Total no of schools | Government schools – 135, private schools- 40 |
| 9. | Total no of AWCs | 218 |
| 10. | Total no of ASHAs | 141 |
| 11. | Total no of VHSNCs | 72 |

PLANNNG PROCESS.

The District Health Action Plan was prepared by the District planning Team under the leadership of the Chief Medical Officer with inputs from the District Programme Officers and DPMU & BPMU along with the block medical officers.

Meeting at the block level was conducted by the block Medical Officers & BPMU staffs along with the VHC, VC and other stake holders. Two villages were selected from each block and VHAP was developed.

Meetings were also held with the Common Village Health Committee and Health Centre Management Committee on how best to maximize outputs of the health centers.

Facility survey of the Health Centers was done by District and Block Programme Management Support Unit with active participation of the staff of the facilities..

Meeting of all the Medical Officers and BPMU was held on 8th November at the CMO’s office where the findings of the facility survey and inputs from Medical Officers, BPM, ASHA Co-Ordinator and H/W of the sub-centre were discussed. The findings of the Family Health Assessment undertaken are being compiled.

The information from the block level plans was compiled and the District Health Action Plan was prepared.

SITUATIONAL ANALYSIS

Tening Block: In Tening block there is 1 CHC –Tening CHC (Upgraded in 2020) and 3 PHCs- Ntuma, Azailong & Mbaulwa PHC and 1 sub-centre – Nsong sc upgraded to HWC-SC. The whole block as a whole is underserved and hard to reach area with no public transportation.

No additional manpower has been appointed at Tening CHC after Upgradation. Tening CHC has adequate infrastructure in place with only some major and minor R/R requirements.

The Nsong sc has been upgraded to HWC with additional appointment of CHO but considering its location & remoteness catering to 8 villages, Nsong sc needs to be upgraded to fully fledged PHC and while in process of Upgradation needs to be made a delivery point on urgent basis.

Peren Block: All the 5 sub-centers – Old Peren, Mpai, New Puilwa, Pedi & Benreu sc are evenly distributed. Poilwa PHC is remote and the present PHC building needs separate transformer to make it functional. Poilwa requires 1 ambulance. District Hospital OT extension is required with blood storage facility to make it functioning FRU.

Athibung Block: Athibung Block is the most backward block in the district and has the highest population of BPL. There are 4 HWC sub-centers – Bongkolong, Ikiesingram, New Nkio & Khelma. The building of – Ikiesingram & Khelma sc needs major R/R, New Nkio sc needs a totally new building since most of the sc building is being eaten by termites. Due to logistic problems health workers attend very infrequently and during the rainy seasons they cannot go to the health center. So, it is necessary to make 1 staff quarters in all the sub-centers. Athibung PHC needs to be upgraded to CHC. Additional manpower is required at new sub centre at Pelhang.

Bongkolong sc to be upgraded to PHC.

Jalukie Block: This block is well connected and easily accessible. The 6 Sub-centers – Punglwa, Gaili, Mhainamtsi, Samzuiram, Lilen & Saijang sc are well placed and functioning well. The new sc at Jalukie Zandi has started to function from October 2019 and urgent requirement is to make it a delivery point.

The CHC is well located. Jalukie is easily accessible from all the blocks and the whole populace finds it more accessible. The OPD load is more than the district hospital. If this CHC becomes a functional FRU with posting of critical specialist, many emergency cases will not have to go to the neighboring districts.

Critical analysis:

While reviewing the existing data, due to poor communication and backwardness of the area, the following initiative needs to be taken up on priority basis.

Man-Power:

DH & CHC needs 1 anesthetist, 1 GDMO each on priority.

Posting of SMO at Tening CHC and 2 GDMO. Posting of additional GNM to make it functional as CHC.

Posting of additional MO for Ahthibung PHC and Heningkunglwa PHC

Infrastructure:

DH needs to extend a room for OT for zoning. Peren district as a whole does not have a mortuary and hence construction of mortuary at CHC is required.

Extension of labour room and OT is urgently required at CHC Jalukie.

Since the upgradation of Mbaulwa from Sub-Centre to PHC, no infrastructural development has been done and the PHC is still running in a Sub Centre building and as such needs a new PHC building.

New PHC building for Dungki PHC is required since the present PHC building is in a dilapidated condition.

New sc building for New Nkio sc is required since the old sc building is in a diliapated condition.

Equipments:

After the facility survey the equipment gaps in the facility has been identified and has to be procured on priority basis. The Equipment list is given in Annexure.

Referral Transport:

Given the peculiar terrain and backwardness of the district, referral transport has to be put in 2 PHCs i.e, Ntuma PHC & Poilwa PHC, and Nsong sc on priority basis. Tening ambulance is nearly off road, Athibung ambulance is off road and MMU gypsy is off road. Most of the villages in the district are inaccessible especially during monsoon as there is no motorable road. Some villages have only footpath and hence it is very difficult for people to access health services and also the heath workers to deliver health service to the people.

The main gaps in service delivery in the district are ANC and immunization coverage and institutional delivery and family planning.

Achievements under NHM( Source : HMIS)

| Sl.no | Particulars | 2017-18(Ap-March) | 2018-19(Ap-March) | 2019-20 (Ap-march) |
| --- | --- | --- | --- | --- |
| 1 | Total no of PW registered for ANC | 1406 | 1326 | 1385 |
| 2 | Out of which registered within 1st trimester | 309 | 290 | 284 |
| 3 | No of PW given TT1 | 1076 | 980 | 876 |
| 4 | No of PW given TT2 | 606 | 624 | 724 |
| 5 | No of PW received 4 or more ANC | 212 | 218 | 273 |
| 6 | No of PW tested for hemoglobin 4 or more than 4 times respective ANCs | 120 | 107 | 147 |
| 7 | No of PW having Hb level <11 | 706 | 576 | 506 |
| 8 | No of pregnant women tested for syphilis | 91 | 817 | 892 |
| 9 | Out of which tested +ve | 1 | 18 | 4 |
| 10 | Total no of home delivery (SBA) | 58 | 46 | 94 |
| 11 | Total no of home delivery (non SBA) | 168 | 107 | 88 |
| 12 | Total no of institutional delivery | 666 | 600 | 634 |
| 13 | Total no of CS conducted | 13 | 15 | 23 |
| 14 | Women receiving 1st post partum checkup within 48 hours of delivery | 506 | 224 | 113 |
| 15 | Women receiving 1st post partum check between 48 hours and 14 days | 436 | 248 | 240 |
| 16 | RTI/STI case identified | 643 | 622 | 542 |
| 17 | Total no of lag.lig done | 36 | 29 | 31 |
| 18 | Total no of mini lap conducted | 2 | 1 | 0 |
| 19 | Total no Cu-T insertion done | 149 | 98 | 111 |
| 20 | Total no OCP distributed | 2058 | 2377 | 2026 |
| 21 | Total no of condom distributed | 6293 | 7206 | 6730 |
| 22 | Total no of PTK used | 582 | 843 | 330 |

Achievements under NHM( Source : HMIS)

| Sl.no | Particulars | 2017-18(Ap-March) | 2018-19(Ap-March) | 2019-20 (Ap-March) |
| --- | --- | --- | --- | --- |
| 23 | No of fully immunized children aged between 9-11 months | 755 | 627 | 718 |
| 24 | No of blood smear examined for malaria | 6120 | 4050 | 3898 |
| 25 | No of RDT conducted for malaria | 8767 | 7659 | 2420 |
| 26 | No of adolescent registered in AFHC | 110 | 242 | 289 |
| 27 | No of DOTs patients registered | 62 | 62 | 107 |
| 28 | No of DOTs cases successfully completed | 63 | 29 | 58 |
| 29 | Total no of OPD cases | 26636 | 26908 | 27384 |
| 30 | Total no of IPD cases | 1331 | 1345 | 1414 |
| 31 | Total no of AYUSH OPD | 2959 | 2272 | 2429 |
| 32 | Total no of Dental cases | 1292 | 1401 | 1967 |
| 33 | Total no of ophthalmic cases | 229 | 600 | 692 |
| 34 | Total no of Major operation | 79 | 26 | 18 |
| 35 | Total no of minor operation | 911 | 1287 | 1476 |
| 36 | Total no of VHND conducted | 824 | 922 | 911 |

PEREN DISTRICT : VILLAGE HEALTH ACTION PLAN 2020-21

New Jalukie and Jalukie B for Jalukie block, Old Nkio and Lalong village for Tening Block, and Ndunglwa and Old Puilwa in Peren block, Bongkolong and Songlhuh under Athibung block.

The block planning team conducted meeting the village health committee and the Village council  to formulate the Village Health Action Plan.

| Sl.no | Priority issues | What needs to be done | What will the community do | Support the villagers can provide | Support of the department | Timeframe |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Diarrhoea | BCC activities on hygiene and sanitation. Teach the villagers about use of ORS and home made remedies. Teach ASHAs how to recognize dehydration. | Construct latrines in every household. Drink boiled water. Washing hands with soap before eating and after going to toilet. Using ORS during diarrhea. | VC to declare mass social work to clean the village, drains and the village pond etc every quarter mandatory for every household in the village The Village council can pass an order for mandatory construction of latrines in every house hold. The VHC to approach RD/ WATSAN for support in supplying portable water to the village and construction of sanitary latrines. VHC can organize awareness programme on VHND. Construct ring wells/bore wells and garbage dump. Control of Stray Domestic animals | Provide ORS to the ASHAs and all the health units. Conduct awareness programmes and health camps. Training of Church Women Leaders & ASHAs on Regular IPC /FGD on Diarrhoeal Management especially during monsoon | Ongoing. |

| Sl.no | Priority issues | What needs to be done | What will the community do | Support the villagers can provide | Support of the department | Timeframe |
| --- | --- | --- | --- | --- | --- | --- |
| 2. | Family planning. | BCC activities on small family norm, spacing, use of OCP, condoms, IUCD, sterilization, not to marry off their daughters before attaining the age of 18 years. | To avail the F/P services available at the health units. Marry off their daughters only after attaining marriageable age. | The VHC, Women group and youth can motivate and encourage the villagers to go for F/P . | Ensure availability of OCP, IUD, condoms in the health units. Conduct sterilization camps once a year. | Ongoing |
| 3 | Due to the socio economic reasons it is difficult for the villagers to seek medical intervention unless in emergency. The villagers request the department to conduct medical camps in the fur flung areas atleast once in a qtr. | To approach the department with request to conduct health camps | To extent all support to the medical team. Will provide refreshment and food to the medical team. | To extent all support to the medical team. Will provide refreshment and food to the medical team. | Provide fund and drugs to conduct health camps | 1st qtr 2021-22 |
| 4 | The village being far from the SC and with no public transportation, it is very difficult for the villagers to avail health services from the sc. As such, the ASHA needs to have adequate stock of emergency medicine | The village leaders and the stake holders to give hand holding support to the ASHA’s in all their endeavours | The village leaders and the stake holders to give hand holding support to the ASHA’s in all their endeavours | The village leaders and the stake holders to give hand holding support to the ASHA’s in all their endeavours | Timely and adequate replenishment of ASHA drug kit. Timely release of all ASHA incentive | Immediate |

Block Health Action Plan :

Besides the Operationalization of HWCs, concentrated long term strategy is required to approach the acute Infrastructure and Human Resource deficit.

Summary of Block Planning process:

The block plan has been prepared under the guidance of the Chief Medical Officer Peren as a joint effort of the Medical Officers & support staff of each block.

Participatory process for inputs and suggestion with various block stake holders like the Administration, Town Council, Village council, Women Association, VHV & HCMC was held in respective blocks to generate crucial information on priority needs of the area. Data of Facility survey formed the basis of the Bock Health Action Plan.

Basing on the compilation of information collected from the above sources, this action plan has been formulated.

All Health centers under Peren District are functioning in government buildings. Peren district has benefitted immensely with the initiation of National Health Mission. Much of the service/amenities lapses/ lacunae have been addressed.

Ambulance services have been provided for in all 4 blocks under NHM, though additional ambulance is needed in Poilwa, Ntuma and Nsong.

Laboratory services: Upgradation of the existing lab and start up of lab in all PHCs. Tening CHC, Heningkunglwa PHC, Dungki PHC and Athibung on priority basis.

Electricity: With electric supply being erratic in the whole of the district Solar inverter is required in Nsong, Bongkolong, New Nkio, Khelma and Ikiesingram. New transformer is required in Poilwa PHC since the PHC is functioning without electricity.

Solar Deep freeze in New Nkio sc needed since New Nkio can cater to all 3 sub centers- Khelma, Ikiesingram and New Nkio and covering 12 underserved villages. New Solar DF is required for Nsong SC.

Essential and basic Drugs: To provide timely and in adequate quantities in all HU throughout the year and hard to reach SC on priorities. Distance from the nearest pharmacy is too far (majority of the villages do not have pharmacy)and more over socio economic status is low and health seeking behavior is low because when there is no medicine in the HU they do not feel the need to seek for health care services.

Manpower: Posting of SMO at CHC Tening with additional posting of 2 GDMO, additional MO posting at Ahthibung PHC and posting of MO at Heningkunglwa PHC since the encumbent MO is on study leave since July 2020. Urgent posting of lab.tech at Dungki PHC and Heningkunglwa PHC. Urgent posting of GNM at Heningkunglwa PHC since only 1 regular ANM is manning the whole PHC. Additional posting of 2 GNM each is urgently required at Tening CHC and Ahthibung PHC in order to fully function 24x7.

This plan has been formulated by the Block MO and BPMU in consultation with the Administration, Town Council, Village Council, HCMC and Church Leaders.

Athibung Block Health Action Plan:

Total Population of the Block: 8610

Road connectivity & Transport/referral systems: POOR

No./Name of  Health Units & HR status: 1 PHC – Athibung, 4 HWC-SC – Bongkolong sc, New Nkio sc, Ikiesingram sc and Khelma sc

No. of Village Health Committees/VHSNCs: 29

No. of Schools (Public/Pvt.): 35

Eligible Couple: 955

| SL | PRIORITY ISSUES | ACTIONS TO BE TAKEN/DONE BY THE BLOCK LOCAL LEADERS | COMMUNITY PARTICIPATION/ROLE OF COMMUNITY | SUPPORT/CONTRIBUTION FROM THE BLOCK | SUPPORT REQUIRED FROM HEALTH & OTHER DEPARTMENTS | TIMELINE |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Early marriage | BCC in public gathering. Encourage in pursuing careers and iniatiating life skills from different department like ITI, youth & Sports etc | Initiate and pursue avenues and careers to benefit the community as a whole | Support and encourage the youth to be more productive and help them to receive all available benefits. Encourage entrepreneurship IP and its development among the youths | To provide adolescent corner and advice and counseling. Support from departments like ITI, Youth & Sports to encourage the youth in seeking different fulfilling careers. | 2nd qtr 2021-22 |
| 2 | Diarrhoea | BCC in public place about sanitation, clean drinking water and boiling before consumption. To use clean drinking water Maintain personal hygiene. Quick reporting of any diarrhea cases. | To maintain sanitation in village surrounding and home. To use clean drinking water Maintain personal hygiene. Quick reporting of any diarrhea cases. | To be a role model village in sanitation. To provide clean drinking water in every home. Quick reporting of any diarrhea cases. | Regular and timely supply of medicine at the health units | 1st qtr 2021-22 |
| 3 | Hypertension and back pain as the primary occupation is farming which involves heavy manual work. | BCC in public gathering from different resource persons from Health Department during VHND & Health camps. | Organise programs to educate the public. | Compulosary attendance in VHND & Health camps. | To provide fund for conduct of health camps & seminars. | 1st qtr 2021-22 |
| 4 | Upgradation of Bongkolong sc to PHC as the Sc caters to 5 villages with 1628 population and is the only delivery point nearest to the other 3 sub centres in the block. | Meet the Officials from Department to take up the issue as priority as this will give a boost in service delivery in village and surrounding areas. | Organize programmes and meetings to deliberate and provide any information and support to health department to take up the issue | Take up issue and formulate plan to make this a reality in the timeline | Approval for Upgradation of SC Bongkolong to PHC | 3rd-4rd qtr 2021-22 |
| 5 | Upgradation of Athibung PHC to CHC as the PHC caters to 29 villages with an approx population of 8610. PHC Athibung is manned by 1 MO, 1 AYUSH MO 1 ANM and 2 GNM. Only basic medical services can be provide at the PHC and all other cases are referred to higher facility at Jalukie or Dimapur. The population being huge it is a constant challenge for the MOs and the nurses to meet the demand. Inaccessibility coupled with poor socio economic factore hinders the general populace to seek medical intervention unless in emergency. | Meet the Officials from Department to take up the issue as priority as this will give a boost in service delivery in the whole block. | Organize programmes and meetings to deliberate and provide any information and support to health department to take up the issue | Take up issue and formulate plan to make this a reality in the timeline | Approval for Upgradation of PHC Athibung to CHC | 3rd-4rd qtr 2021-22 |
| 6 | Construction of toilet at Ikiesingram sc, New Nkio sc and Khelma sc. | Meet up and apprise the Health Department to take up this issue as priority as this is a basic amenity which is severely lacking | Provide manpower and assistance during construction | Accelerate the process for providing of this basic facility and further the procurement of raw materials. | Provide Fund for construction of toilet at this sub centers. | 2nd qtr 2021-22 |
| 7 | Construction of New Nkio sc. New Nkio sc caters to 4 villages with an approx 1166 population. | Meet up and apprise the Health Department to take up this issue as priority as this is a basic amenity which is severely lacking. | Provide manpower and assistance during construction | Accelerate the process for providing of this basic facility and further the procurement of raw materials. . | Provide the required facility needed as soon as possible as it is in very dilapidated condition. | 4rd qtr 2021-22 |
| 8. | Posting of additional ANM & gd.IV staff at Pelhang sc |  |  |  | Urgent appointment of ANM & gd.IV staff at Pelhang sc | 1st Qtr 2021-22 |

Tening Block Health Action Plan :

- Total Population of the Block: 11488

- Road connectivity & Transport/referral systems: Poor

- No./Name of  Health Units & HR status: 4 PHCs & 1 SC

- No. of Schools (Public/Pvt.): 30 Govt school & 8 Private schools

- Eligible Couple: 824

- ANC and Immunization Status: Good

| SL | PRIORITY ISSUES | ACTIONS TO BE TAKEN/DONE BY THE BLOCK LOCAL LEADERS | COMMUNITY PARTICIPATION/ROLE OF COMMUNITY | SUPPORT/CONTRIBUTION FROM THE BLOCK | SUPPORT REQUIRED FROM HEALTH & OTHER DEPARTMENTS | TIMELINE |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Tening PHC has been upgraded to CHC vide Government order No. HFW-5(B) 2007(pt) Dated 18 Feb 2020. With Upgradation, posting of SMO, additional GDMO-2, GNM -1, Obs&Gynae-1, paediatrician-1, MO Dental-1 and lab.tech-1, is required on priority. Tening block as a whole is underserved block of the district with no public transportation, erratic electricity & mobile network, it is utmost importance that soft infrastructure like skilled manpower be adequately placed in the block for any medical emergencies. |  |  |  | Appointment/posting of the required specialist & Medical Officer on priority basis. | 1st Qtr 2021-22 |
| 2 | Extension of Tening CHC building (4 rooms) for Nursing station, Laboratory, OPD AND LABOUR ROOM with toilet attached. |  |  |  |  | 1st Qtr 2021-22 |
|  | OST centre at Tening CHC -due to increase in Drug abusers in the block. Existing manpower of the CHC will manage the OST centre once the centre is setup. | In collaboration with churches and NGO’s |  |  |  | 1st Qtr 2021-22 |
|  | De addiction camps / detoxification and rehabilitation camp to be organized in the block at least once in a year in collaboration with NSACS & church leaders/NGOs. |  |  |  |  | 1st Qtr 2021-22 |
|  | Awareness camps on Drug abuse & Early marriages to be conducted in schools at least once a year. With increase in drug users & early marriage in the block it has become imperative that an awareness camp has to be conducted in school. |  |  |  |  | 1st Qtr 2021-22 |
|  | Construction of2 MO qtr and 2 nursing qtr at Tening CHC |  |  |  |  | 1st Qtr 2021-22 |
|  | Urgent requirement of OT equipments ( given in FS) |  |  |  |  | 1st Qtr 2021-22 |
| 3 | A new ambulance was donated by the to Tening CHC by Honorable MLA & Advisor Water Resources. The ambulance allocated under NHM is nearly off road. Major repair is needed urgently. With COVID cases on the rise, 2 ambulances has to be ready and available for medical emergencies at all times. |  |  |  | Allotment of a new ambulance or provide fund for major repair of existing ambulance | 1st qtr 2021-20 |
| 4 | Posting of lab.tech for PHC Tening is urgently needed. |  |  |  | Appointment of lab.tech for Tening PHC | 1st qtr 2021-22 |
| 5 | Extension of labor room for Ntuma PHC since the present LR is very congested and difficult for the staff to work. |  |  |  | Provide fund for extension of LR | 1st qtr 2020-21 |
| 6 | Post of ICTC counselor for Ntuma PHC since there is no manpower attached to ICTC Ntuma |  |  |  | Appointment of counselor | 1st qtr 2020-21 |
| 7 | Posting of MO under Mbaulwa PHC since no MO has been posted after the transfer of the previous MO |  |  |  | Posting of MO at Mbaulwa PHC | 1st qtr 2020-21 |
| 8 | New PHC building for Mbaulwa PHC at the new site since the present PHC is functioning in a sub centre building and the building is in a rundown condition. |  |  |  | New PHC building for Mbaulwa PHC | 2nd -3rd qtr 2020-21 |
| 9 | Replacement of new GNM under NHM under Mbaulwa PHC |  |  |  | The matter has been resolved at District level |  |
| 10 | Construction of LR & New born care attached with toilet at Azailong PHC |  |  |  | Provide fund for construction of LR with attached toilet at Azailong PHC | 3rd qtr 2020-21 |
| 11 | Construction of fencing for Azailong PHC |  |  |  | Provide fund for construction of fencing at Azailong PHC | 3rd qtr 2020-21 |
| 12 | Construction of Over head tank at Nsong sc & Azailong PHC |  |  |  | Provide fund for overhead tank at Azailong and Nsong sc | 3rd qtr 2020-21 |
| 13 | Upgradation of Nsong sc to PHC |  |  |  | Approval for upgradation of Nsong sc to PHC | 1st Qtr 2020-21 |

Jalukie Block health Action Plan :

- Total Population of the Block: 36709

- Road connectivity & Transport/referral systems: Yes

- No./Name of  Health Units & HR status: 1 CHC, 2 PHC & 7 SC

- Anganwadi Centres: 97

- No. of Schools (Public/Pvt.): 48 Govt. School, 24 Private School

- VHND status: Monthly

- Eligible Couple: 4124

| SL | PRIORITY ISSUES | ACTIONS TO BE TAKEN/DONE BY THE BLOCK LOCAL LEADERS | COMMUNITY PARTICIPATION/ROLE OF COMMUNITY | SUPPORT/CONTRIBUTION FROM THE BLOCK | SUPPORT REQUIRED FROM HEALTH & OTHER DEPARTMENTS | TIMELINE |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Posting of Anesthetist at CHC Jalukie since there are many operation cases. |  |  |  | Appointment of Anesthetist on priority basis. | 1st Qtr 2020-21 |
| 2 | With high nos of CS, lap.ligation and other operation being done at the CHC, Extension & zoning of OT needs to be done on priority. This proposal has been put up in the DHAP for the last few years. |  |  |  | Release of fund for extension of OT | 2nd Qtr 2020-21 |
|  | Extension of the labor room. The average delivery in the CHC is 50 in a month and as such the present LR is too congested and needs to be extended. |  |  |  | Provide Fund for extension of the present LR | 1st Qtr 2020-21 |
|  | CHC Jalukie has the higher patient load in the district and with many programmes being implemented like VHNDs, visit of MOs to SCs, monitoring of Hus etc the CHC sorely need a pool vehicle preferably four wheel drive. |  |  |  | Provide a pool vehicle | 4rd qtr 2020-21 |
| 4 | Newly created SC Jalukie Zandi covers 6 villages with a total population of 2679. The distance between Jalukie Zandi SC and CHC is 78 km via Dimapur and there is no public transportation. The need is felt to make Jalukie Zandi sc a delivery point. |  |  |  | Provide labour table & delivery equipments to start Institutional delivery at Jalukie Zandi | 1st qtr 2020-21 |
| 5 | Dungki PHC needs a new PHC building since the building is very old and unrepairable. |  |  |  | Provide fund for new PHC building. | 2nd qtr 2020-21 |
| 6 | Appointment of a lab.tech and computer operator at Dungki PHC |  |  |  | Appointment of lab.tech and a computer operator. | 3rd qtr 2020-21 |
| 7 | Posting of Medical Officer at Heningkunglwa PHC since the present incumbent is on study leave. PHC Heningkunglwa is presently manned by only 1 regular ANM. |  |  |  | Posting of Medical Officer. | 1st qtr 2021-22 |
| 8 | Appointment of 1 GNM & Lab.tech at Heningkunglwa PHC |  |  |  | Appointment of GNM & lab.tech | 1st qtr 2020-21 |
| 9 | Heningkunglwa PHC urgently needs a separate maternity ward with toilet attached. A separate toilet for male & female is also urgently required since there is no toilet for patients except in the labour room. The PHC is at present 2 beded and needs addition 5 more bed for inpatient. |  |  |  | Provide fund for extension/construction of new maternity ward and separate toilet patient. | 2nd qtr 2020-21 |

Peren Block Health Action Plan :

- Total Population of the Block: 9661

- Road connectivity & Transport/referral systems: POOR

- No./Name of  Health Units & HR status: DH PEREN, PHC POILWA, PEDI SC,BENREU SC, OLD PEREN SC, NEW PUILWA SC, MPAI SC .

- Anganwadi Centres: 45

- No. of Village Health Committees/VHSNCs: 13

- No. of Schools (Public/Pvt.): 21(PUBLIC)/ 3(PVT)

- Eligible Couple: 1002

| SL | PRIORITY ISSUES | ACTIONS TO BE TAKEN/DONE BY THE BLOCK LOCAL LEADERS | COMMUNITY PARTICIPATION/ROLE OF COMMUNITY | SUPPORT/CONTRIBUTION FROM THE BLOCK | SUPPORT REQUIRED FROM HEALTH & OTHER DEPARTMENTS | TIMELINE |
| --- | --- | --- | --- | --- | --- | --- |
| 3 | Poor road connectivity & no public transportation to health units coupled with poor mobile network posses a hindrances for the HW to deliver quality and accessible health service to the populace. Absenteeism of HW in their posting place is also a major issue and as such staff quarter in all HU is required. | VHC and VC to strictly monitor the attendance of the health workers in their posting place | Community to be welcoming to the health workers and all hands to be extended to make their stay in the village comfortable | The block MO/medical officers of health unit to visit all sub centres atleast once a quarter. | mobility support for the medical officers to be provided for visiting the health centres | 1st qrtr 2020-21 |
| 4 | Due to the backwardness of the block, accessibility of the public to avail health services is difficult. |  |  | More health camps should be conducted in the villages. MMU team needs to be appointed. | Medicines and funds should be released timely for health camps and MMU camps. | 2nd qrtr 2020-21 |
| 5 | Poilwa PHC is an underperforming PHC in the district. The new PHC building is far from the village and there is no electricity and no running water. The roof of the PHC is also leaking in many places. The PHC urgently needs retaining wall of the compound since frequent landslide has badly affected the area and at this rate, the PHC building will be badly damaged by next monsoon. The MO & HCMC have approached the department for a separate transformer for the PHC but due to the distance of the PHC from the main village area, the cost for installation would be high which the electricity department cannot bear the expense. Due to all these constrains the PHC cannot effectively delivery health services to the populace. (Photo of the PHC attached) | The HCMC to mobilize the community for manual work during R/R of PHC and construction of retaining wall. | Community to voluntarily assist the HCMC during any social work or construction work if done at the PHC. |  | To provide additional fund for R/R of PHC roof, construction of retaining wall, installation of separate transformer. | 2nd & 3th Qtr 2020-21 |
| 6 | Extension or construction of new labour room of labour room. The present labour room is functioning in 8/8 room size which is too small and congested which for normal functioning |  |  |  | Provide fund | 2nd qtr 2020-21 |
| 7 | Separate room for family planning services at DH Peren as at present it is functioning in a temporary room without door. |  |  |  | Provide fund | 2nd -3rd qtr 2020-21 |
| 8 | Isolation ward and post operative ward required for DH |  |  |  | Provide fund | 2nd -3rd qtr 2020-21 |
| 9 | Construction of MO qtr & staff Qtr |  |  |  | Provide fund | 2nd -3rd qtr 2020-21 |

District Health Action Plan 2020-21

Infrastructure

| SL | PRIORITY ISSUES | Justification | SUPPORT REQUIRED FROM HEALTH & OTHER DEPARTMENTS | Time line |
| --- | --- | --- | --- | --- |
| 1 | INFRASTRUCTURE |  |  |  |
| 2 | Tening PHC has been upgraded to CHC vide Government order No. HFW-5(B) 2007(pt) Dated 18 Feb 2020. With Upgradation, extension of Tening CHC building (4 rooms) for Nursing station, Laboratory, OPD AND LABOUR ROOM with toilet attached. | The present labor room is very congested and there is chances of post deliver infection. | Provide fund for extension | 2nd-3rd qtr 2021-22 |
| 3 | Upgradation of Nsong sc to PHC | Nsong sc caters to 8 most underserved areas in the district where there is no public transportation, no mobile network and the nearest PHC i.e Tening PHC is about 4 hours away. The road becomes unmotorable during monsoon. If Nsong sc is upgraded to PHC, Nsong Circle with approx 7000 population will be immensely benefitted. | Approval for upgradation of Nsong sc to PHC | 2nd-3rd qtr 2021-22 |
| 4 | Construction of new PHC building at new site at Mbaulwa | Mbaulwa PHC caters to 5 under served villages in Tening Block with a population of 6125 (2011 census). There is no regular means of public transportation and two of the villages (Heranglwa & Upper Sinjol) do not have motorable roads during monsoon. The accessibility to remote villages is a big hindrance both for service provider and acceptors, the problem compounded especially during monsoon. The nearest Health Unit from Mbaulwa PHC is 22 KM – about 2 hours by vehicle. Mbaulwa PHC since up gradation from sub centre to PHC in the year 1982, is functioning from two-roomed sub centre building with no additional infrastructure upgradation till date. The present PHC building is in a dilapidated condition which is compromising with delivery of quality health service. In providing basic health service to its citizens both quality and accessibility of health services is of paramount importance, where the lack of either one would jeopardize the health of the community. With the backwardness and remoteness of the block, the need of the hour is to construct a new PHC building at Mbaulwa where all basic infrastructural gaps are met and equipped with trained manpower which will have a direct health bearing on its population; enabling the population of this area avail health services, as desired, fulfilling the concept of health being a fundamental right of the people. | Provide for construction of new PHC building at Mbaulwa | 2nd qtr 2021-22 |
| 5 | Construction of New PHC building at Dungki. | Dungki PHC with a population of 2516 approx (2011 census) caters to 3 villages which lie in close proximity but the geography of the centre is such that these 3 villages are secluded from the rest of the block. It takes about 45 to 1 hour crossing 3 rivulets and muddy road on foot to reach the nearest Health Unit CHC Jalukie which is just 9 Km away. With no public transportation the only means of transport is hiring of vehicle or on foot that is obliterating connectivity for 4 months. Situated in Jalukie valley where summers are hot with monsoon diseases, OPD case load are quite high in comparison with the rest of the Health units in the district. The present PHC building was constructed in 1978 and ever since no repair /renovation work was under taken in the PHC building. The present condition of the building is such that R/R cannot be done since the structure of the building is too old and depilated and eaten up by termites. During monsoon the rooms gets flooded from the leakage in the roof and the walls are falling off in all the places. The flooring of the building is very unstable due to cracks and splits. Infrastructural lapses compounded with the remoteness of the PHC are having a direct bearing in achieving a secured healthy present and future generation. | Provide for construction of new PHC building at Dungki | 2nd qtr 2021-22 |
| 6 | Construction of district mortuary attached to CHC Jalukie | Peren district do not have a mortuary. As such, a mortuary is needed attached to CHC Jalukie. | Provide fund for construction of a mortuary with manpower. | 4rd qtr 2021-22 |
| 7 | Extension of Labor Room at DH Peren, CHC Jalukie and Ntuma PHC | The LR at DH Peren, CHC Jalukie and Ntuma PHC is very small and congested. | Provide fund for extension of LR at DH, CHC and Ntuma PHC | 2nd Qtr 2021-22 |
| 8 | Upgradation of Bongkolong sc to PHC | Bongkolong sc is 38 km away from the nearest PHC Athibung. There is no public transportation and no all weather motorable roads. Bongkolong sc caters to 5 villages with an approx 2000 population. Institutional delivery is happening 16 institutional deliveries April to Sept 2019. If Bongkolong is upgraded to PHC with infrastructure and manpower, it will cater to 17 villages which are very underserved and hard to reach. | Approval for upgradation of Bongkolong sc to PHC | 2nd qtr 2021-22 |
| 9 | installation of separate transformer for Poilwa PHC | PHC Poliwa is situated far away from the main village and as such there is no light connection in the PHC. In order to make delivery happen, electrification of the PHC is urgently required for which a separate transformer is required. Both DH & PHC Poilwa have approached the electricity department for the same but due to the high cost involved, the electricity department is not willing to install unless the cost is borne by the Medical Department. | Provide fund for installation of separate transformer at PHC Poilwa | 2nd qtr 2021-22 |
| 10 | Construction of retaining wall at PHC Poilwa | Poilwa PHC is an underperforming PHC in the district. The new PHC building is far from the village and there is no electricity and no running water. The roof of the PHC is also leaking in many places. The PHC urgently needs retaining wall of the compound since frequent landslide has badly affected the area and at this rate, the PHC building will be badly damaged by next monsoon. | Provide fund for construction of retaining wall | 2nd -3rd qtr 2021-22 |
| 11 | Construction of a new SC building at New Nkio | The sc building at New Nkio is in a run down condition since most of the wooden walls are eaten by termites. | Provide fund for construction of new sc building at New Nkio | 2nd Qtr 2021-22 |

Manpower

| SL | PRIORITY ISSUES | Justification | SUPPORT REQUIRED FROM HEALTH & OTHER DEPARTMENTS | Time line |
| --- | --- | --- | --- | --- |
| 1 | Tening CHC –posting of SMO at CHC Tening, 1 obs&gynae, 1 anesthetist, 1 MO Dental, 1 GDMO & 2 GNMs. Posting of additional MO at Ahthibung PHC. Posting of MO, GNM & Lab.tech at Heningkunglwa PHC. Posting of surgeon at CHC Jalukie. Posting of additional GNM at Ahthibung PHC Additional ANM & 1 Gr.IV staff to be posted at new SC Pelhang | Tening CHC caters to the whole of Tening block as well as villages near Manipur border. As such, additional manpower posting is sorely felt. Athibung PHC is the lone PHC in Athibung block. Additional MO is required to make Athibung PHC function 24x7 CHC Jalukie requires a posting of surgeon since there are many cases. The incumbent MO at Heningkunglwa PHC is on study leave and the whole PHC is Posting of lab,tech at Heningkunglwa is required since many lab,testing needs to be done due to the presence of Operation Salvage in Heningkunglwa. ( Operation Salvage: An NGO undertaking for Rehabilitation of Alcohol Abusers and Drug addicts) Ahthibung PHC is functioning 24x7 with shortage of manpower which is taxing the existing manpower immensely. Pelhang sc which was inaugurated on 20th March 2020 is functioning with only 1 ANM and there is no other Gr.IV staff. | Posting of additional manpower at CHC Tening Posting of additional MO at Athibung PHC Posting of surgeon at CHC Jalukie Posting of Lab.Tech at Heningkunglwa PHC | 1st qtr 2021-22 |
| 2 | DPMU & BPMU: posting of DEO at DH Peren. Appointment of DEO at Jalukie block for RCH data entry. | DEO at DH Peren is vacant since Jan 2019 and no appoint has been made. DH Peren urgently requires a DEO for RCH data entry. A DEO is urgently required for Jalukie block – the block being the most populated and with too many programme activities being done simultaneously its is becoming very difficult for the BPM alone to do all entry along with routine duty. This is also one reason why Jalukie block is always in backlog in RCH entry. | Appointment of DEO at DH peren & Jalukie block for RCH Data entry | 1st qtr 2021-22 |

Referral Transport & Health Camps

| SL | PRIORITY ISSUES | Justification | SUPPORT REQUIRED FROM HEALTH & OTHER DEPARTMENTS | Time line |
| --- | --- | --- | --- | --- |
|  | REFERRAL TRANSPORT |  |  |  |
| 1 | Procurement of new ambulance or major R/R of Tening ambulance. Major R/R of Athibung ambulance . Procurement of ambulance for Ntuma, Nsong & Poilwa. | Tening ambulance is near off road. There is no public transportation unless private vehicle. Majority of the patient referred outside for treatment depends on the Tening ambulance. The yearly fund made available for maintence of the ambulance is not enough to cover the repair cost since the ambulance needs major R/R. Athibung ambulance is off road since June 2019. The public is facing immense problem when the patients are referred outside. Ntuma PHC, Poilwa PHC and Nsong sc are located in the extreme ends of the district where there is no public transportation. It will be very beneficial for the public if ambulance is provide for at these Health Units. | Provide fund for R/R of Tening and Athibung ambulance or procurement of new ambulance Procurement of ambulance for Poilwa PHC, Ntuma PHC a7 Nsong sc. | 1st qtr 2021-22 |
|  | HEALTH CAMPS |  |  |  |
| 1 | Conduct health camps in hard to reach areas atleast once every quarter. | The village being far from the SC and with no public transportation, it is very difficult for the villagers to avail health services from the sc. As such, health camps should be conducted in HRAs atleast once in every qtr. | Provide fund & medicine for conduct of health camps | 1st qtr 2021-22 |

MMU & RBSK

| SL | PRIORITY ISSUES | Justification | SUPPORT REQUIRED FROM HEALTH & OTHER DEPARTMENTS | Time line |
| --- | --- | --- | --- | --- |
| 1 | Posting of Medical Officer for MMU along with driver and nurses. | The MMU Team is without a MO, Nurse & driver. The lone staff under MMU - lab.tech joins the VHND team of CHC, Dungki & Heningkunglwa. Appointment of the MMU team is urgently felt because most of the villages under Peren is hard to reach areas and access to medical care is limited due to non existing public transport. | Appointment of MO, Nurse & driver under MMU | 1st qtr 2021-22 |
| 2 | Repair or replacement of MMU gypsy | The MMU gypsy is off road for the past Aug 2019. Application for release of fund for repairing of the same has been put up. The MMU team which comprises of doctors and nurses of different HU is facing problem in conducting MMU camps because of transportation. | Urgent release of fund for R/R of MMU gypsy | 1st qtr 2021-22 |
|  | RBSK |  |  |  |
| 1 | Posting of 2nd MO & GNM for RBSK team. | The RBSK team Peren is functioning with 1 AYUSH MO & 1 ANM. | Urgent appointment of 2nd MO & 1 GNM | 1st qtr 2021-22 |

UIP/RCH

| SL | PRIORITY ISSUES | Justification | SUPPORT REQUIRED FROM HEALTH & OTHER DEPARTMENTS | Time line |
| --- | --- | --- | --- | --- |
| 1 | Alternate Vaccine Delivery | 4-Wheel Drive Gypsy for carrying vaccines (SVS to DVS to CCP to session sites) and a motorcycle (specifically for purpose of immunization) to be used during monsoon for HRA where often bad roads and landslides obstructs vehicular movements to the villages. Almost 80-90% of HRA don’t have public transportation in the district over and above the pathetic road conditions. | Provision of Gypsy for AVD & a motorcycle | 2nd qtr 2021-22 |
| 2 | Internet and mobile connectivity | Peren district is facing immense hardship because of poor net connectivity whereas all reporting needs to be done within a stipulated timeline in specific portal – HMIS, RCH, NCCMIS, all M&E reports, during any immunization campaigns to name a few and the staff are facing untold miseries. NIC option is just a fancy dream as often their network has more sad stories. To make matter worst, most of the villages does not have mobile network to communicate information even through SMS. In the present scenario, catching up with the policy guidelines and timelines becomes impossible. This matter has been discussed often in the DTF meetings and with officers in administration department but till today the network has got just worst. We are helpless in this area but we wise to make a very sincere request to help us plan smarter, sent report faster and manage the system in a more systematic way. | The department can Co ordinate with other Department heads for political commitment. Connection of V-sat at CMO office. | 1st qtr 2021-22 |
| 3 | Immunization awareness | - Grant fund for conducting immunization awareness meeting for Eligible Couples at the villages. - These funds should be based on distance from the HU. - The meeting should be conducted preferably quarterly or bi-annually. | Provide fund for IEC/BCC | 2nd Qtr 2021-22 |
| 4 | Drugs | Sanction some medicine for common ailments like Co-Trimoxazole, Metronidazole, Amoxicillin, Ibubrufen. Paracetamol, Vitamins, ORS for the communities whose villages are far away from the HU, where public transportation is not available and which can be carried to the RI session sites. This can act as a booster to assure and motivate parents to bring their children for immunization, especially for resistant families. This has proved to be very successful based on experiences in the field in low SES communities. | Timely & adequate supply of medicines at CMO store. | 1st qtr 2021-22 |
| 5 | Vaccine supply chain. | Vaccine supply chain has been erratic for more than a year. On one side, the state commitment to achieve 90% FIC by 2019, on the contrary, supply chain of vaccine is going through erratic phases. Many children could not get BCG in time due to 6failure in availability of this vaccine. As a result, we can never work towards achieving the immunization targets, leave aside the susceptible cohort of unimmunized children in the communities leading to a continuous vicious cycle of VPDs circulating in the environment. One of the priority areas, hence, would be an uninterrupted vaccine supply if we are to climb the ladder of achieving the immunization target. | Continuous and adequate supply chain of vaccines. | 1st qtr 2021-22 |
| 7 | Solar DF at Nsong SC and New Nkio sc | Solae Deep Freezer at Nsong SC under Tening block has been out of order for more than a year and it has been informed that the equipments is beyond repair. Nsong SC caters to 7 villages- Nsong, Lalong, Ngam, Nchen, Bamsaikilwa, Nsong villager, Old Ngaulong ( the most challenging HRAs in the district which are absolutely non accessible during monsoon). The furthest among the villages is Lalong 30 km away from Nsong CCP and most difficult terrain Bamsaikilwa (though practically all villages under Nsong have pathetic road connectivity). These villages suffer in terms of not availing vaccination in time and also in all other health benefits. Since the breakdown of the solar equipment, CC handler is going through immense hardship in collecting vaccine for RI sessions from DVs. It is therefore very important to replace the old existing solar DF by a new one for the cause of hundreds of children and PW who deserve equal share of entitled immunization. Solar Deep Freezer is needed since New Nkio sc will be able to cater to 3 sub centers – New Nkio, Khelma & Ikiesingram covering 12 HRA. | Provision of solar DF at Nsong sc and New Nkio sc | 2nd qtr 2021-22 |
| 8 | Requirement of 8 new stabilizer | The district DVS & CCP are at present using 1 stabilizer for both ILR and DF and the has the risk of being overloaded which may in turn lead to break down of ILR & DF. | Provision of 8 new stabilizer for all CCPs | 2nd qtr 2021-22 |

National Vector Borne Disease Control Programme

| SL | PRIORITY ISSUES | Justification | SUPPORT REQUIRED FROM HEALTH & OTHER DEPARTMENTS | Time line |
| --- | --- | --- | --- | --- |
| 1 | Requirement of microscope at PHC Poilwa, Tening and Mbaulwa. | Microscope is required at the PHC s because all blood slides from the health units without microscope have to come to IRC Jalukie for examination. Taking into consideration the Poor road connectivity and no public transportation it is very difficult for the MTS to collect slides and sent to IRC within 48 hours. Sometimes due to delay in sending the blood slides, the process have to be done all over again. | Provision of 3 new microscopes for Poilwa, Tening & Mbaulwa PHC. | 2nd qtr 2021-22 |
| 3 | Requirement of new Xerox machine at IRC Jalukie | The present Xerox machine is beyond repair and the IRC urgently needs a new Xerox machine. | Provision of new Xerox machine or provision of additional fund apart from the OE to purchase a new machine by the district. | 1st qtr 2021-22 |
| 4 | Requirement of a new computer set for IRC Jalukie | The present desk top model is out dated – Windows XP and as such it has outlived its utility. It has become very difficult for compilation and sending reports. | Provision of new Desk Top or provision of additional fund apart from the OE to purchase a new machine by the district. | 1st qtr 2021-22 |
| 5 | Net connectivity | As most of the reports are to be done online and as such Net connection support to be provided to the MTS, Consultant & accountant under NVBDCP on monthly basis or quarterly. | Provision of monthly or quarterly net bill for MTS, consultant and accountant. | 1st qtr 2021-22 |
| 6 | Major R/R of roof at IRC Jalukie | The IRC Jalukie building is more that 40 years old and is in a dilapidated condition. The roof is leaking at countless place and during rain, all equipments & furniture’s have to be covered by plastic for protection. It has become very difficult for the staff to function smoothly. Major R/R is urgently required. | Provision of fund for R/R of IRC Jalukie | 2nd Qtr 2021-22 |

Integrated Disease Surveillance Programme

| SL | PRIORITY ISSUES | Justification | SUPPORT REQUIRED FROM HEALTH & OTHER DEPARTMENTS | Time line |
| --- | --- | --- | --- | --- |
| 1 | Requirement of Desk top with printer | There is no functional desk top in the IDSP Office in Peren. | Provision of 1 set Desk Top with printer | 1st Qtr 2021-22 |
| 2 | Provision of Computer table, 1 nos of office table and 2 office almirah | There is no office furniture in IDSP office | Provision of 1 computer table, 1 office table & 2 almirah | 1st qtr 2021-22 |