# PHEK DISTRICT

# HEALTH ACTION PLAN

2021-2022

# Submitted by:

District Health Society

Phek: Nagaland

SITUATION ANALYSIS

Background information

One of the oldest Districts formed after Nagaland attained Statehood in December 1963, with it’s headquarter at Phek. The district lies in the South East of Nagaland state with Kohima in the West, Myanmar in the East, Kiphire and Zunheboto in the north and Manipur in the south with an altitude of 1, 524 mtrs above sea level. Phek district has a population of 1,63,294 (2011 census) inhabited by Chakhesang, Pochuri, Chokri, Kheza, Poumai, Kuki, and Sema communities.. The district is subdivided into 5 (five) blocks with 14 (fourteen) administrative centres.

2. BASIC HEALTH PROFILE.

Estimated Total Population of Eligible Couple	:	28321

Estimated total Pregnant women		:	2441

Estimated total Population ( 0-1 yr)		:	2170

Estimated total Population ( 0-5 yrs)		:	24031

Estimated total Population ( 0-16yrs)		:	48061

Background Characteristics

| Sl. No | Background Characteristics | Number |
| --- | --- | --- |
| 1 | Geographical Area (in Sq. Kms) | 2025 Sq.Km |
| 2 | Total Population | 1,63,294 (2011 census) |
| 3 | Sex Ration ( F/M * 1000) | 951/ 1000 Male(census 2011) |
| 4 | Density –per sq.km. | 81/sq.km |
| 5 | No. of Villages | 117 |
| 6 | Total No. of Blocks | 5 |
| 7 | Number of towns | 4 |
| 9 | Total No. of Health Units | 75 |
| 10 | Total No. of ASHAs | 146 |
| 11 | Total No. of VHCs | 107 |
| 12 | Total No. of RKS/HCMC | 27( 1 DH, 3 CHCs, 23 PHCs) |
| 13 | Literacy Rate (2011 Census) | 79.13% |
| 13 | No. of Anganwadi Centres | 393 |

PHEK DISTRICT MAP

| PHEK DISTRICT HEALTH FACILITY |  |  |
| --- | --- | --- |
| Sl. No | Name of Health Unit | Type of Facility |
| 1 | District Hospital Phek | District Hospital |
| 2 | Chozuba CHC | CHC |
| 3 | Meluri CHC | CHC |
| 4 | Pfutsero CHC | CHC |
| 5 | Akhegow PHC | PHC |
| 6 | Chetheba PHC 24X7 | PHC |
| 7 | Chizami PHC 24X7 | PHC |
| 8 | Dzülhami PHC | PHC |
| 9 | Hotsu PHC | PHC |
| 10 | Khezhakeno PHC | PHC |
| 11 | Khuzami PHC | PHC |
| 12 | Kikruma PHC | PHC |
| 13 | Laruri PHC | PHC |
| 14 | Lephori PHC | PHC |
| 15 | Lozaphuhu PHC | PHC |
| 16 | Phesachodu PHC | PHC |
| 17 | Phor (Thuda) PHC | PHC |
| 18 | Porba PHC | PHC |
| 19 | Razieba PHC | PHC |
| 20 | Rüzazho PHC | PHC |
| 21 | Sakraba PHC | PHC |
| 22 | Thetsumi PHC | PHC |
| 23 | Thevopisü PHC | PHC |
| 24 | Thipuzu PHC | PHC |
| 25 | Wezihu PHC 24X7 | PHC |
| 26 | Yoruba PHC | PHC |
| 27 | Zuketsa PHC | PHC |
| 28 | K Basa SC | HWC |
| 29 | Lekromi/Kami SC | HWC |
| 30 | Pfutseromi SC | HWC |
| 31 | Rünguzu Nawe SC | HWC |
| 32 | Zapami SC | HWC |
| 33 | Leshimi SC | HWC |
| 34 | Phugi SC | HWC |
| 35 | Chesezu Nawe SC | HWC |
| 36 | Mesulumi SC | HWC |
| 37 | Pholami SC | HWC |
| 38 | Suthozu Nawe SC | HWC |
| 39 | Zhamai SC | HWC |
| 40 | Chepoketa SC | SC |
| 41 | Chobama SC | SC |
| 42 | Chokriba SC | SC |
| 43 | Chozuba Village SC | SC |
| 44 | Gidemi SC | SC |
| 45 | K Bawe SC | SC |
| 46 | Ketsapo SC | SC |
| 47 | Khesomi SC | SC |
| 48 | Khetsokhuno SC | SC |
| 49 | Khomi Middle SC | SC |
| 50 | Khumiasü SC | SC |
| 51 | Kotisu SC | SC |
| 52 | Lanyi SC | SC |
| 53 | Losami SC | SC |
| 54 | Matikhrü SC | SC |
| 55 | Metsale SC | SC |
| 56 | New Thewati SC | SC |
| 57 | Old Phek Village SC | SC |
| 58 | Phek Basa SC | SC |
| 59 | Pokhungri SC | SC |
| 60 | Rd Block (Kikruma) SC | SC |
| 61 | Reguri SC | SC |
| 62 | Rukizu Colony SC | SC |
| 63 | Rünguzu Nasa SC | SC |
| 64 | Sekrezu SC | SC |
| 65 | Sowhemi (Sohomi) SC | SC |
| 66 | Suthotsu SC | SC |
| 67 | Suthozu Nasa SC | SC |
| 68 | Tehephumi SC | SC |
| 69 | Thenyizumi SC | SC |
| 70 | Therotsesemi SC | SC |
| 71 | Zelome SC | SC |
| 72 | Zipu SC | SC |
| 73 | Kizari SC | SC |
| 74 | Kanjang | SC |
| 75 | Meluri Village | SC |

INFRASTRUCTURE of HEALTH UNIT

DISTRICT HOSPITAL PHEK

| SL. NO | Health Unit Name | MS | GDMO/Specialist |  | MO Dental |  | MO Ayush |  | Physiotherapy |  | GNM |  | ANM |  | Pharmacist State | Lap. Tech |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | State | NHM | State | NHM | State | NHM | State | NHM | State | NHM | State | NHM |  | State | NHM/ OTHERS |
| 1 | PHEK DH | 1 | 7 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 16 | 14 | 8 | 0 | 4 | 1 | 2 |

COMMUNITY HEALTH CENTRE

| SL. NO | Health Unit Name | SMO | GDMO |  | MO Dental |  | MO Ayush |  | GNM |  | ANM |  | Pharmacist | Lap. Tech |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | State | NHM | State | NHM | State | NHM | State | NHM | State | NHM |  | State | NHM | NSACS | NVBDCP |
| 1 | CHC Meluri | 1 | 1 (SL) | 1 | 0 | 1 | 0 | 1 | 3 | 2 | 5 | 0 | 2 | 1 | 0 | 1 | 1 |
| 2 | CHC PFUtsero | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 6 | 3 | 6 | 0 | 2 | 1 | 0 | 1 | 1 |
| 3 | CHC Chozuba | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 3 | 1 | 5 | 0 | 2 | 1 | 0 | 1 | 1 |

PRIMARY HEALTH CENTRE

| SL. NO | Health Unit Name | BLOCK | GDMO |  | GNM |  | ANM |  | Pharmacist | Lap. Tech |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | State | NHM | State | NHM | State | NHM |  | State | NHM |
| 1 | PHC Ruzazho | Chozuba | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 |
| 2 | PHC Yoruba | Chozuba | 1 SL | 0 | 0 | 2 (1NHAK) | 1 | 0 | 0 | 0 | 0 |
| 3 | PHC Akhegow | Meluri | 1 (MC) | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 |
| 4 | PHC Laruri | Meluri | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |
| 5 | PHC Lephori | Meluri | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 |
| 6 | PHC Phor (Thuda) | Meluri | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 |
| 7 | PHC Sakraba | Pfutsero | 0 | 1 | 0 | 1 | 2 | 0 | 1 | 0 | 0 |
| 8 | PHC Thetsumi | Pfutsero | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 |
| 9 | PHC Porba | Pfutsero | 1 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 |
| 10 | PHC Razieba | Pfutsero | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 |
| 11 | PHC Khezhakeno | Kikruma | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 |
| 12 | PHC Kikruma | Kikruma | 1 | 0 | 0 | 3 | 3 | 0 | 1 | 1 | 0 |
| 13 | PHC Phesachodu | Kikruma | 1 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 |
| 14 | PHC Zuketsa | Kikruma | 1 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 1 |
| 15 | PHC Thipuzu | Kikruma | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 |
| 16 | PHC Lozaphuhu | Phek Sadar | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 |

PRIMARY HEALTH CENTRE HEALTH AND WELLNESS

| SL. NO | Health Unit Name | BLOCK | CHO |  | GDMO |  | GNM |  | ANM |  | Pharmacist | Lap. Tech |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | State | NHM | State | NHM | State | NHM | State | NHM |  | State | NHM |
| 1 | PHC Chetheba | Chozuba | 0 | 0 | 1 SL | 0 | 0 | 3 | 1 | 0 | 1 | 0 | 0 |
| 2 | PHC Dzulhami | Chozuba | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 |
| 3 | PHC Thuvopisu | Chozuba | 0 | 1 | 1 SL | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 |
| 4 | PHC Wazeho | Meluri | 0 | 0 | 1 | 0 | 0 | 3 | 1 | 0 | 0 | 1 | 0 |
| 5 | PHC Hotsu | Meluri | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |
| 6 | PHC Chizami | Pfutsero | 0 | 0 | 1 | 0 | 1 | 1 | 2 | 0 | 1 | 1 | 0 |
| 7 | PHC Khuzami | Phek Sadar | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |

HEALTH AND WELLNESS SUB-CENTRE CENTRE

| SL. NO | Health Unit Name | Block | CHO |  | ANM |  | Pharmacist |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | State | NHM | State | NHM |  |
| 1 | SC Chesezu Nawe | Chozuba | 0 | 1 | 1 | 1 | 0 |
| 2 | SC K.Basa | Chozuba | 0 | 1 | 0 | 1 | 0 |
| 3 | SC Phugi | Chozuba | 0 | 1 | 1 | 1 | 1 |
| 4 | SC Runguzu Nawe | Chozuba | 0 | 1 | 1 | 0 | 0 |
| 5 | SC Zhamai | Pfutsero | 0 | 1 | 1 | 1 | 1 |
| 6 | SC Mesulumi | Pfutsero | 0 | 1 | 1 | 0 | 0 |
| 7 | SC Suthozu Nawe | Chozuba | 0 | 1 | 1 | 0 | 0 |
| 8 | SC Zapami | Kikruma | 0 | 1 | 1 | 1 | 0 |
| 9 | SC Lekromi/Kami | Kikruma | 0 | 1 | 1 | 1 | 1 |
| 10 | SC Pfutseromi | Kikruma | 0 | 1 | 1 | 1 | 1 |
| 11 | SC Leshimi | Kikruma | 0 | 1 | 0 | 2 | 0 |
| 12 | SC Pholami | Pfutsero | 0 | 1 | 1 | 0 | 0 |
| 13 | SC Chozuba Village | Chozuba | 0 | 1 | 1 | 1 | 0 |
| 14 | SC Sekrezu | Chozuba | 0 | 1 | 1 | 1 | 0 |
| 15 | SC Chobama | Pfutsero | 0 | 1 | 1 | 1 | 0 |
| 16 | SC Chepoketa | Phek Sadar | 0 | 1 | 1 | 1 | 0 |
| 17 | SC Kutsapo | Phek Sadar | 0 | 1 | 1 | 1 | 0 |
| 18 | SC Losami | Phek Sadar | 0 | 1 | 0 | 1 | 0 |
| 19 | SC Phek Village | Phek Sadar | 0 | 1 | 1 | 1 | 0 |
| 20 | SC Khomi Middle | Phek Sadar | 0 | 0 | 1 | 1 | 0 |

SUB-CENTRE CENTRE

| SL. NO | Health Unit Name | Block | ANM |  | Pharmacist |
| --- | --- | --- | --- | --- | --- |
|  |  |  | State | NHM |  |
| 1 | SC Chokriba | Chozuba | 1 | 0 | 0 |
| 2 | SC K.Bawe | Chozuba | 1 | 1 | 0 |
| 3 | SC Khesomi | Chozuba | 1 | 1 | 0 |
| 4 | SC Runguzu Nasa | Chozuba | 0 | 1 | 0 |
| 5 | SC Suthozu Nasa | Chozuba | 1 | 1 | 0 |
| 6 | SC Thenyizumi | Chozuba | 1 | 1 | 0 |
| 7 | SC Therotsesemi | Chozuba | 1 | 1 | 0 |
| 8 | SC Khumiasu | Meluri | 1 | 1 | 0 |
| 9 | SC Matikhru | Meluri | 0 | 1 | 0 |
| 10 | SC New Thewati | Meluri | 1 | 1 | 0 |
| 11 | SC Pokhungri | Meluri | 1 | 1 | 0 |
| 12 | SC Reguri | Meluri | 0 | 1 | 0 |
| 13 | SC Zipu | Meluri | 1 | 1 | 0 |
| 14 | SC Rukizu | Pfutsero | 1 | 0 | 0 |
| 15 | SC Gidemi | Pfutsero | 1 | 1 | 0 |
| 16 | SC Zelome | Pfutsero | 0 | 1 | 0 |
| 17 | SC RD Block Kikruma | Kikruma | 1 | 1 | 0 |
| 18 | SC Khetsokhuno | Phek Sadar | 1 | 0 | 0 |
| 19 | SC Kotisu | Phek Sadar | 1 | 0 | 0 |
| 20 | SC Lanyi | Phek Sadar | 1 | 1 | 0 |
| 21 | SC Metsale | Phek Sadar | 1 | 1 | 0 |
| 22 | SC Sohomi | Phek Sadar | 1 | 0 | 0 |
| 23 | SC Suthotsu | Phek Sadar | 1 | 1 | 0 |
| 24 | SC Tehephumi | Phek Sadar | 1 | 1 | 0 |
| 25 | SC Phek Basa | Phek Sadar | 1 | 1 | 0 |
| 26 | SC Kizari | Phek Sadar | 0 | 1 | 0 |
| 27 | Kanjang | Meluri | 0 | 1 | 0 |
| 28 | Meluri Village | Meluri | 0 | 1 | 0 |

PROCESS OF DISTRICT HEALTH ACTION PLAN DEVELOPMENT

- District level Health Action Planning& Monitoring Committee constituted. Members as per the guidelines given by the govt.

- Block level Health Action Planning & Monitoring Committee constituted. Members as per the guidelines given by the govt.

- All The Proposal are collectively from the Village Health Action Plan and Block Health Action plan.

ACTIVITIES Proposal

for the Financial Year 2021-2022

- NVBDCP PROPOSAL FOR FINANCIAL YEAR 2021-2022

- A) MONITORING AND SUPERVISION AT DISTRICT LEVEL

| SL. NO. | HEALTH STAFF | FIELD MONITORING | JUSTIFICATION |
| --- | --- | --- | --- |
| 1 | DVBO | 7 days field visit in a month 3 HU/village per day | To provide better health care and reporting |
| 2 | DVBDC | 10 days field visit in a month 3 HU/village per day for | To provide better health care and reporting |

- B) MONITORING AND SUPERVISION AT BLOCK AND VILLAGE LEVEL

| SL. NO. | HEALTH STAFF | FIELD MONITORING | JUSTIFICATION |
| --- | --- | --- | --- |
| 1 | MTS | 15 days field visit in a month 3 HU/village/ASHA per day | To provide better health care and reporting |

- MAINTENANCE OF VEHICLE

| SL. NO. | TYPE OF VEHICLE | JUSTIFICATION |
| --- | --- | --- |
| 1 | BOLERO | Need maintenance fund quarterly for better surveillance |
| 2 | MOTORBIKE 9 NOS | Need maintenance fund quarterly for better surveillance |

- NVBDCP PROJECTED ACTIVITIES

| SL. NO. | TYPE OF ACTIVITY | JUSTIFICATION |
| --- | --- | --- |
| 1 | WORLD MALARIA DAY | Continuous activity of NVBDCP guideline. |
| 2 | ANTI MALARIA MONTH | Continuous activity of NVBDCP guideline. |
| 3. | WORLD MOSQUITO DAY | Continuous activity of NVBDCP guideline. |
| 4. | LLIN FORTNIGHTLY OBSERVATION | 2 fortnight observation (1 before transmission season and 1 during transmission season) is necessary to ensure continuous use of bed net. |
| 5. | AWARENESS CAMPAIGN | Awareness campaign is needed to educate Villagers about signs and symptoms, causes, treatment and preventive measures on vector borne diseases. |

- TRAINING

| SL.NO | HEALTH STAFF | JUSTIFICATION. |
| --- | --- | --- |
| 1 | Medical officers | 1 day orientation training is needed to help understand the GOI guideline about the diagnosis and treatment. |
| 2 | DVBDC/MTS | For Quality supervision and monitoring. |
| 3 | MI/SI/SW/PFW | Training is required to help the staffs know the role and responsibility in the field and to collect quality blood slides/ record keeping and reporting. |
| 4 | ANM/GNM | Training is needed for diagnosis and treatment/record keeping and reporting. |
| 5 | LAB TECH | Training is needed for better diagnosis and treatment. |
| 5 | ASHA | Training is needed for quality RDT and blood slide collection/record keeping and reporting. |

- Non Communicable Diseases (NCD):

Proposal for NCD FY-2021-2022:

- District Monitoring and Supervision.

- Operational Cost for Stationary.

- Creation of NCD clinic at Chozuba CHC.

- Maternal Health:

Activity: 1

- Activity Proposed: Meeting at district level on MCDSR

- Name of the Activity: Meeting at district level

- Justification:  Monthly meeting of MCDSR for the district level officer, District hospital and DPMU. To review the Maternal and Child death cases reported, MCDSR guidelines and identify area of concerns for improvement. Financial requirement to conduct this activities for refreshment @ Rs. 1,000 per Month.

- Deliverables:

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost | FMR CODE |
| --- | --- | --- | --- |
| 12 | 1,000/- | 12,000/- |  |

Activity: 2

- Activity Proposed: Review/ Re-orientation on MCDSR

- Name of the Activity: Review/ Re-orientation on MCDSR

- Justification:  Two time of Review/ re-orientation on MCDSR of all Block Medical Officers with District Officials at District Headquarter. Financial requirement for DA/TA for 5 Block and district officials to provided with Rs. 30,000/- per Review/Orientation programme.

- Deliverables:

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost | FMR CODE |
| --- | --- | --- | --- |
| 2 | 30,000/- | 60,000/- |  |

Activity: 3

- Activity Proposed: Incentive and mobility support of MCDSR

- Name of the Activity: Incentive and mobility support of MCDSR

Justification:  Maternal Death review incentive for ASHA Rs.200 per case reported and Rs. 150 for 3 person of MCDSR team per verbal autopsy. And Rs. 1000 per case reported under SUMAN initiative.

- Deliverables:

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost | FMR CODE |
| --- | --- | --- | --- |
| 148 |  |  |  |

Activity: 4

- Activity Proposed: Training on Dakshata

- Name of the Activity: Training on Dakshata

Justification:  Training on Dakshata for three days to all catagories.

MO: 27 Mediacal Officer from 23 PHC/3 CHC/ 1 DH

CHO: 12 CHO from 12 HWC-SC

ANM: 33 ANM from 33 Subcentre

Total number of batch: 5 batches

Total participants: 73

- Deliverables:

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost | FMR CODE |
| --- | --- | --- | --- |
| 73 | 3650 | 2,66,450 |  |

| Detail break up of fund for Three days Training expenses at District level meeting for MO/CHO/ANM on Dakshata. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sl no | Name of District | Batch | No. of Participant | Rate including all expenditure for participant @ per Head DA/TA Lum sum | Institutional Over Head @ 100 per person | Total of (B x C) + D X Per Head |  |
|  |  |  | B | C | D |  |  |
|  | Phek | 5 | 73 | 3550 | 100 | 2,66,450 |  |

Activity: 5

- Activity Proposed: Mobility support for VHND

- Name of the Activity :Mobility support for VHND

Justification:  Mobility support for Medical Officer to attend monthly activities of VHND in Hard to Reach area to strengthen and improve performance. Financial requirement Rs. 1000 per VHND for 16 HRA villages.

- Deliverables:

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost | FMR CODE |
| --- | --- | --- | --- |
| 16 | 1000 | 1,92,000 |  |

Activity: 6

- Activity Proposed: RCH outreach camp

- Name of the Activity : RCH outreach camp

- Justification Two RCH outreach camp in one financial year for more coverage in Hard to Reach Area (HRA). Financial requirement  Rs. 30,000/- per camp

.

- Deliverables:

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost | FMR CODE |
| --- | --- | --- | --- |
| 2 | 30,000 | 60,000 |  |

Activity: 7

- Activity Proposed: Other maternal Health Training

- Name of the Activity: : One day workshop Ensuring Quality Antenatal Care

Justification:  One day workshop of all MOs/CHOs and ANM in the district on Ensuring Quality Antenatal Care through 1000 days approach.

Total Batches: 3 Batch

Total Participant: 73

- Deliverables:

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost | FMR CODE |
| --- | --- | --- | --- |
| 73 | 1600 | 1,16,800 |  |

| Detail break up of fund for Three days Training expenses at District level meeting for MO/CHO/ANM |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sl no | Name of District | Batch | No. of Participant | Rate including all expenditure for participant @ per Head DA/TA Lum sum | Institutional Over Head @ 100 per person | Total of (B x C) + D X Per Head |  |
|  |  |  | B | C | D |  |  |
|  | Phek | 3 | 73 | 1500 | 100 | 1,16,800 |  |

Activity: 8

- Activity Proposed: Line Listing of High Risk Pregnancies/ Severe Anaemia

Name of the Activity: : Training of MO/CHOANM on Tracking of High Risk Pregnancies.

Justification:  One day training of MOs/CHOs/ANMs on Tracking of High Risk Pregnancies to ensure quality ANC and improve institutional delivery.

Total Batch: 3 Batches

Total Participant: 73 participant

- Deliverables:

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost | FMR CODE |
| --- | --- | --- | --- |
| 73 | 1600 | 1,16,800 |  |

| Detail break up of fund for Three days Training expenses at District level meeting for MO/CHO/ANM |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sl no | Name of District | Batch | No. of Participant | Rate including all expenditure for participant @ per Head DA/TA Lum sum | Institutional Over Head @ 100 per person | Total of (B x C) + D X Per Head |  |
|  |  |  | B | C | D |  |  |
|  | Phek | 3 | 73 | 1500 | 100 | 1,16,800 |  |

Activity: 9

- Activity Proposed: IEC/BCC activities under MH

Name of the Activity: : One Day Workshop.

Justification:  One day workshop on important of ANC and institutional delivery with Church leaders in all the 5 blocks. Which will create more awareness and effective information to the community.

Total Batch: 5 Batches

Total Participant: 234 ( 117 Villages two each).

- Deliverables:

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost | FMR CODE |
| --- | --- | --- | --- |
| 234 | 1050 | 2,45,700 |  |

| Detail break up of fund for Three days Training expenses at District level meeting |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sl no | Name of District | Batch | No. of Participant | Rate including all expenditure for participant @ per Head DA/TA Lum sum | Institutional Over Head @ 100 per person | Total of (B x C) + D X Per Head |  |
|  |  |  | B | C | D |  |  |
|  | Phek | 5 | 234 | 1000 | 50 | 2,45,700 |  |

Activity: 10

- FMR Code:

Activity Proposed: Innovative Proposal

Name of the Activity: : Sensitization on safe delivery practices to Traditional Birth Attendant (TBA).

.Justification:  Sensitization on safe delivery practices to Traditional Birth Attendant in all villages of the district. Since most of the Home deliveries are conduct/attended by Traditional Birth attendant in the village.

Total Batch: 5 Batches

Total Participant: 117 participant (117 Village)

Deliverables:

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost | FMR CODE |
| --- | --- | --- | --- |
| 117 | 2100 | 1,53,300 |  |

| Detail break up of fund for Three days Training expenses at District level meeting for TBA |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sl no | Name of District | Batch | No. of Participant | Rate including all expenditure for participant @ per Head DA/TA Lum sum | Institutional Over Head @ 100 per person | Total of (B x C) + D X Per Head |  |
|  |  |  | B | C | D |  |  |
|  | Phek | 5 | 117 | 1000 | 50 | 1,22,850 |  |

- Newborn and Child Health

Proposal:

1.  Procurement of Equipment

- NBSU: ANNEXURE-I

- NBCC: ANNEXURE-II

Activity: 1

- FMR Code:

- Activity Proposed: One day Training on FIMNCI

Name of the Activity: Sensitization on safe delivery practices to Traditional Birth Attendant.

.Justification:  Training on FIMNCI of MOs/GNMs/ANMs of 16 delivery point in the district.

Total Batch: 2 Batches

Total Participant: 32

Deliverables:

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost | FMR CODE |
| --- | --- | --- | --- |
| 32 | 1600 | 51,200 |  |

| Detail break up of fund for Three days Training expenses at District level meeting for MO/GNM/ANM |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sl no | Name of District | Batch | No. of Participant | Rate including all expenditure for participant @ per Head DA/TA Lum sum | Institutional Over Head @ 100 per person | Total of (B x C) + D X Per Head |  |
|  |  |  | B | C | D |  |  |
|  | Phek | 2 | 32 | 1500 | 100 | 51,200 |  |

Activity: 2

- FMR Code:

- Activity Proposed: IMNCI

- Name of the Activity:. : One day Training on IMNCI

.Justification:  Training on IMNCI of MO/GNM/ANM of all NBCC and NBSU health facility in the district.

Total Batch: 2 Batches

Total Participant: 32

Deliverables:

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost | FMR CODE |
| --- | --- | --- | --- |
| 32 | 1600 | 51,200 |  |

| Detail break up of fund for Three days Training expenses at District level meeting for MO/GNM/ANM |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sl no | Name of District | Batch | No. of Participant | Rate including all expenditure for participant @ per Head DA/TA Lum sum | Institutional Over Head @ 100 per person | Total of (B x C) + D X Per Head |  |
|  |  |  | B | C | D |  |  |
|  | Phek | 2 | 32 | 1500 | 100 | 51,200 |  |

Activity: 3

- FMR Code:

- Activity Proposed: Anaemia Mukt Bharat Programme

Name of the Activity: : One day Orientation on Anaemia Mukt Bharat Programme.

Justification:  One day Orientation for MOs/CHOs/GNM and ANMs on Anaemia Mukt Bharat Programme. Separate batch for Medical officer, CHO/GNM and ANM in the district.

Total Batch: 3 Batches

Total Participant: 73

- Deliverables:

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost | FMR CODE |
| --- | --- | --- | --- |
| 73 | 1600 | 1,16,800 |  |

| Detail break up of fund for Three days Training expenses at District level meeting for MO/CHO/ANM |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sl no | Name of District | Batch | No. of Participant | Rate including all expenditure for participant @ per Head DA/TA Lum sum | Institutional Over Head @ 100 per person | Total of (B x C) + D X Per Head |  |
|  |  |  | B | C | D |  |  |
|  | Phek | 3 | 73 | 1500 | 100 | 1,16,800 |  |

Activity: 4

- FMR Code:

- Activity Proposed:

Name of the Activity: : One day Orientation for Frontline workers and Teachers.

Justification:  One day Orientation for Frontline workers (ASHA/AWW) and Teachers at the Block level. Separate batch for ASHA/AWW and teachers in 5 Block in the district.

Total Batch: 5 Batches ( 5 Block)

Total Participant: 146 ASHA/256 AWW

- Deliverables:

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost | FMR CODE |
| --- | --- | --- | --- |
| 402 | 1300 | 2,22,600 |  |

| Detail break up of fund for Three days Training expenses at District level meeting for ASHA/AWW |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sl no | Name of District | Batch | No. of Participant | Rate including all expenditure for participant @ per Head DA/TA Lum sum | Institutional Over Head @ 100 per person | Total of (B x C) + D X Per Head |  |
|  |  |  | B | C | D |  |  |
|  | Phek | 5 | 402 | 1250 | 50 | 2,22,600 |  |

Activity: 3

FMR Code:

- Activity Proposed: Child Death review

- Name of the Activity: Incentive and mobility support of MCDSR REVIEW

Justification:  Child Death review incentive for ASHA Rs.200 per case reported and Rs. 150 for 3 person of MCDSR team per verbal autopsy. And Rs. 1000 per case reported under SUMAN initiative.

- Deliverables:

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost | FMR CODE |
| --- | --- | --- | --- |

- CHILD HEALTH 2021-2022

Activity: 1

- FMR Code:

- Activity Proposed:  Recurrent cost of NBSU

- Name of the Activity:	 Maintenance & consumable for NBSU

- Justification: Ongoing

- Deliverables: Based on report the proposed budget @ Rs. .80 Lakhs per NBSU on need based. Since most of the NBSU case loads less, accordingly the utilization of fund is low, therefore the rate per unit is cut down as per the state specific need and also to meet in the state resource envelope.

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost(in Lakhs) | FMR CODE |
| --- | --- | --- | --- |
| 1 | 80000 | 80000 |  |

| Districts | Target for 2018-19 | Cost per unit | Total Amount |
| --- | --- | --- | --- |
| 7. Phek | 1 | 80000 | 80000 |
| Grand Total | 1 |  | 80000 |

Activity: 2

- FMR Code:

- Activity Proposed:  Recurrent cost of NBCC

- Name of the Activity:	Maintenance& consumable for NBCC

- Justification:	On going activity, since the state resource envelope is limited, therefore the budget per NBCC is cut down @Rs. 10000/NBCC for GoI consideration and approval.

- Deliverables:

- Funding Proposed:

| No. of Units: | Cost per unit | Total Cost(in Lakhs) | FMR CODE |
| --- | --- | --- | --- |
| 16 | Rs. 10000/- | 1.6 |  |

| Districts | Proposed Amount for 2018-19 |  |  |
| --- | --- | --- | --- |
| Name of HU | Block | Cost per unit | Total Cost in Rs. |
| DH |  | 10000 | 10000 |
| Chozuba |  | 10000 | 10000 |
| Pfutsero |  | 10000 | 10000 |
| Meluri |  | 10000 | 10000 |
| Waziho |  | 10000 | 10000 |
| Chizami |  | 10000 | 10000 |
| Chetheba |  | 10000 | 10000 |
| Porba |  | 10000 | 10000 |
| Khezhakeno |  | 10000 | 10000 |
| Phesachodu |  | 10000 | 10000 |
| Thivopisu |  | 10000 | 10000 |
| Ruzazho |  | 10000 | 10000 |
| Yoruba |  | 10000 | 10000 |
| Kikruma |  | 10000 | 10000 |
| Zuketsa |  | 10000 | 10000 |
|  |  |  | 1,60,000 |

Activity:: 3

- FMR Code:

- Activity Proposed:  National Deworming Day (NDD)

- Name of the Activity: Incentive for ASHA for mobilizing and ensuring every eligible child (1to19 yrs out of school and non-enrolled) is administered Albendazole during NDD.

- Justification:  Ongoing activity.

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost(in Lakhs) | FMR CODE |
| --- | --- | --- | --- |
| 146 | 200 per ASHAs | .292 |  |

Table A: Budget for ASHA incentive for NDD 2019-20

|  |  | No. of ASHAs in Position | Incentive for ASHA |  | Total Amount in Rs. |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Aug 2020 @ Rs. 100/ | Feb 2021 @Rs. 100/ |  |
|  |  | A | B | C | (B + C x A) |
| 1 | Phek | 146 | 100 | 100 | 29200 |
|  | Total |  |  |  | 29200 |

Activity:: 4

- FMR Code:

- Activity Proposed:  Management of Diarrhoea & ARI Micro nutritional malnutrition.

- Name of the Activity:	ASHA incentive on IDCF 2020

- Justification: On going

- Deliverables: The proposed amount is for the incentive to ASHA for IDCF 2020

- Funding Proposed:

| No. of Units: | Cost per unit | Total Cost(in Lakhs) | FMR CODE |
| --- | --- | --- | --- |
| 146 | 100 | .146 |  |

Table A: Budget for ASHA incentive for IDCF 2019

|  |  | No. of ASHAs in Position | Incentive for ASHA | Total Amount in Rs. |
| --- | --- | --- | --- | --- |
|  |  |  | For ORS @ Rs 100/ASHA |  |
|  |  | A | B | (A x B) |
| 4 | Phek | 146 | 100 | 14600 |
|  | Total | 146 |  | 14600 |

Activity:: 5

FMR Code:

- Activity Proposed: Incentive for mobilizing children and/or ensuring compliance and reporting (6-59 months)

- Name of the Activity:	ASHA incentive on NIPI

- Justification: New

- Deliverables: The proposed amount is for the incentive to ASHA for mobilizing children and/or ensuring compliance and reporting (6-59 months) under NIPI Programme for FY 2020-21

- Funding Proposed:

| No. of Units: | Cost per unit | Total Cost(in Lakhs) | FMR CODE |
| --- | --- | --- | --- |
| 146 | 100 | .146 |  |

Activity: 6

- FMR Code:

- Name of the Activity: Procurement of Albendazole for age group of 1 to 5 yrs

- Justification: District to indicate the target group as per the  cencus please fellow the table below

- Deliverables:

| FMR Code | Activity | Target |
| --- | --- | --- |
| 6.2.2.4 | Procurement of Albendazole Tab | Table below |

- Funding Proposed:

| No of unit | Cost per unit | Total Cost(in Lakhs) | FMR Code |
| --- | --- | --- | --- |
| 35924.68 | 5 | 1.80 |  |

| 2011 | Total Population (Census 2011) | Under 5 yrs (10% of Pop.) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Target for 2 Round | Total Tab requirement for 1 round | 10% wastage factor | Total Target group/tab required | Total Target group/tab required for 2 round |
|  |  |  | D | A | B | A+B = C | C x D |
| Phek | 163294 | 16329.4 | 2 | 16329.4 | 1632.94 | 17962.34 | 35924.68 |

To find the target group follow the guidelines.

The structure of population of India in percentage is available at As per Census 2011.

| Category of beneficiaries | Percent to Total Population (Rounded off to nearest zero) |
| --- | --- |
| Children under 5 years | 10 % |
| Children 5 – 10 years | 12 % |
| Adolescents (10 – 19years) | 22 % |
| Women in Reproductive Age (20 – 49 years) | 20 % |

(Source:http://censusindia.gov.in/Census_And_You/age_structure_and_marital_status.aspx and: C2 and C14 Table, India, Census of India 2001)

- For calculating children 1-2 years who are given half dose of Albendazole :

Age wise number of population for every state is available at the ‘Age – Data : Single Year Age Data – C13 Table (India/States/UTs)

http://www.censusindia.gov.in/2011census/population_enumeration.aspx

Activity:: 7

- FMR Code:

- Activity Proposed:  Procurement of Albendazole for age group of 5- 10 yrs

- Name of the Activity: For National Deworming Activity(NDD)

- Justification: As per the State essential drug list the schedule rate is Rs.5/tab. this is inclusive of all local taxes handling charges and transportation. The schedule rate of the state is comparatively higher as the company responsible for providing the medicine is not in a position to supply in less rate due the less quantity of order.

- Deliverables:

| FMR Code | Activity | Target |
| --- | --- | --- |
|  | Procurement of Albendazole Tab | Table below |

- Funding Proposed:

| No of unit | Cost per unit | Total Cost(in Lakhs) | FMR Code |
| --- | --- | --- | --- |
| 43109.62 | Rs. 5 | 2.16 |  |

| 2011 | Total Population (Census 2011) | Age group of 5 to 10 yrs(12%) | Target for 1 Round | Total Tab requirement for 1 round | 10% wastage factor | Total Tab. required/target group | Total Target group/tab required for 2 round |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | A | B | A+B |  |
| Phek | 163294 | 19595.28 | 2 | 19595.28 | 1959.528 | 21554.81 | 43109.62 |

Activity: 8

- FMR Code:

- Activity Proposed:  Management of Diarrhoea & ARI Micro nutritional malnutrition.

- Name of the Activity:	IDCF FY-2021-2022

- Justification: On going

- Deliverables: Field level monitoring visit during the campaign and one day meeting expenditure before the campaign start, with the Block official and with other sister department for IDCF activity at the district level, during the meeting they will review brief/trained the key level worker how to go about the IDCF.

- Funding Proposed:

| No. of Units: | Cost per unit | Total Cost(in Lakhs) | FMR CODE |
| --- | --- | --- | --- |
| Detail in table below | Detail in table below | 14.30 |  |

Budget for Daily Mobility Support for field level monitoring, and one day meeting expenditure at District level

|  |  | Rate(in Rs) | Target | Total amount in Lakhs |
| --- | --- | --- | --- | --- |
| 1 | Daily Mobility Support for field level monitoring at District Level | 40000 | 1 District | .40 |
| 3 | One day meeting at District level proposed amount Lumsum @Rs. 90000/District | 90000 | 1 District | .90 |

Activity: 9

- FMR Code:

- Activity Proposed:  Child death review.

- Name of the Activity:	one time review meeting on District Level.

- Whether New/ or being continued:  New

- Achievements if continued from previous years:  NA

- JustificationDeliverables:

| FMR Code | Activity | Target |
| --- | --- | --- |
| 10.1.2 | Child Death Audit | 1 District |

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost in lakhs | FMR CODE |
| --- | --- | --- | --- |
| 1 district level workshop | Detail Below | .57 |  |

Two days Advocacy/Workshop on Child Death Review process for HWs, at the District level

| Sl no | Name of District | No. of Block | No. of persons 4 Per Block for workshop | Rate including all expenditure for participant @ per Head DA/TA Lum sum(Rs 2000/person) | Institutional Over Head (stationeries) @ 300 per person for 2 days | Printing of Formats | Total of D x C |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Phek | 5 | 20 | 40000 | 12000 | 5000 | 57000 |

Activity:  10

- FMR Code:

- Activity Proposed: Printing of MCP Card

- Name of the Activity:

- Justification:

- Deliverables:

| No. of Units: | Cost per unit | Total Cost(in Lakhs) | FMR CODE |
| --- | --- | --- | --- |
| 3157 | Rs.30/card | .95 |  |

| 2011 | Projected Popn. Of 2011 | Expected Pregnancies | 10% wastage factor | Target required |
| --- | --- | --- | --- | --- |
|  |  | B + 10% X B |  |  |
| Phek | 164931.0224 | 2870 | 287 | 3157 |

Activity: 11

- FMR Code:

- Activity Proposed: District level (Meetings/ review meetings)

- Name of the Activity: (Based on the needs district needs to proposed for CH review meeting at district level the given budget is just am example

- Whether New/ or being continued:  New

- Achievements if continued from previous years:

- Justification:

- Deliverables:

| FMR Code | Activity | Target |
| --- | --- | --- |
| 16.1.2.1.1 | 1 meeting per district with BLO,BPM for 11 district | 60000 x 1(District) |

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost (in lac) | FMR CODE |
| --- | --- | --- | --- |
| 1 meeting per district | 60000 x 1(District) = 6.60 | .60 |  |

Activity:: 12

- FMR Code:

- Activity Proposed: NDD 2021-22

- Name of the Activity: PM activity for NDD this activity was not approved in SPIP 2019-20, however request to proposed in DHAP 2020-21 since during the programme implementation fund is required to carry out the activity. Given below budget is just an example.

- Justification:

- Deliverables:

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost(in Lakhs) | FMR CODE |
| --- | --- | --- | --- |
| Detail in table below (for 1 District & 5 Block level) table A | Detail in table A below |  |  |

Table A:: Detail budget requirement for district & Block level

| Tentative budget for Aug 2018 NDD |  |  |  |  |  |  | Tentative budget for Feb 2018 NDD | Total budget required for two Round NDD |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sl no | Name of District | Block | Tentative Budget per block(in Rs) | Total (in Rs) | District level meeting expenses | Total Amount |  |  |
|  |  | I | II | (I x II=A) | B | (A+B)=C | D | (C+D)=F |
| 8 | Phek | 5 | 10000 | 50000 | 15000 | 65000 | 65000 | 130000 |

TRAINING PROPOSAL FOR FINANCIAL YEAR 2021-2021

| Sl.no | Category of training | Staff |  |
| --- | --- | --- | --- |
|  |  |  | Phek Proposal |
|  |  |  | Load 2020-21 |
| 1 | SBA | Specialist (O&G) |  |
|  |  | Nurses | 10 |
| 2 | EmOC | Mos | 5 |
| 3 | LSAS | Mos | 1 |
| 4 | MTP | Mos | 2 |
| 5 | RTI /STI | Mos | 3 |
|  |  | Nurses | 5 |
| 6 | BEmOC | Mos | 2 |
| 7 | IMEP | Nurses | 7 |
|  |  | LT | 2 |
|  |  | WH | 2 |
| 8 | Orientation on Deworming during pregnancy,Calcuim supllementation,Screening of hyperthyoidism | Medical Officers/O&G | 3 |
|  |  | Staff Nurses | 3 |
|  |  | ANMs | 3 |
| 7 | Training on Diagnosis and Management of Gestational Diabetes Mellitus(GDM) | TOT |  |
|  |  | Medical Officers/O&G | 3 |
|  |  | Staff Nurses | 3 |
|  |  | ANMs | 3 |
| 8 | Sensitization workshop on Dakshata Program | CMO,Dy CMO MS, DIO&MO | 1 |
| 9 | 5 days training of trainers & quality improvement mentors( Dakshata) | 1 Doctor 2 Nurse |  |
|  | on site training of labour room staff at DH( Dakshata) | Nurses |  |
|  | Training of staff from CHC,PHC,& SC level facilities ( Dakshata) | Nurses | 73 |
|  | Post training follow up support( Dakshata) | Trainer |  |
| 10 | Blood Storage Unit | Mos | 1 |
|  |  | Nurses | 1 |
|  |  | LT | 1 |
| 11 | IMEP | Mos | 3 |
| 12 | IMNCI | Nursing students |  |
|  |  | ANMs | 9 |
| 13 | F-IMNCI | Mos | 1 |
|  |  | SNs | 2 |
| 14 | NSSK | Mos |  |
|  |  | SNs | 7 |
|  |  | ANMs | 5 |
| 15 | SNCU | Mos |  |
|  |  | SNs |  |
| 16 | Laparoscopic Sterilization | Gynea/Surg. |  |
|  |  | SN |  |
|  |  | OT Assitant |  |
| 17 | NSV | MO | 1 |
| 18 | IUCD insertion | MO | 2 |
|  |  | MO(AYUSH) | 3 |
|  |  | GNM | 9 |
|  |  | ANM | 7 |
| 19 | PPIUCD | MOs | 4 |
|  |  | Nurses | 5 |
| 20 | Training on Injectable Contraceptive(DMPA) | Mos | 4 |
|  |  | SN | 4 |
|  |  | ANMs/LHV | 4 |
| 21 | Training on RMNCH+A | Counsellors | 2 |
| 22 | AFHS Training | MOs | 4 |
| 23 | AFHS Training | ANMs | 4 |
| 24 | AFHS Training | Couselors | 4 |
| 25 | PE Training | Peer Educators |  |
| 26 | Teachers | Teachers | 99 |
|  | AWWs | AWWs | 351 |
| 27 | One day Orientation | Mobile Health Team | 4 |
| 28 | HMIS and RCH Re-orientation | GNM | 27 |
|  |  | ANM | 47 |
| 29 | Re-orientation on Kayakalp | MO | 24 |
| 30 | Orientation on NQAS | MO | 24 |

PROCUREMENTS

7.

| SL. No | Proposal | Categories | Total Number Requirements | Justification |
| --- | --- | --- | --- | --- |
| 1 | Labour Table | Health and Wellness Sub-Centre | 20 HWC | To Improve institutional Delivery and safety of Mother’s and Child. Many rural area prefer for Home delivery due to lack of proper equipment in the facilities. |
| 2 | Delivery Set | Health and Wellness Sub-Centre | 20 HWC | Delivery set for all the Health and Wellness sub-centre for encourage for institutional delivery. |
| 3 | IUCD Kits | Health and Wellness Sub-Centre | 20 HWC | Family Planning services at Sub- Centre are very poor due lack of Kits and Commodities. With availability of IUCD Kits can improve the programme of Family Planning. |

| Sl. No | Equipments Proposal for District Hospital Particulars | Present Status | Requirements |
| --- | --- | --- | --- |
|  | Pediatric Unit |  |  |
| 1. | Electronic Weighing Scale | 0 | 2 |
| 2. | Infusion Pump | 0 | 2 |
| 3. | Syringe Pump | 1 | 2 |
| 4. | Pulse Oxymeter | 1 | 4 |
| 5. | Bilirubinometer | 0 | 1 |
| 6. | Phototherapy Flux meter | 1 | 1 |
| 7. | Cardiopulmonary Monitor | 0 | 1 |
| Gynae Ward |  |  |  |
| 1. | Labour room lamp | 2 | 2 |
| 2. | Cryo therapy | 0 | 1 |
| 3. | Hysterectomy Set | 1 | 2 |
| 4. | MVA Set | 1 | 4 |
| 5. | PPIUCD set | 0 | 6 |
| 6. | Tubal laparoscopic set | 1 | 1 |
| 7. | Uterine manipulator | 0 | 2 |
| 8. | Vicryl 2346 | 50 | 200 |
| 9. | Vicryl 2347 | 50 | 200 |
| 10. | O.T Biowaste pin | 1 | 2 |
| 11. | Lifting Forcep | 4 | 10 |
| 12. | Caesarian Section set | 0 | 2 |
| 13. | Kelly’s Pad | - | 10 |
| 14. | Delivery apron | 5 | 20 |
| Dental Unit |  |  |  |
| 1. | Dental Chairs | 3 | 1 |
| 2. | Ultrasonic Scaler | 0 | 1 |
| 3. | RVG X-Ray | 0 | 1 |
| 4. | Airoter Straight Handpiece | 0 | 1 |
| 5. | Extraction Forcep set | 2 | 1 |
| 6. | Filling instrument set | 1 | 1 |
| Surgery Ward |  |  |  |
| 1. | Laparoscope 30 degrees | 0 | 1 |
| 2. | Laparoscore 0 degrees | 0 | 1 |
| 3. | Insufflator | 0 | 1 |
| 4. | Light source | 0 | 1 |
| 5. | Harmonic scalpel | 0 | 1 |
| 6. | LAP Recording system | 0 | 1 |
| 7. | Veress needle | 0 | 1 |
| 8. | Trocar with canula 10mm (round tip) | 0 | 1 |
| 9. | Trocar with canula 10mm (sharp tip) | 0 | 1 |
| 10. | Trocar with canula 5mm (round tip) | 0 | 3 |
| 11. | Reducer to 5mm | 0 | 3 |
| 12. | Reducer to 10mm | 0 | 2 |
| 13. | Maryland Dissector | 0 | 2 |
| 14. | Endoscope graper tooth | 0 | 2 |
| 15. | Endoscope graper nontooth | 0 | 2 |
| 16. | Endoscope scissor straight | 0 | 1 |
| 17. | Endoscope scissor curve | 0 | 1 |
| 18. | Lap needle holder | 0 | 1 |
| 19. | Ring applicator | 0 | 1 |
| 20. | Clip applicator | 0 | 1 |
| 21. | Grasper 5mm | 0 | 2 |
| 22. | Lap biopsy forcep | 0 | 1 |
| 23. | Lap suction tip | 0 | 1 |
| 24. | Lap aspiration needle | 0 | 1 |
| 25. | Endohook cautery tip | 0 | 1 |
| 26. | Endoprobe | 0 | 1 |
| 27. | Cautery rod | 0 | 1 |
| 28. | Suction irrigation tubing | 0 | 1 |
| Orthopaedic Unit |  |  |  |
| 1. | C-arm x-ray machine |  | 1 |
| 2. | Bone drill and saw (preferably Stryker channel-VII but its expensive) Manman drill and saw | 0 | 1 |
| 3. | Electric POP cutter | 0 | 1 |
| 4. | Hexagonal screw driver for 2.5mm screws (Adler company) | 0 | 3 |
| 5. | Hexagonal screw driver for 3.5mm screws (Adler company) | 0 | 3 |
| 6. | Bone nibbler double action straight (adler company) small large | 0 | 2 |
| 7. | Bone nibbler double action curve (adler company) small large | 0 | 2 |
| 8. | Hand drill | 0 | 2 |
| 9. | Bone chisel straight : small/medium & large | 0 | 3 each |
| 10. | Bone chisel curve : small/medium & large | 1 | 3 each |
| 11. | Bone gauge : small / medium & large | 1 | 3 each |
| 12. | Ortho periosteal elevator with handle : 6mm & 4mm | 1 | 2 each |
| 13. | Bone levers ; small / Medium & large | 1 | 5 each |
| 14 | Wire bender | 0 | 2 |
| 15. | Wire cutter : small & large | 1 | 2 each |
| 16. | Steel mallet | 0 | 2 |
| 17. | Pelvic fracture reduction set | 0 | 1 |
| 18 | Inter-locking set (Adler company) | 0 | 1 |
| 19. | Hemiarthroplasty set | 0 | 1 |
| 20. | Bone holding forcep straight (Adler company) : Small / Medium & Large | 1 | 5 each |
| 21. | Bone holding forcep Curve (Adler company) : Small / Medium & Large | 1 | 5 each |
| 22. | Plate holding forcep (Adler company) Small / Medium & Large | 1 | 5 each |
| 23. | Bone awl with handle (for SS wire) | 0 | 2 |
| 24. | DHS set | 0 | 1 |
| 25. | DCS set | 0 | 1 |
| 26. | Spinal set (Instrument) | 0 | 1 |
| 27. | Pedicle screws (Instrument) | 0 | 1 |
| 28. | PIVD (Instrument) | 0 | 1 |
| 29. | Wire passer curved : Small / Medium & Large | 1 | 2 each |
| 30. | Bone tap holder for : 2.5 mm & 3.5mm | 1 | 5 each |
| 31. | Schanz pin introducer | 0 | 2 |
| 32. | Self retaining retractor for spine operation | 1 | 2 sets |
| 33. | Self retaining retractor : Small / Medium & Large | 1 | 2 each |
| 34. | Bone fites | 0 | 2 |
| 35. | Crutchfield tongs | 1 | 5 |
| 36. | Digital automatic pneumatic tourniquet set | 0 | 2 |
| Medicine Unit |  |  |  |
| 1. | Defibrilator | 0 | 1 |
| 2. | Infusion Pump | 0 | 2 |
| 3. | Patient Monitor | 0 | 2 |
| 4. | ECG Machine | 1 | 1 |
| 5. | Otoscope | 1 | 4 |
| Physiotherapy Unit |  |  |  |
| 1. | Physiotherapy USG machine | 0 | 1 |
| 2. | Interferential therapy unit | 0 | 1 |
| 3. | TENS | 0 | 1 |
| 4. | Electrical Muscle stimulator | 0 | 1 |
| 5. | Traction bed | 0 | 1 |
| 6. | Traction unit | 0 | 1 |
| Anesthesia |  |  |  |
| 1. | Anesthesia Workstation 9100c NXT | 1 | 1 |

HR Requirements:

8.

| Sl.No | Health Unit | Propose | Indicators | Total No | Justification |
| --- | --- | --- | --- | --- | --- |
| 1 | Hutsu PHC | HR | MO/GNM | 1-MO 1-GNM | PHC is functioning with only one GNM. |
| 2 | Avankung SC | HR | ANM | 1 | Sub-Centre is functioning with one ANM, |
| 3 | DPMU | HR | Statistical Assistant | 1 | District Programme Management Unit required Statistical assistant to do all Data entry. Since DPM are over loaded with NHM activities and all the vertical programmes. |
| 4 | CHC Chozuba | HR | 2 GNM | 2 | CHC Chozuba is functioning with only 5 GNM. It is very difficult to adjust the nurses duty for Morning, evening and Night. |
| 5 | District NCD Cell | HR | DEO | 1 | The district NCD is functioning without Data entry Operator, it very difficult for IDSP section to report all the monthly activities at this COVID-19 Situation. |
| 6 | District NCD Cell | HR | NCD Consultant | 1 | The district NCD cell is functioning without NCD Consultant till date. |

9. Monitoring Requirement

- Activity Proposed: Monitoring Fund Under HMIS and RCH

- Name of the Activity:	Monitoring  mobility support.

- Justification: Monitoring for DPMU and BPMU fund is required for mobility support for quality report and data. Monitoring and supervision of health units for DPMU and BPMU will bring data quality report for HMIS and RCH.

- Deliverables:

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost(in Lakhs) | FMR CODE |
| --- | --- | --- | --- |
| 1 DPMU | 3 Health Unit in a month@ 1000 | 0.36 |  |
| 5 Block | 5 Health Unit in a month@500 | 1.50 |  |
|  | Total | 1.86 |  |

- Activity Proposed: Monitoring Fund Under VHND

- Name of the Activity:	Monitoring  mobility support.

- Justification: Monitoring for DPMU and BPMU fund is required for mobility support of VHND conduct in the Village.

| No of Units: | Cost per unit | Total Cost(in Lakhs) | FMR CODE |
| --- | --- | --- | --- |
| 1 DCM | 3 VHND in a month@ 1000 | 0.36 |  |
| 5 Block | 5 VHND in a month@500 | 1.50 |  |
|  | Total | 1.86 |  |

| 10. PROPOSAL FOR REPLACEMENT AND REPAIRING OF AMBULANCE |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| SL. NO | Vehicle Reg. No | Health Unit | Year of Manufacture | Years | Proposal | Justifications |
| 1 | NL-10-8166 | CHC Chozuba | Oct-11 | 9 | New Ambulance | The present conditions of ambulances are very poor which resulting to poor performance. To perform better in referral transport the health unit required new ambulance. |
| 2 | NL-10-8169 | PHC Dzulha | 13-Dec-11 | 9 | New Ambulance |  |
| 3 | NL-10-6851 | PHC Ruzhazo | 17-12-2008 | 12 | New Ambulance |  |
| 4 | NL-10-6857 | PHC Akhegow | 2010 | 10 | New Ambulance |  |
| 5 | NL-10-7581 | PHC Weziho | 2010 | 10 | New Ambulance |  |
| 6 | NL-10-8923 | CHC Meluri | 2012 | 8 | Major Repairing | Major repairing required of ambulance. |
| 7 | NL-10-4362 | PHC Sutsu/Laluri | 2003 | 17 | New Ambulance | One the oldies Ambulance in the district, repairing of ambulance will cost more the new vehicle. It is very difficult for far fluent area without proper ambulance mostly during Pregnant Women Delivery and emergencies. Presently Ambulance is Off Road. |
| 8 | NL-10-7599 | PHC Khuza | Mar-13 | 7 | Major repairing | Major repairing required of ambulance. |
| 9 | NL-11-2490 | DH Phek | Nov-19 | 2 | Minor Repairing | Required minor repairing and maintenance |
| 10 | UP 32MN8026 | DH Phek | Apr-15 | 5 | Minor Repairing | Required minor repairing and maintenance |
| 11 | NL-10-6844 | PHC Zuketsa | 2008 | 12 | New Ambulance | The present conditions of ambulances are very poor which resulting to poor performance. To perform better in referral transport the health unit required new ambulance. |
| 12 | NL-10-8227 | PHC Chizami | 2008 | 12 | New Ambulance |  |
| 13 | NL-11-2878 | CHC Pfutsero | 2019 | 1 | Minor Repairing | Required minor repairing and maintenance |
| 14 | NL-10-7880 | NMMU | 2011 | 9 | New Ambulance | One of the Major covering in the where there are no Health Unit in the village and Health Unit without Medical Officer. The presently vehicle is in very poor condition, as NMMU team cannot visit far fluent areas. |
| 15 | New Proposal | Chetheba PHC 24X7 |  |  | New Ambulance | New Ambulance is urgently require at PHC Chetheba (24X7), which is covering 7 villages with the population of 13,632(According to 2011 Census) with five Sub-centres. |

| 11. PROPOSAL FOR HEALTH AND WELLNESS SUB-CENTRES SL.NO | District | Block | Health Unit Name Propose for Upgradation SC to HWC-SC | Justification |
| --- | --- | --- | --- | --- |
| 1 | Phek | Phek Sadar | Kizari | Kizari SC fall under Phek Sadar Block , Covering 810 population in the village. Health Unit Covered one Village Namely Tezatsu Village. Nearest PHC from the Subcentre is Lozaphuhu PHC which is about 44 KM. The Sub Centre function under Govt. Building. Kizari SC falls under hard to reach area due to very poor road condition, transportation and network connectivity. Kizari village is the remotest village under Phek Sadar, So inorder to create Health care awareness to the villagers Sufficient space for outpatient care, for dispensing medicines, diagnostic services, adequate spaces for display of communication material of health messages are required. |
| 2 | Phek | Phek Sadar | Tehephu | Tehephu SC fall under Phek Sadar Block , Covering 461 population in the village. Nearest PHC from the Subcentre is Khuza PHC which is about 35 KM. The Sub centre function under Govt. Building. Tehephu SC falls under hard to reach area due to very poor road condition and transportation. The Community participation of Tehephu village is encouraging. Sufficient space for outpatient care, for dispensing medicines, diagnostic services, adequate spaces for display of communication material of health messages are required. |
| 3 | Phek | Phek Sadar | Lanezho | Lanezho SC fall under Phek Sadar Block , Covering 270 population in the village. The Sub Centre is located just below the National Highway 29 leading to Meluri and Kiphire. Nearest PHC from the Subcentre is Khuza PHC which is about 25 KM. The Health Unit function under Govt. Building. The Health unit is performing good with average 31 OPD in a month. Sufficient space for outpatient care, for dispensing medicines, diagnostic services, adequate spaces for display of communication material of health messages are required. |
| 4 | Phek | Meluri | Matikhrii SC | The Sub-Centre fall under Meluri Block which the first peripheral of health care to the public for the remote population by providing daily OPD services .The average monthly OPD is 28(approx) But the optimum utilization of sub-Centre in meeting their key objective to strengthen primary health is hindered due to the factors like poor infrastructure, Weak connecting to the CHC and PHC as the Sub-Centre is situated at far flung area and without any transportation, lack of manpower in Sub-Centre and geographical barriers.The Nearest PHC is Lephory PHC. Total population:-390 Total Household:120 Distance to CHC:-34 Km. Distance to PHC:-26 Km. ANM:-2 Grade-iv staff:-2 |
| 5 | Phek | Meluri | Phokhungri SC | The Sub-Centre Phokhungri which is situated at remote border of meluri block bodering Myanmar is a Very Hard to Reach Area.The average Monthly OPD is 32.Conducting routine Immunization and VHND. The Sub Centre is Running in Govt. Building providing good health care facilities but there is always a distance and poor transportation facilities for emergency patients. The Sub-Centre had even Conducted Normal Institution Delivery Once. Total population:-1666 Total Village Covering:-3 Village (Phokhungri village,Avankhung village and Lutsam |
| 6 | Phek | Meluri | New Thewati SC | The Sub-Centre New Thewati falls under meluri Block which is 104 km away from CHC Meluri and 45 Km away from PHC weziho which is the nearest PHC. The Health Unit covers two Village(New thewati village and Old Thewati Village ) with a population of 533.The average monthly OPD is 30(approx),conducting immunization and Monthly VHND. The sub-centre infrastructure are not good ANM:-2 Grd-iv:-2 |
| 7 | Phek | Meluri | Reguri SC | The Sub-centre Reguri falls under Meluri Block situated at the far flung area bordering mynanar and ukhrul district of manipur state. The distance from CHC meluri is 119 km and the Nearest PHC is Lephory PHC with a distance of 60 Km(approx). The average Monthly OPD is 25, conducting RI session and Monthly VHND. The sub-centre is running from the Govt. Building but without any Staff quarter and there is shotage of manpower at Sub-centre. ANM:-1 Grd-iv:-3 |

12. PHEK DISTRICT CIVIL WORK PROPOSAL

- NEW CONSTRUCTION OF PHC AKHEGWO:

Justification:

Construction of PHC building:-

SC Akhegwo was upgradated to PHC Akhegwo in the year 2009 whereas The Building was constructed in the year 1980s which has 5 Rooms with 2 Toilets,one toilet is attached in the labour room. The building is half bricks and half timber whereby it is very old building where the working condition has become a daily problems for the staff of PHC. The rooms are very limited where there is no separate room for Male and Female ward, No Nurses duty room, No laboratory room, No Store room, No Office room.

The PHC Akhegwo covers 3 Village Namely:-	1.Kukhegwo Village

2.New Akhegwo Village

3.Akhegwo Village

New Construction of Quarter at PHC Akhegwo.

| Categories of Quarter | Present status | Type | Remarks/Justification |
| --- | --- | --- | --- |
| MO | No Building | Quarter for MO | MO Quarter not available |
| Nurses | No Building | Quarter for Nurses | No Nurse Quarter |
| Staff | No Building | Three type building | No Staffs Quarter All the staffs are staying in the rented house |

- New Construction of Suthotsu Sub-Centre:

Justification:

New Construction of Health Unit of Suthotsu Sub Centre under Phek Block of Phek district. Presently Health Unit is functioning at VHC House in the village. Sub Centre covering the population of 354. Present status of health unit construction is in pathetic condition.

- New Construction of PHC of Thipuzu Health Unit.

Justification:

New  PHC building for Thipuzu health unit under Pfutsero block of Phek District, There is no PHC building. As It is functioning in a very old sub centre building. Health Unit Covered 3447 population. Without proper infrastructure health facility around the villages people were facing many health issued and most importantly mother and child health care were lacking.

- PHC CHIZAMI UPGRADATION TO TRAUMA CENTRE.

Justification:

Proposing for construction of Stabilization Unit (Trauma Centre) and Force ambulance of Chizami PHC:

Chizami PHC is Covering 7763 population of five village, namely Mesulumi, Enhulumi, Sumi, Chizami village and Chizami town. PHC located near the National highway 29 of the district headquarter Phek and Kiphire district. The installation of Trauma Centre will improve to hold  any emergencies incident occur stretch area. Since the stretch areas are frequently road incident occurred in the district, with lack of infrastructure and force ambulance difficult to assist for any causality.

- New Construction of KhutsuKhono Sub Centre:

Justification:

Presently Sub centre is functioning in temporary house, since the existing sub centre is in very poor condition to provide health care services. Health unit is covering 359 population of the village. The distance from nearest PHC is about 10 KM and District Hospital is about 21 KM. Most of the month in a year are not motorable which people in the village face many problems with lack of proper infrastructure.

- Construction of MO Quarter of Zuketsa PHC:

Justification:

Proposal for new Construction of MO quarter at PHC Zuketsa. Present MO quarter was damaged by landslide. It is very difficult for Medical Officer to attend duty and stay in the station without MO quarter. To provide quality health service by Medical Officer, it is urgently need quarter for stay to provide best quality services.

- Construction of Security Fencing of Chetheba PHC and Repair/Renovation of Staff Quarter.

Justification:

Security fencing/ Boundary wall is required at PHC Chetheba. A new building was constructed but there is no security fencing nor boundary wall. Therefore, Security fencing/ boundary wall is required to check stray cattle and encroachment of land.

Present PHC staffs quarter is at the verge of break down condition, to repair the quarter will help the staffs to provide better services for the public. (Attached Photos)

13. IT Requirements for DPMU and BPMU

| SL. NO | Requirement | Total No. | Justification |
| --- | --- | --- | --- |
| 1 | Laptop for DPM (QA) | 1 | Urgently require of One Laptop for district programme Manager Quality Assurance. Without Laptop it is very difficult to work in a IT World. |
| 2 | Laptop for District Accounts Assistant | 3 | Laptop provided under NHM was very old version (Intel Pentium Processor) for two Blocks and one block particularly Phek Sadar without laptop. |
| 3 | Printer for all the block | 5 | Printer for the all the 5 blocks for reporting and office work at BPMU. |
| 4 | Logistic for Internet Connection | 7 | Internet recharge should provided to DPM, BPMs and DEO for daily and Monthly report of HMIS /RCH and other activities. |

14. UNTIED FUNDS

| PHEK DISTRICT |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Facility Level | No of facility Health Units | Untied Grant |  | AMG |  |  |
|  |  | Unit Cost (Rs) | Total Cost (Rs) | Unit Cost(Rs) | Total (Rs) | FMR Code: 4.1 |
| DH | 1 | 10,00,000 | 10,00,000 | NA | NA | 4.1.1 |
| CHC | 3 | 5,00,000 | 15,00,000 | NA | NA | 4.1.3 |
| PHC | 23 | 1,75,000 | 40,25,000 |  |  | 4.1.3 |
| SC | 48 | 10,000 | 4,80,000 | 10,000 | 4,80,000 | 4.1.5 |
| VHSNC | 107 | 10,000 | 10,70,000 |  |  | 4.1.6 |
| HWC-SC | 19 | 30,000 | 5,70,000 |  |  |  |
| HWC-PHC | 7 | 30,000 | 21,000 |  |  |  |
| TOTAL |  |  | 86.66,000 |  | 4,80,000 |  |

15. HEALTH ACTION PLAN

- Activity Proposed : Health Action Plan (including block and village)

- Name of the Activity : District Health Action Plan

- Whether New or being continued : Continued

- Achievements if Continued from previous years :

- Justification:

- The District Health Mission has been entrusted with the responsibility of formulation and ensuring implementation of the health plans within the district.

- All the Block Health Action Plan (BHAP) is prepared based on the VHAP which is prepared based on field survey, household survey and facility survey. The analysis of the report is incorporated in the final PIP at the.

- The DHAP are then prepared based on the BHAP by the district planning teams.

- The draft DHAP is then appraised at the state level and after considering and incorporating the suggestions and observations, the final draft is placed for approval before the District Planning and Development Board (DPDB) and submitted to the State Health Society for approval.

Deliverables :

| FMR Code | Activity | Target |
| --- | --- | --- |
|  | Health Action Plans(including Block, Village) |  |
|  | District | 1 |
|  | Block | 5 |

7. Funding Proposed:

| No of Units * | Cost per unit (Rs in lakhs) | Total Cost | FMR Code | Remarks |
| --- | --- | --- | --- | --- |
|  |  | (Rs in Lakhs) |  |  |
| 1 | District Level | 1.5 |  |  |
| 2 | Block Level | 5.99 |  |  |

Annexure: FMR B7

| Sl.no | Activity | Units | Rate (Rs) | Amount (Rs. In Lakhs) |
| --- | --- | --- | --- | --- |
| 1 | Field survey @ 5 villages per block | 25 | 5000 | 1.5 |
| 2 | Facility Survey per health unit | 75 | 1000 | .74 |
| 3 | Village Health Action Plan ( 5 VHAPs per block) | 25 | 5000 | 1.25 |
| 4 | BHAP planning meeting/ writing/printing and Mobility Support | 5 | 50000 | 2.5 |
| 5 | District level planning meeting/DHAP writing /printing | 1.5 | 150000 | 1.5 |
| Grand total |  |  |  | 7.49 |

Focus on difficult areas:

Health care delivery has touched almost all the remote areas although the topographical layout and terrain is very steep, arduous and the villages are far in between. Phek Districts has five (5) Blocks and the layout of the Block topographically is such that communication is easier towards Kohima rather than it’s Head Quarter, Phek. The challenges of people living in hilly remote terrain are a stumbling block to achieving the desired outcome of National Health Policy. Poor connectivity and deplorable road conditions to villages located in high altitude which in terms of economy is highly expensive and unaffordable. Public transport is easily available and therefore hiring of vehicle is not affordable to move from village to village. Electricity is irregular and alternative source not available during power failure. Delivery mostly happens at home attended by traditional birth attendants. Journey through in these roads are unfavourable during pregnancy. Mobile team caters to the remotest areas, though comprehensive package cannot be fully delivered. Illiteracy and backwardness of the far flung areas posses further challenge as villagers resort to service of local quacks rather than modern drugs for common ailments. Antenatal and Post-natal check-ups remain poorly done the village with a Sub-Centre. Traditional way of life in these far flung areas will always remain a challenge for proper implementation of health care services. Socio-economy progress and education to improve the overall development will only bring about positive change for people living in these difficulty terrains far from urban town and cities.