CHILD HEALTH PIP 2020-21

Activity: 1

- FMR Code: 1.3.1.1

- Activity Proposed: Recurrent cost of SNCU

- Name of the Activity:	Maintenance & consumable for SNCU

- Justification: Ongoing, for GoI information DH Mokokchung is new SNCU which functioning w.e.f 1st Sept 2019.

- Deliverables: District Hospital NHAK (Kohima), DH Dimapur is ongoing and for DH Mokokchung is new SNCU which start functioning w.e.f 1st Sept 2019 accordingly the budget proposed for three SNCU recurrent cost.

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost(in Lakhs) | FMR CODE |
| --- | --- | --- | --- |
| For NHAK | Rs. 10.00 lakhs | 10 | 1.3.1.1 |
| For Dimapur DH | Rs. 10.00 Lakhs | 10 |  |
| DH Mokokchung | Rs. 10.00 Lakhs | 10 |  |
| Total |  | 30.00 |  |

Activity: 2

- FMR Code: 1.3.1.2

- Activity Proposed:  Recurrent cost of NBSU

- Name of the Activity:	 Maintenance & consumable for NBSU

- Justification: Ongoing

- Deliverables: Based on report the proposed budget @ Rs. .80 Lakhs per NBSU on need based. Since most of the NBSU case loads less, accordingly the utilization of fund is low, therefore the rate per unit is cut down as per the state specific need and also to meet in the state resource envelope.

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost(in Lakhs) | FMR CODE |
| --- | --- | --- | --- |
| 2 | 80000 | 160000 | 1.3.1.2 |

| Districts | Target for 2018-19 | Cost per unit | Total Amount |
| --- | --- | --- | --- |
| 1. Longleng | 2 | 80000 | 160000 |
| Grand Total | 2 |  | 160000 |

Activity: 3

- FMR Code: 1.3.1.3

- Activity Proposed:  Recurrent cost of NBCC

- Name of the Activity:	Maintenance& consumable for NBCC

- Justification:	On going activity, since the state resource envelope is limited, therefore the budget per NBCC is cut down @Rs. 10000/NBCC for GoI consideration and approval.

- Deliverables:

- Funding Proposed:

| No. of Units: | Cost per unit | Total Cost(in Lakhs) | FMR CODE |
| --- | --- | --- | --- |
|  | Rs. 10000/- |  | 1.3.1.3 |

| Districts | Proposed Amount for 2018-19 |  |  |
| --- | --- | --- | --- |
| Name of HU | Block | Cost per unit | Total Cost in Rs. |
| DH Longleng | Longleng | 10000 |  |
| PHC Yachem | Longleng | 10000 |  |
| PHC Yongnyah | Yongnyah | 10000 |  |
| PHC Tamlu | Tamlu | 10000 |  |
| Pongo SC | Longleng | 10000 |  |
| Yongshei SC | Yongnyah | 10000 |  |
| Tangha | Yongnyah | 10000 |  |
| New |  |  |  |
| Buranamsang HWC-SC | Tamlu | 10000 |  |
| Nyang HWC-SC | Yongnyah | 10000 |  |
| Yangching HWC-SC | Longleng | 10000 |  |
| Sakshi PHC | Longleng | 10000 |  |

Activity:: 5

- FMR Code: 3.1.1.1.6

- Activity Proposed:  National Deworming Day (NDD)

- Name of the Activity: Incentive for ASHA for mobilizing and ensuring every eligible child (1to19 yrs out of school and non-enrolled) is administered Albendazole during NDD.

- Justification:  Ongoing activity.

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost(in Lakhs) | FMR CODE |
| --- | --- | --- | --- |
| 108 | 200 per ASHAs | 3.984 | 3.1.1.1.6 |

Table A: Budget for ASHA incentive for NDD 2019-20

|  |  | No. of ASHAs in Position | Incentive for ASHA |  | Total Amount in Rs. |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Aug 2020 @ Rs. 100/ | Feb 2021 @Rs. 100/ |  |
|  |  | A | B | C | (B + C x A) |
| 1 | Longleng | 108 | 100 | 100 | 21600 |
|  | Total | 108 |  |  | 21600 |

Activity:: 7

- FMR Code: 3.1.1.1.7

- Activity Proposed:  Management of Diarrhoea & ARI Micro nutritional malnutrition.

- Name of the Activity:	ASHA incentive on IDCF 2020

- Justification: On going

- Deliverables: The proposed amount is for the incentive to ASHA for IDCF 2020

- Funding Proposed:

| No. of Units: | Cost per unit | Total Cost(in Lakhs) | FMR CODE |
| --- | --- | --- | --- |
| 108 | 100 | 1.992 | 3.1.1.1.7 |

Table A: Budget for ASHA incentive for IDCF 2019

|  |  | No. of ASHAs in Position | Incentive for ASHA | Total Amount in Rs. |
| --- | --- | --- | --- | --- |
|  |  |  | For ORS @ Rs 100/ASHA |  |
|  |  | A | B | (B + C x A) |
| 1 | Longleng | 108 | 100 | 10800 |
|  | Total | 108 |  | 10800 |

Activity:: 9

FMR Code: 3.1.1.1.9

- Activity Proposed: Incentive for mobilizing children and/or ensuring compliance and reporting (6-59 months)

- Name of the Activity:	ASHA incentive on NIPI

- Justification: New

- Deliverables: The proposed amount is for the incentive to ASHA for mobilizing children and/or ensuring compliance and reporting (6-59 months) under NIPI Programme for FY 2020-21

- Funding Proposed:

| No. of Units: | Cost per unit | Total Cost(in Lakhs) | FMR CODE |
| --- | --- | --- | --- |
| 108 | 100 | 1.93 | 3.1.1.1.9 |

Activity: 12

- FMR Code: 6.2.2.4

- Name of the Activity: Procurement of Albendazole for age group of 1 to 5 yrs

- Justification: District to indicate the target group as per the  census please fellow the table below

- Deliverables:

| FMR Code | Activity | Target |
| --- | --- | --- |
| 6.2.2.4 | Procurement of Albendazole Tab | Table below |

- Funding Proposed:

| No of unit | Cost per unit | Total Cost(in Lakhs) | FMR Code |
| --- | --- | --- | --- |
|  | 5 |  | 6.2.2.4 |

| 2011 | Total Population (Census 2011) | Under 5 yrs (10% of Pop.) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Target for 2 Round | Total Tab requirement for 1 round | 10% wastage factor | Total Target group/tab required | Total Target group/tab required for 2 round |
|  |  |  | D | A | B | A+B = C | C x D |
| Dimapur | 379769 | 37976.9 | 2 | 37976.9 | 3797.69 | 41774.59 | 83549.18 |
| Kiphire | 74033 | 7403.3 | 2 | 7403.3 | 740.33 | 8143.63 | 16287.26 |
| Kohima | 270063 | 27006.3 | 2 | 27006.3 | 2700.63 | 29706.93 | 59413.86 |
| Longleng | 50593 | 5059.3 | 2 | 5059.3 | 505.93 | 5565.23 | 11130.46 |
| Mokokchung | 193171 | 19317.1 | 2 | 19317.1 | 1931.71 | 21248.81 | 42497.62 |
| Mon | 250671 | 25067.1 | 2 | 25067.1 | 2506.71 | 27573.81 | 55147.62 |
| Peren | 94954 | 9495.4 | 2 | 9495.4 | 949.54 | 10444.94 | 20889.88 |
| Phek | 163294 | 16329.4 | 2 | 16329.4 | 1632.94 | 17962.34 | 35924.68 |
| Tuensang | 196801 | 19680.1 | 2 | 19680.1 | 1968.01 | 21648.11 | 43296.22 |
| Wokha | 166239 | 16623.9 | 2 | 16623.9 | 1662.39 | 18286.29 | 36572.58 |
| Zunheboto | 141014 | 14101.4 | 2 | 14101.4 | 1410.14 | 15511.54 | 31023.08 |
| Nagaland | 1980602 |  |  |  |  | 217866.2 | 435732.4 |
| Say |  |  |  |  |  |  | 435800 |

To find the target group follow the guidelines.

The structure of population of India in percentage is available at As per Census 2011.

| Category of beneficiaries | Percent to Total Population (Rounded off to nearest zero) |
| --- | --- |
| Children under 5 years | 10 % |
| Children 5 – 10 years | 12 % |
| Adolescents (10 – 19years) | 22 % |
| Women in Reproductive Age (20 – 49 years) | 20 % |

(Source:http://censusindia.gov.in/Census_And_You/age_structure_and_marital_status.aspx and: C2 and C14 Table, India, Census of India 2001)

- For calculating children 1-2 years who are given half dose of Albendazole :

Age wise number of population for every state is available at the ‘Age – Data : Single Year Age Data – C13 Table (India/States/UTs)

http://www.censusindia.gov.in/2011census/population_enumeration.aspx

Activity:: 13

- FMR Code: 6.2.2.6

- Activity Proposed:  Procurement of Albendazole for age group of 5- 10 yrs

- Name of the Activity: For National Deworming Activity(NDD)

- Justification: As per the State essential drug list the schedule rate is Rs.5/tab. this is inclusive of all local taxes handling charges and transportation. The schedule rate of the state is comparatively higher as the company responsible for providing the medicine is not in a position to supply in less rate due the less quantity of order.

- Deliverables:

| FMR Code | Activity | Target |
| --- | --- | --- |
| 6.2.2.6 | Procurement of Albendazole Tab | Table below |

- Funding Proposed:

| No of unit | Cost per unit | Total Cost(in Lakhs) | FMR Code |
| --- | --- | --- | --- |
|  | Rs. 5 |  | 6.2.2.6 |

| 2011 | Total Population (Census 2011) | Age group of 5 to 10 yrs(12%) | Target for 1 Round | Total Tab requirement for 1 round | 10% wastage factor | Total Tab. required/target group | Total Target group/tab required for 2 round |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | A | B | A+B |  |
| Dimapur | 379769 | 45572.28 | 2 | 45572.28 | 4557.228 | 50129.51 | 100259 |
| Kiphire | 74033 | 8883.96 | 2 | 8883.96 | 888.396 | 9772.356 | 19544.71 |
| Kohima | 270063 | 32407.56 | 2 | 32407.56 | 3240.756 | 35648.32 | 71296.64 |
| Longleng | 50593 | 6071.16 | 2 | 6071.16 | 607.116 | 6678.276 | 13356.55 |
| Mokokchung | 193171 | 23180.52 | 2 | 23180.52 | 2318.052 | 25498.57 | 50997.14 |
| Mon | 250671 | 30080.52 | 2 | 30080.52 | 3008.052 | 33088.57 | 66177.14 |
| Peren | 94954 | 11394.48 | 2 | 11394.48 | 1139.448 | 12533.93 | 25067.86 |
| Phek | 163294 | 19595.28 | 2 | 19595.28 | 1959.528 | 21554.81 | 43109.62 |
| Tuensang | 196801 | 23616.12 | 2 | 23616.12 | 2361.612 | 25977.73 | 51955.46 |
| Wokha | 166239 | 19948.68 | 2 | 19948.68 | 1994.868 | 21943.55 | 43887.1 |
| Zunheboto | 141014 | 16921.68 | 2 | 16921.68 | 1692.168 | 18613.85 | 37227.7 |
| Nagaland | 1980602 |  |  |  |  | 261439.5 | 522878.9 |
| Say |  |  |  |  |  |  | 522900 |

Activity: 18

- FMR Code: 9.5.2.2

- Activity Proposed:  Management of Diarrhoea & ARI Micro nutritional malnutrition.

- Name of the Activity:	IDCF 2020

- Justification: On going

- Deliverables: Field level monitoring visit during the campaign and one day meeting expenditure before the campaign start, with the Block official and with other sister department for IDCF activity at the district level, during the meeting they will review brief/trained the key level worker how to go about the IDCF.

- Funding Proposed:

| No. of Units: | Cost per unit | Total Cost(in Lakhs) | FMR CODE |
| --- | --- | --- | --- |
| Detail in table below | Detail in table below | 14.30 | 9.5.2.2 |

Budget for Daily Mobility Support for field level monitoring, and one day meeting expenditure at District level

|  |  | Rate(in Rs) | Target | Total amount in Lakhs |
| --- | --- | --- | --- | --- |
| 1 | Daily Mobility Support for field level monitoring at District Level | 40000 | 1 District | .40 |
| 3 | One day meeting at District level proposed amount Lumsum @Rs. 90000/District | 90000 | 1 District | .90 |

Activity:: 19 (only for Kiphire, Dimapur, Wokha & Kohima for ASHAs incentive and Training budget for Kohima and wokha)

- FMR Code: 9.5.2.24 (Training on HBYC) 12.2.12 (Printing on HBYC), & 3.1.1.1.12 (ASHA incentive)

- Activity Proposed: HBYC (New Activity)

- Name of the Activity: As per the GoI directive the HBYC is a new activity to be initiated during the FY 2019-20.

- Deliverables:

- Funding Proposed:

| FMR CODE | Activity | Unit cost | Target | Amount in Lakhs |
| --- | --- | --- | --- | --- |
| 9.5.2.24 | Training on HBYC:: District level ToT & District Level training for 1 district | Detail in Table 1 & 2 below |  |  |
| 3.1.1.1.12 | Incentive to ASHA proposed 30% of ELB | 250 | 4200 |  |

District level ToT on HBYC detail budget break up (Table -1)

| Name of Training | No. of Persons to be Trained | No of Batch | No of Days of Training | DA to Trainees @ Rs. 800/ day including lodging (800 x 30 x 5) | TA to Trainees @ Rs. 3000 (one time) (30 x 3000 two ways) | Resource person honorarium @ Rs. 1000/ day for 2 Resource Persons | Food (Lunch, Tea & Snacks) @ Rs. 350/ day/person/Batch | Training Materials @Rs. 250/Trainee (Pen, Notepad, Chart-papers, Marker, photostat) | Total cost | Unit Cost |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| District level ToT on HBYC Training | 30 | 1 | 5 | 120000 | 90000 | 10000 | 56000 | 7500 | 283500 | 9450 |

Detail budget break up of district level training on HBYC for ASHAs. (Table -2)

| Sl. No. | District | No. of ASHAs | No. of batches (Average Batch Size = 30) | Total participants (No. of ASHAs+2 Resource Persons)*no. of batches | No of Days of Training | DA to ASHA @ Rs. 400/- per day inclusive of lodging | TA to ASHA @ Rs. 800/- one time | Resource person honorarium @ Rs. 1000/ day for 2 Resource Persons | TA to Resource Person @ Rs. 2000 one time for to and fro | Food (Lunch, Tea & Snacks) @ Rs. 250/ day/person | Training Materials @Rs. 100/ASHA (Pen, Notepad, Chart-papers, Marker, photostat) | Institutional cost (Hiring of Hall/ POL etc.) @ Rs. 1000/- per day | Total cost | unit cost |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Kohima | 140 | 4 | 148 | 5 | 280000 | 112000 | 40000 | 16000 | 185000 | 14000 | 20000 | 667000 | 4764 |
| 2 | Wokha | 174 | 6 | 186 | 5 | 348000 | 139200 | 60000 | 24000 | 232500 | 17400 | 30000 | 851100 | 4891 |
|  |  | 314 | 10 |  |  | 628000 | 251200 | 100000 | 40000 | 417500 | 31400 | 50000 | 1518100 | 4835 |

ASHAs incentive for HBYC (Table 4)

| 2011-12 | Total Population (Census 2011) | Expected Live Birth (A) | 30% of ELB (Target for ASHAs HBYC incentive) |
| --- | --- | --- | --- |
| Dimapur | 379769 | 5924 | 1777.2 |
| Kiphire | 74033 | 1155 | 346.5 |
| Kohima | 270063 | 4213 | 1263.9 |
| Wokha | 166239 | 2593 | 777.9 |
| Total |  | 13885 | 4165.5 |
|  |  |  | Say 4200 |

Activity: 20

- FMR Code: 10.1.2

- Activity Proposed:  Child death review.

- Name of the Activity:	one time review meeting on District Level.

- Whether New/ or being continued:  New

- Achievements if continued from previous years:  NA

- JustificationDeliverables:

| FMR Code | Activity | Target |
| --- | --- | --- |
| 10.1.2 | Child Death Audit | 1 District |

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost in lakhs | FMR CODE |
| --- | --- | --- | --- |
| 1 district level workshop | Detail Below |  | 10.1.2 |

Two days Advocacy/Workshop on Child Death Review process for HWs, at the District level

| Sl no | Name of District | No. of Block | No. of persons 4 Per Block for workshop | Rate including all expenditure for participant @ per Head DA/TA Lum sum(Rs 2000/person) | Institutional Over Head (stationeries) @ 300 per person for 2 days | Printing of Formats | Total of D x C |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Longleng | 3 | 12 | 24000 | 7200 | 5000 | 36200 |
|  | Total |  |  |  |  |  | 36200 |

Activity:  21

- FMR Code: 12.1.2

- Activity Proposed: Printing of MCP Card

- Name of the Activity:

- Justification:

- Deliverables:

| No. of Units: | Cost per unit | Total Cost(in Lakhs) | FMR CODE |
| --- | --- | --- | --- |
| 40000 | Rs.30/card | 12.00 | 12.1.2 |

| 2011 | Projected Popn. Of 2011 | Expected Pregnancies | 10% wastage factor | Target required |
| --- | --- | --- | --- | --- |
|  |  | B + 10% X B |  |  |
| Longleng | 51100.19483 | 889 | 88.9 | 977.9 |

Activity: 24

- FMR Code: 16.1.2.1.1

- Activity Proposed: District level (Meetings/ review meetings)

- Name of the Activity: (Based on the needs district needs to proposed for CH review meeting at district level the given budget is just am example

- Whether New/ or being continued:  New

- Achievements if continued from previous years:

- Justification:

- Deliverables:

| FMR Code | Activity | Target |
| --- | --- | --- |
| 16.1.2.1.1 | 1 meeting per district with BLO,BPM for 1 district | 60000 x 1 |

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost (in lac) | FMR CODE |
| --- | --- | --- | --- |
| 1 meeting per district | 60000 x1=.60 | .60 |  |

Activity:: 25

- FMR Code: 16.1.5.3.1

- Activity Proposed: NDD 2020-21

- Name of the Activity: PM activity for NDD this activity was not approved in SPIP 2019-20, however request to proposed in DHAP 2020-21 since during the programme implementation fund is required to carry out the activity. Given below budget is just an example.

- Justification:

- Deliverables:

- Funding Proposed:

| No of Units: | Cost per unit | Total Cost(in Lakhs) | FMR CODE |
| --- | --- | --- | --- |
| Detail in table below (for 1 District & 3 Block level) table A | Detail in table A below |  | 16.1.5.3.1 |

Table A:: Detail budget requirement for district & Block level

| Tentative budget for Aug 2018 NDD |  |  |  |  |  |  | Tentative budget for Feb 2018 NDD | Total budget required for two Round NDD |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sl no | Name of District | Block | Tentative Budget per block(in Rs) | Total (in Rs) | District level meeting expenses | Total Amount |  |  |
|  |  | I | II | (I x II=A) | B | (A+B)=C | D | (C+D)=F |
| 1 | Longleng | 3 | 10000 | 30000 | 15000 | 45000 | 45000 | 90000 |
|  |  | 3 | Total |  |  |  |  | 90000 |
| (Rupees ninety thousand only) |  |  |  |  |  |  |  |  |