Block Health Action Plan Format/Framework

This plan has been formulated by the Block MO and BPMU in consultation with the Administration, Town Council, Village Council, HCMC and Church Leaders.

- Name of the Block/Villages: Tening block

- Geographical Location (District): Peren

- Total Population of the Block: 11488

- Road connectivity & Transport/referral systems: Poor

- No./Name of  Health Units & HR status: 4 PHCs & 1 SC

- Socio-economic status/main Occupation: Farming

- Anganwadi Centres: 81

- Water Supply: Poor

- Sanitation Status: Good

- No. of Village Health Committees/VHSNCs: 25 with 4 HCMC

- SBI Account status: Active

- No. of Schools (Public/Pvt.): 30 Govt school & 8 Private schools

- VHND status:  Good

- Eligible Couple: 824

- ANC and Immunization Status: Good

- Main Health concerns: DIARRHOEA, EARLY MARRIAGE, BACK PAIN, HYPERTENSION

| SL | PRIORITY ISSUES | ACTIONS TO BE TAKEN/DONE BY THE BLOCK LOCAL LEADERS | COMMUNITY PARTICIPATION/ROLE OF COMMUNITY | SUPPORT/CONTRIBUTION FROM THE BLOCK | SUPPORT REQUIRED FROM HEALTH & OTHER DEPARTMENTS | TIMELINE |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Upgradation of PHC Tening to CHC | Approach the department and local political leaders for approval | To assist in any work if approved for upgradation | To assist in any work if approved for upgradation | To approve and provide for upgardation to CHC | 3rd-4rd qtr 2020-21 |
| 2 | R/R and rewiring for PHC Tening as the wiring is very old and there is chance for short circuit. | To generate work force to help in R/R |  |  | Provide fund for R/R & rewiring | 2nd qtr 2020-21 |
| 3 | Procurement of new ambulance or major repair of the existing ambulance. The present ambulance is practically off road. |  |  |  | Allotment of a new ambulance or provide fund for major repair of existing ambulance | 1st qtr 2020-21 |
|  | Posting of lab.tech for PHC Tening is urgently needed. |  |  |  | Appointment of lab.tech for Tening PHC | 1st qtr 2020-21 |
|  | Extension of labor room for Ntuma PHC since the present LR is very congested and difficult for the staff to work. |  |  |  | Provide fund for extension of LR | 1st qtr 2020-21 |
|  | Post of ICTC counselor for Ntuma PHC since there is no manpower attached to ICTC Ntuma |  |  |  | Appointment of counselor | 1st qtr 2020-21 |
|  | Posting of MO under Mbaulwa PHC since no MO has been posted after the transfer of the previous MO |  |  |  | Posting of MO at Mbaulwa PHC | 1st qtr 2020-21 |
|  | New PHC building for Mbaulwa PHC at the new site since the present PHC is functioning in a sub centre building and the building is in a rundown condition. |  |  |  | New PHC building for Mbaulwa PHC | 2nd -3rd qtr 2020-21 |
|  | Replacement of new GNM under NHM under Mbaulwa PHC |  |  |  |  |  |
|  | Construction of LR & New born care attached with toilet at Azailong PHC |  |  |  |  |  |
|  | Construction of fencing for Azailong PHC |  |  |  |  |  |
|  | Construction of Over head tank at Nsong sc & Azailong PHC |  |  |  |  |  |
|  | Upgradation of Nsong sc to PHC |  |  |  |  |  |

Covers 6 villages old nkio 48 km. population 3759