Sechu Block Health Action Plan

- Name of the Block/Villages: Sechu Zubza

- Geographical Location (District): Sechu Zubza

- Total Population of the Block: 16,767

- Road connectivity & Transport/referral systems: Poor

- No./Name of  Health Units & HR status: 8 Health Units/3 M.O,7 GNM,14 ANM,1 CHO,1 LHV,4 LAB.TECH.

- Socio-economic status/main Occupation: Farmers

- Anganwadi Centres: 62 AWC’s and all Active

- Water Supply: Good

- Sanitation Status: average

- No. of Village Health Committees/VHSNCs:12

- SBI Account status:Active

- No. of Schools (Public/Pvt.): 28(public schools)/ 13(private schools)

- VHND status: Conduct once monthly

- Eligible Couple: 2767

- ANC and Immunization Status: 27% in ANC and 18% in immunization

- Main Health concerns: NCD

| SL | PRIORITY ISSUES | ACTIONS TO BE TAKEN/DONE BY THE BLOCK LOCAL LEADERS | COMMUNITY PARTICIPATION/ROLE OF COMMUNITY | SUPPORT/CONTRIBUTION FROM THE BLOCK | SUPPORT REQUIRED FROM HEALTH & OTHER DEPARTMENTS | TIMELINE |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Low ANC and immunization coverage | Mobilze the missed out children and pregnant women | To be more cooperative in availing the services | To be more cooperative in availing the services | Adequate and timely supply of medicines to the H.U .Timely release of funds and incentives to the Asha’s and health workers. | 2nd Quarter(2020-21) |
| 2 | Manpower a). Required a regular lab.tech in Mezoma PHC b)Required a Lab.Technician in Jotsoma PHC c). Required a Medical Officer in Jotsoma PHC d) . Required 2nd ANM each for Seithogei SC and Dziileke SC | NA | NA | NA | To fill in the required man power | 2nd Quarter(2020-21) |
| 3 | Infrastructure a).Separate toilets for staffs and patients required in Khonoma PHC b). Required a building for Seithogei SC which is currently functional under one room provided by Kohima Orphanage. | NA | NA | NA | To put in the state PIP | 2nd Quarter(2020-21) |
| 4 | The village being near to the state capital,majority of the villagers avail the services from the private hospitals | Spread awareness to avail the services from the HU | To take the priority in availing the services | Providing 1st priority to the HU whenever required | To conduct health talks and health camps | 2nd Quarter(2020-21) |
| 5 | NCD related | Coordinate with the health workers in spreading awareness in the village | Avail the NCD screening services | Conduct FGD and spread awareness during meetings and VHND | conduct health camps and health talks | 2nd Quarter(2020-21) |

# Officials & Stakeholders/community involved in the planning: