Tseminyu Block Health Action Plan

- Name of the Block/Villages: Tseminyu

- Geographical Location (District): Kohima

- Total Population of the Block: 56839

- Road connectivity & Transport/referral systems:  Vehicular(Poor)

- No./Name of  Health Units & HR status: 11 Health Units/1-SMO,MO-6,GNM-10,ANM-21,Lab tech-6,LHV-3

- Socio-economic status/main Occupation: Farmer

- Anganwadi  Centres :94

- Water Supply: Piped

- Sanitation Status: Average

- No. of Village Health Committees/VHSNCs: 40

- SBI Account status: Yes (Active)

- No. of Schools (Public/Pvt.)public-49,private-9

- VHND status: Monthly

- Eligible Couple: 9378

- ANC and Immunization Status: ANC- 9%, Immunization- 9%

- Main Health concerns: NCD Related

| SL | PRIORITY ISSUES | ACTIONS TO BE TAKEN/DONE BY THE BLOCK LOCAL LEADERS | COMMUNITY PARTICIPATION/ROLE OF COMMUNITY | SUPPORT/CONTRIBUTION FROM THE BLOCK | SUPPORT REQUIRED FROM HEALTH & OTHER DEPARTMENTS | TIMELINE |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | ANC and Immunization | Re-sensitize the village leaders. VCC, VHC,Church leaders , Ashas and Awws to mobilize the villagers and organise awareness programs on the importance of Ante natal care and immunization | Availing the services in time provided by the department. Encourage the pregnant women to come for complete Anc. Mobilise the drop out children | Support and give importance of ANC and institutional deliveries. The village leaders to give hand holding support to ASHAs and health workers on VHNDs and routine Immunizations | Provide sufficient and continues supply of vaccines and medicines in time. Timely release of funds and incentives for the ASHAs and health workers. | 2nd quarter |
| 2 | Malaria | The village leaders to take initiative in keeping the village environment clean and healthy. | Sanitation and cleanliness drive to conduct monthly. | To co-ordinate with the health workers and give hand holding support. To come for blood test at the SC level whenever fever occurs. | Conduct health camp especially during Malaria month as transportation system is very poor, the villagers finds it difficult to come for the treatment in time. Carry out IRS from time to time. | 2nd quarter |
| 3 | NCD | The village leaders to take initiative to control and ban the selling of tobacco and alcohol within the village premises | The villagers to be cautious in their diets. Avail the screening services in time in the SC | The community to support and encourage the health workers to do away with these kinds of diseases | Conduct health camps and FGD in the village level more often | 2nd quarter |
| 4 | MANPOWER : 1. Required additional MO at CHC Tseminyu. 2. Required MO at PHC Tesophenyu which now is functioning without an MO. 3. PHC chunlikha which is a 24*7 PHC required additional staff nurse. | NA | NA | NA | NA | 2nd quarter |
| 5 | INFRASTRUCTURE : 1. Repair and renovations of ward and labour room toilets in the CHC Tseminyu. 2. Repair and renovations of 8 staff quarters under CHC Tseminyu . 3. Water tape connection in the OPD at CHC Tseminyu. 4. Separate toilets for public and staff at CHC tseminyu. 5. PHC building with sufficient rooms and staff quarters at Tesophenyu PHC. 6. Separate toilets for staff and public at PHC Tesophenyu. 7. Staff quarters at PHC Chunlikha. 8. Separate toilets for patients male and female. 9. Repair and renovations required at PHC Chunlikha as the structure is in a debilated state especially the wooden window frames and doors 10. Major repair and renovations of Tseminyu New town SC |  |  |  |  |  |
| 6 | 1. Electric wiring of indoors at CHC Tseminyu 2. Roof and wall paintings of CHC Tseminyu |  |  |  |  |  |

# Officials & Stakeholders/community involved in the planning: