Village Health Action Plan Format

- Name of the Village: Seiyhama

- Geographical Location (block/District): Kohima

- Total Population: 903 (2011 census)

- Road connectivity & Transport systems: Poor

- No./Name of  Health Units & HR status: Seiyhama SC/ 6

- Socio-economic status/main Occupation: Cultivation

- Anganwadi Centres: 4

- Water Supply: No

- Sanitation Status: Fair

- Village Health Committee/VHSNC: Yes

- SBI Account status: Acyive

- No. of Schools (Public/Pvt.): 1

- VHND status: Regular/Monthly

- Eligible Couples: 149

- ANC and Immunization Status: Low

- Main Health concerns: Low Service delivery

| SL | PRIORITY ISSUES | ACTIONS TO BE TAKEN/DONE BY THE VILLAGER LOCAL LEADERS | COMMUNITY PARTICIPATION/ROLE OF COMMUNITY | SUPPORT/CONTRIBUTION FROM THE VILLAGE | SUPPORT REQUIRED FROM HEALTH & OTHER DEPARTMENTS | TIMELINE |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Creation of Sub Centre at Teichuma- The village has a population of 610, which fall under Seiyhama Sub Centre. The same SC covered 5 villages | - To Coordinate with Teichuma Village and apprise concern department/Medical for Creation of New SC | - Provide local arrangement/ Logistic support | - Contribute available resources and Services. | - Creation of New SC at Teichuma Village. | 1st Quarter |
| 2 | VHND | - Ensure conduct VHND regularly. - Apprise line department like Social Welfare for Nutritional supplement | - Involvement of VC and VHC Members. | - Coordinate with line departments for logistic support. - ASHAs and AWWs to mobilized the target beneficiaries. | - Mobility support for Supervision - Untied funds to conduct VHND. - Social Welfare Deptt/AWW to provide supplements | Ongoing |
| 3 | ANC & Immunization |  |  |  |  |  |

# Officials & Stakeholders/community involved in the planning: