Annexure - 2: Key Deliverables under NHM 2022-24

# RCH flexipool including Routine Immunization Programme, Pulse Polio Immunization Programme

| Indicator Type | Indicator Statement | Indicator | Unit | Target 2021-22 | Progress 2021-22 | Likely achievement 2021-22 | Target 2022-23 | Target 2023-24 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Maternal Health |  |  |  |  |  |  |  |  |
| Output | Percentage of pregnant women received Skilled Birth attendant during deliveries (Institutional + home) | % of SBA (Skilled Birth Attendant) deliveries to total reported deliveries | Percentage | 90% | 80% | 85% | 95 % | 95% |
| Output | Pregnant women given 180 Iron Folic Acid (IFA) tablets | % of pregnant women given 180 IFA tablets as against pregnant women registered for ANC | Percentage | 90% | 70% | 80% | 90-95 % | 90-95% |
| Output | LaQshya certified units (labour rooms) | Number of nationally certified LaQshya units (Labour rooms) | nos. | 1 | 1 | 1 | 1 | 1 |
| Output | LaQshya certified units (operation theaters) | Number of nationally certified LaQshya units (Operation Theatre) | nos. | 1 | 1 | 1 | 1 | 1 |
| Output | Public facilities notified under SUMAN | Number of public facilities notified under SUMAN | nos. | 1 | 1 | 1 | 1 | 1 |
| Output | ANC registration | Percentage ANC registered within 1st trimester (within 12 weeks) | Percentage | 75% | 62% | 65% | 90% | 90-95% |
| Output | ANC check-ups | Percentage PW received 4 or more ANC check ups | Percentage | 80% | 67% | 70% | 85% | 90% |
| Output | Institutional Deliveries | Institutional deliveries % | Percentage | Maintain at least 95% | 97% | 90% | 97% | 97% |
| Output | PMSMA | % of Pregnant Women who attended PMSMA session out of Total ANC registered | Percentage | At least 25% | 34% | 40% | 70% | 80-85% |
| Routine Immunization |  |  |  |  |  |  |  |  |
| Output | Full immunization coverage | Percentage Full Immunization Coverage (FIC) | Percentage | 90% | 76% | 85% | 90-95% | 90-95% |
| Output | Coverage of birth dose Hepatitis B | Improvement in % of children receiving birth dose Hepatitis B as against institutional deliveries | Percentage | 90% | 60% | 80% | 95% | 95% |
| Output | Dropout % of children | Decrease in dropout % of children from penta 1 to penta 3 | Percentage | 17% | 12% | 15% | 10% | 8% |
| Output | Dropout % of children | Decrease in dropout % of children Pentavalent 1 to MR 1 | Percentage | 12% | 8% | 10% | 10% | 8% |
| Output | Dropout % of children | Decrease in dropout % of Children MR 1 to MR 2 | Percentage | 7% | 4% | 6% | 5% | 4% |
| Output | TT10 coverage | Improvement in % of Children receiving TT10 | Percentage | 55% | 40% | 45% | 70% | 75% |
| Child Health |  |  |  |  |  |  |  |  |
| Output | SNCU successful discharge rate | SNCU successful discharge rate (minimum benchmark: sustained above 80%) | Percentage | 90% | 80% | 85% | 95% | 95% |
| Output | Districts with SNCU | No. of Districts with functional SNCU | nos | Minimum Benchmark: 90% | 1 | 1 | 1 | 1 |
| Output | Functional NBSUs at CHC-FRU | No. of Functional NBSUs at CHC-FRU Level | nos | Minimum Benchmark: 90% | 0 | 0 | 2 | 2 |
| Output | HR training in FBNC | No. of HR trained in FBNC Module (NSSK, FBNC Observership, NBSU) | nos | Minimum Benchmark: 90% |  |  |  |  |
| Output | Equipment functionality | No. of functional Equipment at SNCU/ NICU | nos | Minimum Benchmark: 90% |  |  |  |  |
| Output | HR in-position | No. of HR in-position as per FBNC Guideline | nos | Atleast 80% |  |  |  |  |
| Output | Child Death Reporting | No. of Child Death Reported against Estimated deaths | nos | Atleast 80% |  |  |  |  |
| Output | Child Death Review | No. of Child Death Reviewed at Block & District Level | nos | Atleast 6 per block for community level deaths and 100% Child Death Review at Facility level with 500 deliveries annually) |  |  |  |  |
| Output | Districts with Skill Station | No. of Districts with established Skill Station (Atleast 80%) | Percentage | Atleast 80% |  |  |  |  |
| Output | SAANS implementation in districts | No. of Districts implemented SAANS IEC/ BCC Campaign (100%) | Percentage | 100% |  |  |  |  |
| Output | SAANS trainings | No. of District level ToTs& Block level training under SAANS (CHOs, ANMs, MOs) | Percentage | Minimum Benchmark: 90% - District level and 50% at block level | 90% | 90% | 100% | 100% |
| Output | Handheld Pulse Oximeter availability | No. of DH/ SDH with Handheld Pulse Oximeter | Percentage | Minimum Benchmark: 90% | 100% | 100% | 100% | 100% |
| Output | ASHA/AF training | No. of batches completed for module 6 & 7 training against planned for newly deployed ASHAs/AFs | Percentage | Atleast 80% ASHAS trained | 80% | 90% | 95% | 95% |
| Output | HBNC kits procurement for new ASHAs | No. of new HBNC kits procured against required for newly deployed ASHAs | Percentage | Expected Achievement: 100% |  |  |  |  |
| Output | Home visits by ASHAs for Newborns | No. of newborns received complete schedule of home visits against target newborns (live births) in ASHA catchment area | Percentage | Expected Achievement: 90% |  |  |  |  |
| Output | HBYC training of ASHAs, FLWs | Atleast 50% of ASHAs, FLWs trained under HBYC in implemented Districts (90% Districts) | Percentage | Expected Achievement: 90% |  |  |  |  |
| Output | HBYC-ECD kits procurement | No. of new HBYC-ECD kits procured against required for ASHAs/AFs who are trained in HBYC | Percentage | Expected Achievement: 100% |  |  |  |  |
| Output | Paediatric HDU/ ICU unit | No. of Districts with functional Paediatric HDU/ ICU unit | Percentage | Expected Achievement: 80% | 82% | 90% | 90-95% | 90-95% |
| Output | Paediatric Ward | No. of District Hospital with functional Paediatric Ward | Percentage | Expected Achievement: 80% | 1 | 1 | 1 | 1 |
| Output | CoE | Functional CoE with HUB-SPOKE Model | nos |  | 0 |  |  |  |
| Output | F-IMNCI and Critical Care trained staff | No of staff posted in Paediatric Care Units trained in F-IMNCI and Critical Care | Percentage | Expected Achievement: 80% | 70% | 70% | 70% | 70% |
| Output | Equipment at Paediatric Care Units | No of equipment functional at Paediatric Care Units | Percentage | Expected Achievement: 80% | 85% | 85% | 85% | 85% |
| Nutrition |  |  |  |  |  |  |  |  |
| Output | Nutrition Rehabilitation Centre (NRC) | Bed occupancy rate and Cure rate | Percentage | Expected Achievement: Bed occupancy rate: 75% Cure rate: 90% | 0 | 0 | 0 | 0 |
| Output | Mothers’ Absolute Affection Programme (MAA) | Delivery points completely saturated with 4 days IYCF training | Percentage | Expected Achievement: 75% | 0 | 0 | 0 | 0 |
| Output | Intensified Diarrhoea Control Fortnight (IDCF) | Prepositioning of ORS at household having under-five children for awareness generation | Percentage | ORS Prepositioning: > 75% of the total under five children | 90% | 90% | 90-95% | 90-95% |
| Output | Vitamin-A Supplementation programme | Procurement and availability of Vitamin-A solution in all facilities and with ANMs | Percentage | 90% | 80% | 85% | 90-95% | 90-95% |
| Output | Lactation Management Centres (LMCs) | Establishment of LMUs at all DH having functional 12 bedded SNCUs and CLMCs at high load MCs and DHs | nos | 0 | 0 | 0 | 0 | 0 |
| Comprehensive Abortion Care |  |  |  |  |  |  |  |  |
| Output | CAC services | Number of public health facilities CHC and above equipped (Drugs (MMA Combipack/ Mifepristone & Misoprostol), Equipment (MVA/EVA) and Trained Provider (MTP Trained MO/OBGYN)) for providing CAC services | Percentage | Expected Achievement: 100% | 90% | 90% | 90-95% | 90-95% |
| Output | MO training | Number of MO trained as per the target set in ROP | Percentage | Expected Achievement: 100% | 100% | 100% | 100% | 100% |
| Rashtriya Bal Swasthya Karyakram (RBSK) |  |  |  |  |  |  |  |  |
| Output | Newborn Screening | No of Delivery points conducting Newborn Screening | Percentage | Expected Achievement: 90% | 90% | 90% | 95% | 95% |
| Output | Functional DEICs | Functional DEIC with Infrastructure, Essential Equipment and HR as per Guidelines (atleast 50% of districts having functional DEICs) | Percentage | Expected Achievement: 100% | 60% | 60% | 90% | 90% |
| Output | RBSK MHTs - | RBSK MHTs fully operational for community screening (100% blocks) | Percentage | Expected Achievement: 100% | 100% | 100% | 100% | 100% |
| Output | RBSK MHTs | Atleast 80% Public Schools and Anganwadi Centre covered by RBSK MHTs | Percentage | Expected Achievement: 80% | 90% | 90% | 100% | 100% |
| Output | Secondary/ Territory management of Conditions | Secondary/ Territory management of Conditions specified under RBSK |  | 0 | 0 | 0 | 0 | 0 |
| Family Planning |  |  |  |  |  |  |  |  |
| Output | PPIUCD | PPIUCD acceptance % | Percentage | 80% | 65% | 70% | 80% | 85% |
| Output | Injectable MPA | Injectable MPA users % | Percentage | 0 | 0 | 0 | 20% | 30% |
| Output | FPLMIS | % of Facilities indenting and issuing the stock in FPLMIS | Percentage | 90% | 90% | 90% | 100% | 100% |
| Adolescent Health/ Rashtriya Kishore Swasthya Karyakram(RKSK) |  |  |  |  |  |  |  |  |
| Output | Client load at AFHC | Average monthly Client load of atleast 150 Clients / AFHC/month in PE Districts at DH/SDH /CHC level. (HMIS) | nos | Functional AFHC with atleast 150 clients per month | 170-180 | 170 | 200 | 300 |
| Output | WIFS coverage | At least 60% coverage of in-school beneficiaries and 50% coverage of out-of-school (girls) under WIFS Programme (HMIS) | Percentage | 60% coverage of in-school beneficiaries and 50% coverage of out-of-school (girls) | 0 | 0 | 80% | 85% |
| Output | Selection and training of PEs | 100% selection of the targeted Peer Educators (PEs) and training of atleast 75% of the Selected PEs. | Percentage | Selection of all targeted PE s and training for atleast 75% of the selected PE in the FY 2021-22. |  |  |  |  |
| Output | Menstrual Hygiene Scheme coverage | 75% coverage of the targeted AGs / month under Menstrual Hygiene Scheme (HMIS) | Percentage | Coverage of 75 % of Adolescent girls targeted under MHS |  |  |  |  |
| Output | School Health & Wellness Programme implementation | 100% of the selected Districts implementing School Health & Wellness Programme as per approvals in RoP 2021-22 | Percentage | All selected districts implementing SHP |  |  |  |  |
| Output | Adolescent pregnancy | Percentage of women aged 15-19 years who were already mothers or pregnant | Percentage | 7 | 2% |  |  |  |
| Output | Women aged 20-24 years who were married by age 18 years | Percentage of women aged 20-24 years who were married by exact age 18 years | Percentage | 25 |  |  |  |  |
| Output | Married women age 15-19 with unmet need for family planning | Percentage of currently married women age 15-19 with unmet need for family planning | Percentage | 20% |  |  |  |  |
| Output | Prevalence of Iron Deficiency Anaemia (IDA) among adolescents | Reduce prevalence of Iron Deficiency Anaemia (IDA) among adolescent’s girls and boys. | Percentage | Girls - 52% Boys - 28% |  |  |  |  |
| Output | tobacco users ( 13 to 19 yrs ) | Percentage of tobacco users ( 13 to 19 yrs ) |  | 8.5% |  |  |  |  |
| PCPNDT |  |  |  |  |  |  |  |  |
| Output | Constitution and regular meetings of statutory bodies | Constitution and regular meetings of statutory bodies as mandated by Law (SAA,SSB, SAC, DAA, DAC) | Percentage | 100% |  |  |  |  |
| National Iodine Deficiency Disorders Control Programme |  |  |  |  |  |  |  |  |
| Output | Review of implementation of NIDDCP | No. of States /UTs Reviewed for Programme implementation n | nos. |  |  |  |  |  |
| Output | Monitoring of availability and consumption of adequately iodized salt in all States/UTs | Availability of adequately Iodized salt in the country (greater than 30 ppm at production level, greater than 15ppm at consumption level | nos. |  |  |  |  |  |
| Output | Testing of salt samples | Number of salt samples tested using Salt Testing Kits (Qualitative testing) | Nos. | Minimum 50 samples per district per month | 92% | 92% | 95% | 95% |
| Output | Testing of salt samples | Number of salt samples tested for estimation of iodine content i.e Volumetric testing | Nos. | Minimum 25 samples per district per month | 92% | 92% | 95% | 95% |
| Output | Testing of Urine samples | Number of urine samples tested for Urinary iodine estimation | Nos. | Minimum 25 samples per district per month |  |  |  |  |
| Output | Testing of Urine samples | Urinary iodine estimation of urine samples has not been done by the State |  |  |  |  |  |  |
| Output | IDD surveys/resurveys | Number of district IDD surveys/ resurveys conducted in State/UT |  |  |  |  |  |  |

# NDCP Flexi Pool

| Indicator Type | Indicator Statement | Indicator | Unit | Target 2021-22 | Progress 2021-22 | Likely achievement 2021-22 | Target 2022-23 | Target 2023-24 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| National Tuberculosis Elimination Programme (NTEP) |  |  |  |  |  |  |  |  |
| Output | Total TB cases notified (Both public and private sectors) | % of cases notified against target Numerator: No. of TB cases notified (public+private) Denominator: Target approved by GoI | Percentage | 95% |  |  |  |  |
| Output | Expansion of rapid molecular diagnostics for TB | Number of blocks with rapid molecular diagnostics | Nos. | 3 |  |  |  |  |
| Output | Expansion of rapid molecular diagnostics for TB | % of eligible TB patients tested for Rifampicin resistance | Nos. | 100% |  |  |  |  |
| Output | State TB Score | % improvement in Annual TB Score Numerator: (State Annual TB Score in Current Yr- State Annual TB Score in last yr) Denominator: State Annual TB Score in last yr | Percentage | 100% |  |  |  |  |
| Output | NikshayPoshanYojana | % of eligible patients receiving at least first installment of DBT Numerator: No. of eligible patients receiving at least first installment of DBT Denominator: No. of eligible patients | Percentage | 59% |  |  |  |  |
| Output | Districts with TB free Status | No. of districts to achieve TB free Status # Bronze # Silver # Gold #TB Free district/City | No. | 1 |  |  |  |  |
| Output | Rabies Vaccine and Rabies Immunoglobulins | Availability of Rabies Vaccine and Rabies Immunoglobulins | Percentage | Availability of Stock as per EML at 100% health Facilities |  |  |  |  |
| Output | Rabies Post Exposure Prophylaxis Services | Strengthening of Rabies Post Exposure Prophylaxis Services | Percentage | As per Approval in ROP |  |  |  |  |
| Output | Capacity building of HR | Improved Capacity of States and district level manpower for prevention and control of rabies | Nos. | 1 each at State & 1 District Level |  |  |  |  |
| Output | Capacity building of HR | Improving capacity of health professionals with respect to diagnosis, case management, prevention & control of Leptospirosis | Nos. | 1 training at state level and 1 training at district level) | 1 | 1 | 4 | 4 |
| Output | Diagnostic services for Leptospirosis | Strengthening Diagnostic services for Leptospirosis | Percentage | 100% |  |  |  |  |
| Output | Hepatitis C - Functional labs reporting under the program | No of serological tests done for diagnosis of viral hepatitis C | Nos. |  |  |  |  |  |
| Output | Hepatitis C - Functional treatment sites reporting under the program | No of new patients initiated on treatment of hepatitis C | Nos. |  |  |  |  |  |
| Output | Hepatitis B- Functional labs reporting under the program | No of serological tests done for diagnosis of viral hepatitis B | Nos. |  |  |  |  |  |
| Output | Hepatitis B-Functional treatment sites reporting under the program | No of new patients initiated on treatment of hepatitis B | Nos. |  |  |  |  |  |
| Output | Treatment site in each district | To establish at least one Treatment site in each district | Nos. |  |  |  |  |  |
| Output | Screening during ANC for HBsAg | Screening during ANC for HBsAg (Hepatitis B surface antigen) of 100% pregnant women subjected to ANCs | Percentage | 90% | 90% | 90% | 100% | 100% |
| Output | Institutional delivery of HBsAg positive pregnant women | To ensure 100% institutional delivery of HBsAg positive pregnant women who test during ANCs | Percentage |  |  |  |  |  |
| Output | Hepatitis B birth dose | Administration of Hepatitis B birth dose to all Newborns | Percentage |  |  |  |  |  |
| Output | NVHCP Portal | NVHCP MIS portal usage | Percentage | 80% | 50% | 70% | 90% | 95% |
| Output | Improved capacity of Districts to detect and respond to disease outbreaks | District Public Health Labs (DPHLs) strengthened for diagnosis/testing of epidemic prone diseases | Nos. |  |  |  |  |  |
| Outcome | Laboratory confirmation of outbreak prone diseases under IDSP | Number of Laboratory generating L (Laboratory) form under IDSP | Nos. |  |  |  |  |  |
| Output | Decline in Percentage of Grade II Disability (G2D) cases among new cases | Reduction in Percentage of detection of new Grade II (G2D) disability cases among new cases at the national level | Percentage |  |  |  |  |  |
| Output | Malaria | Percentages of reduction in Malaria Cases | Percentage | 0% | 0% | 0% | 0% | 0% |
|  |  | Zero Indigenous Malaria Cases | Nos. | 0 | 0 | 0 | 0 | 0 |
|  |  | Number of districts to achieve Disease Free Status – Malaria | Nos. | 0 | 0 | 0 | 0 | 0 |
|  |  | Notification of Malaria | Nos. | 0 | 0 | 0 | 0 | 0 |
| Output | Lymphatic Filariasis | Conduct annual Mass Drug Administration (MDA) in eligible districts | Nos. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable |
|  |  | The proportion of districts/IUs with coverage >65% for DA and 85% for IDA of the total population (admin coverage/independent assessment) | Percentage | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable |
|  |  | Morbidity management and disease prevention (MMDP) services for hydrocele and Lymphoedema cases | Nos. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable |
|  |  | % of PHCs in the endemic districts providing MMDP care (lymphoedema and ADL management and Hydrocele) | Percentage | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable |
|  |  | % of total lymphoedema cases provided with MMDP kits | Percentage | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable |
|  |  | % of hydrocele surgeries conducted | Percentage | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable |
|  |  | sustain <1% Mf rate in LF endemic districts validated by TAS during the year | Percentage | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable |
|  |  | Cumulative number of endemic districts which have achieved mf rate <1% verified by TAS 1 (%) | Nos. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable |
|  |  | Cumulative number of districts to achieve Disease Free Status- LF as per TAS 3 Clearance (%) | Nos. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable |
| Output | Dengue & Chikungunya | Reduce/sustain case fatality rate for Dengue at <1% | Percentage | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable |
|  |  | Number of Sentinel site hospitals set up (1 per district) against total no. of districts/Functional | Nos. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable |
|  |  | Notification of Dengue | Nos. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable |
| Output | Japanese Encephalitis | JE vaccination Coverage under routine Immunization | Percentage | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable |
|  |  | Reduce case fatality rate due to JE | Percentage | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable |
|  |  | Number of Sentinel site hospitals set up (1 per district) against total no. of endemic districts/Functional | Nos. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable |

# NCD Flexi Pool

| Indicator Type | Indicator Statement | Indicator | Unit | Target 2021-22 | Progress 2021-22 | Likely achievement 2021-22 | Target 2022-23 | Target 2023-24 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| National Tobacco Control Programme (NTCP) |  |  |  |  |  |  |  |  |
| Output | Increase in availability of Tobacco Cessation Services available | Additional No. of districts with Tobacco Cessation Centers | Nos. |  |  |  |  |  |
| Outcome | Improved access for Tobacco Cessation Services | No. of People availed tobacco cessation services in 2022-24 | Nos. |  |  |  |  |  |
| National Mental Health Programme (NMHP) |  |  |  |  |  |  |  |  |
| Output | Improved coverage of mental health services | Number of District Mental Health Units operationalized | Nos. | 1 | 1 | 1 | 1 | 1 |
| Output | Improved coverage of mental health services | Number of districts with a District Mental Health Programme | Nos. | 1 | 1 | 1 | 1 | 1 |
| Outcome | Improved coverage of Mental Health Services | % Increased registrations of people with mental disorders at District Mental Health Units | Percentage | 3% | 3% | 3% | 4% | 5% |
| National Programme for Health Care of Elderly |  |  |  |  |  |  |  |  |
| Output | Provision of primary and secondary Geriatric health care services at District Hospital and below | No. of District Hospitals with geriatric OPD services | Nos. |  |  |  |  |  |
| Output | Provision of primary and secondary Geriatric health care services at District Hospital and below | Number of DH with at least 10beds reserved for elderly patients | Nos. |  |  |  |  |  |
| Output | Provision of primary and secondary Geriatric health care services at District Hospital and below | Number of District Hospitals with physiotherapy services | Nos. |  |  |  |  |  |
| Output | Provision of primary and secondary Geriatric health care services at District Hospital and below | Number of district hospitals with laboratory services | Nos. |  |  |  |  |  |
| Output | Provision of primary and secondary Geriatric health care services at District Hospital and below | No. of CHCs with geriatric OPD services | Nos. |  |  |  |  |  |
| Output | Provision of primary and secondary Geriatric health care services at District Hospital and below | No. of CHCs with geriatric physiotherapy services | Nos. |  |  |  |  |  |
| Outcome | Geriatric patients provided treatment at District Hospitals and CHCs | % increase in no. of geriatric OPD, in-patient care, physiotherapy and laboratory services in district hospitals | Percentage |  |  |  |  |  |
| Outcome | Geriatric patients provided treatment at District Hospitals and CHCs | % increase in the no. of geriatric patients in geriatric OPD, physiotherapy services in CHCs | Percentage |  |  |  |  |  |
| Outcome | Provision of Geriatric health care services at CHCs | No. of CHCs where Physiotherapy services has been rolled out, have worked out mechanism for regular home visits by the designated personnel in their catchment areas | Nos. |  |  |  |  |  |
| Outcome | Provision of Geriatric health care services at CHCs | No. of CHCs where Physiotherapy Services has been rolled out against total no. of CHCs | Nos. |  |  |  |  |  |
| National Programme for Prevention and Control of Cancer, diabetes, cardiovascular diseases and Stroke (NPCDCS) |  |  |  |  |  |  |  |  |
| Output | Additional NCD clinics to be set up at CHCs | NCD Clinics to be set up at CHCs | nos. | 2 | 0 | 0 | 2 | 2 |
| Output | Screening for High Blood pressure and High Blood Sugar. | No. of Persons Screened for High blood pressure and High Blood Sugar (% increase) | nos. |  | 472 | 472 |  |  |
| Output | Setting up of NCD Clinics at District Hospitals | No. of NCD Clinics set up at District hospitals | nos. | 1 | 1 | 1 |  |  |
| Outcome | Improved access to NCD health services | No. of persons availing facilities at NCD clinic (% increase) | nos. | 1742 | 1742 | 1742 |  |  |
| Outcome | Early Diagnosis | Patients under treatment on diabetes and hypertension (% increase) Data Source AB-HWC | Nos. |  |  |  |  |  |
| National Programme for Control of Blindness and Vision Impairment (NPCBVI) |  |  |  |  |  |  |  |  |
| Output | Eye care services under NPCB and VI provided at primary, secondary at District level and below level | Cataract Surgeries (in Lacs) | nos. |  |  |  |  |  |
| Output | Eye care services under NPCB and VI provided at primary, secondary at District level and below level | Collection of donated eyes for corneal transplant ion | nos. |  |  |  |  |  |
| Output | Eye care services under NPCB and VI provided at primary, secondary and district level and below level | No. of free spectacles to school children suffering from refractive errors (in Lacs) | nos. |  |  |  |  |  |
| Output | Eye care services under NPCB and VI | Treatment of other eye diseases specially for Diabetic Retinopathy | nos. |  |  |  |  |  |
| # Pradhan Mantri National Dialysis Program (PMNDP) |  |  |  |  |  |  |  |  |
| Output | New patients registered for dialysis | Average number of fresh cases registered for dialysis at the centres (monthly) | Percentage | NA |  |  |  |  |
| Output | Old cases of dialysis | Average number of old cases | Percentage | NA |  |  |  |  |
| Output | Dialysis Sessions held | Average number of sessions held per month | Percentage |  |  |  |  |  |
| Output | Hemodialysis machine utilisation | Utilisation of Hemodialysis Machines (Numerator: No. of H.D. sessions conducted. Denominator: Max No. of HD sessions that can be performed ideally 40 sessions per machine per month) | Percentage |  |  |  |  |  |
| Output | Waiting list for dialysis services | Number of patients waiting for dialysis | Nos. |  |  |  |  |  |
| Output | Drop out patients of hemodialysis services | Number of drop out patients of hemodialysis services at the end of reporting month | Percentage |  |  |  |  |  |
| Output | BPL patients provided services | Number of BPL patients provided services | Nos. |  |  |  |  |  |
| Output | APL patients provided services | Number of APL patients provided services | Nos. |  |  |  |  |  |
| Output | Peritoneal dialysis | Number of patients started Peritoneal dialysis under PMNDP | Nos. |  |  |  |  |  |
| Output | Patients shifted from Hemodialysis to Peritoneal dialysis | Number of patients shifted from Hemodialysis to Peritoneal dialysis | Nos. |  |  |  |  |  |
| Output | Peritonitis during Peritoneal dialysis | Number of patients suffered with Peritonitis during Peritoneal dialysis | Nos. |  |  |  |  |  |
| # National Programme for Prevention & Control of Deafness (NPPCD) |  |  |  |  |  |  |  |  |
| Output | NPPCD implementation | No. of District implemented NPPCD | Nos. | 1 | 1 | 1 | 1 | 1 |
| Output | Examination under NPPCD | No. of Persons Examined with Deafness. | Nos. | 626 | 626 | 626 |  |  |
| Output | Hearing Aid | Total No. of Hearing Aid fitted | Nos. | 176 | 176 | 176 |  |  |
| National Programme on Climate Change and Human Health |  |  |  |  |  |  |  |  |
| Output | Strengthening of State level organizational structure | Whether the State has appointed State Nodal Officer-Climate Change (SNO-CC) (Yes/No) | NA |  |  |  |  |  |
| Output | Strengthening of State level organizational structure | Whether the State has constituted Governing Body under Hon’ble Health Ministers of State (Yes/No) | NA |  |  |  |  |  |
| Output | Strengthening of State level organizational structure | Whether the State has set up multi-sectoral Task Force under Principal Secretary (Health) (Yes/No) | NA |  |  |  |  |  |
| Output | Strengthening of State level organizational structure | Whether the State has established Environment Health Cell (Yes/No) | NA |  |  |  |  |  |
| Output | Strengthening of District level organizational structure | No. of Districts appointed District Nodal Officer-Climate Change (DNO-CC) Numerator: No. of Districts with DNO-CC Denominator: No. of Districts in the State | Nos. |  |  |  |  |  |
| Output | Strengthening of District level organizational structure | No. of Districts set up multi-sectoral Task Force under District Collector Numerator: No. of District level with multi-sectoral Task Force Denominator: No. of Districts in the State | NA |  |  |  |  |  |
| Output | Consultant Climate Change and Health | Whether the State has appointed Consultant Climate Change and Health as per posts approved in ROP | NA |  |  |  |  |  |
| Output | State Action Plan Climate Change and Human Health (SAPCCHH) inclusive of air pollution and heat action plans | a. Whether the State has submitted the First draft of SAPCCHH? b. Whether the State has published the approved version of SAPCCHH? | NA |  |  |  |  |  |
| National Programme for Palliative Care (NPPC) |  |  |  |  |  |  |  |  |
| Output | Strengthening palliative care service | Cumulative number of districts covered and providing services under NPPC, as per framework, against total no of districts approved under the program | Nos |  |  |  |  |  |
| National Oral Health Programme (NOHP) |  |  |  |  |  |  |  |  |
| Output | Strengthening Oral Health Services | Cumulative no. of functional dental care units at public health facilities till PHC level against total public health facilities till PHC level (DH/SDH/CHC/PHC) | Nos | 2 | 2 | 2 | 5 | 5 |

# National Urban Health Mission

| Indicator Type | Indicator Statement | Indicator | Unit | Target 2021-22 | Progress 2021-22 | Likely achievement 2021-22 | Target 2022-23 | Target 2023-24 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Output | Improving access to healthcare in urban India | No. of OPDs carried out at health facilities in urban India (% increase) | Percentage | NA |  |  |  |  |
| Output | Improving access to healthcare in urban India | No. of operational health and wellness centres (HWCs) increased) | nos. | NA |  |  |  |  |
| Output | Providing quality healthcare services in Urban India | Number of children getting full immunization at all Urban Health Facilities (% increase) | Percentage | NA |  |  |  |  |
| Output | Providing quality healthcare services in Urban India | Number of women getting at least 4 ANCs at all Urban Health Facilities (% increase) | Percentage | NA |  |  |  |  |
| Outcome | Reduction in Infant Mortality Rate (IMR) | Infant Mortality Rate (IMR) | nos. | NA |  |  |  |  |
| Outcome | Reduction in Maternal Mortality Ratio (MMR) | Maternal Mortality Ratio (MMR) | nos. | NA |  |  |  |  |
| Output | Improving access to healthcare in urban India | Number of Cities where identification/ mapping of urban slums completed/to be completed | nos | NA |  |  |  |  |
| Output | Improving access to healthcare in urban India | Number of cities where vulnerability mapping completed/to be completed | nos | NA |  |  |  |  |
| Output | Providing quality healthcare services inProviding quality healthcare services in Urban India Urban India | Number of monthly UHNDs held/ to be held | Percentage | NA |  |  |  |  |
| Output | Providing quality healthcare services in Urban India | Number of Special Outreach sessions held/to be held | Percentage | NA |  |  |  |  |
| Output | Providing quality healthcare services in Urban India | Number of Mahila Aarogya Samiti (MAS) formed/to be formed | Percentage | NA |  |  |  |  |
| Output | Providing quality healthcare services in Urban India | Number of MAS trained/to be trained | Percentage | NA |  |  |  |  |
| Output | Improving access to healthcare in urban India | Number of UPHCs providing Telemedicine services | nos | NA |  |  |  |  |
| Output | Improving access to healthcare in urban India | Number of HWC-UPHC providing Lab test ( Minimum 63 lab test In House/ Hub Spoke/PPP mode) | nos | NA |  |  |  |  |
| Output | Improving access to healthcare in urban India | Number of HWC- UPHC providing drugs as per EDL | nos | NA |  |  |  |  |

# Health Systems Strengthening (HSS)

| Indicator Type | Indicator Statement | Indicator | Unit | Target 2021-22 | Progress 2021-22 | Likely achievement 2021-22 | Target 2022-23 | Target 2023-24 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Quality Assurance |  |  |  |  |  |  |  |  |
| Output | NQAS certified public health facilities | Number of NQAS certified public health facilities (% increase) Annual | Percentage |  |  |  |  |  |
| Output | Public health facilities with Kayakalp score greater than 70% | Number of public health facilities with Kayakalp score more than 70% (% increase) | Percentage |  |  |  |  |  |
| Output | Implementation of DVDMS in PHCs | Percentage of PHCs implementing the DVDMS | Percentage |  |  |  |  |  |
| Outcome | Increased availability of drugs and diagnostics at public health facilities | Increase in annual footfall (no. of OPD) in public health facilities (% increase) | Percentage |  |  |  |  |  |
| Outcome | Improved utilization of public health facilities | Increase in annual footfall in public health facilities (% increase) | Percentage |  |  |  |  |  |
| Output | Bio-medical waste management authorization | At all health facilities | Nos. |  |  |  |  |  |
| Outcome | Strengthening of public health facilities to provide quality healthcare services Improved utilization of NQAS/ LaQshya certified public health facilities | Increase in annual footfalls (no. of OPD) in NQAS certified public health facilities (% increase) | Percentage |  |  |  |  |  |
| Output | Free Diagnostics Services | Number of tests performed at public health facilities | Nos. |  |  |  |  |  |
| Output | Free Diagnostics Services | Number of hub labs in the state | Nos. |  |  |  |  |  |
| Output | Generic medicines availability | Availability of quality generic medicines as per States/UTs EMLs. | Nos. |  |  |  |  |  |
| Output | Free Diagnostics Services | Number of high-end tests (not included in the list of tests in FDSI guidelines) done per month | Nos. |  |  |  |  |  |
| Blood Service & Disorders |  |  |  |  |  |  |  |  |
| Output | Number of FRUs having Blood Banks/ Blood Storage Units | Cumulative number of FRUs (including DHs) having Blood Banks/ Blood Storage Units against total no. of FRUs (DH/SDH/CHC) | Nos. | Each District Hospital to have a Blood bank integrated with E-Raktkosh |  |  |  |  |
| Output | Voluntary blood donation | Voluntary blood donation against the blood collection units targeted for replacement/ donation | Nos. | Each CHC/FRU to have a BSU linked with BB |  |  |  |  |
| Output | Number of patients requiring blood transfusion | No. of patients received blood transfusion against the no. of patients requiring blood transfusion at FRUs (DH/SDH/CHC) | Nos. | Free blood to patients admitted in Govt Hospitals |  |  |  |  |
| Output | No of ICHH centres in the state | Number of integrated centres for hemoglobinopathies& hemophilia in the district against no. of identified districts with high prevalence of hemoglobinopathies& hemophilia | Nos. | Provision for drugs for Hemoglobinopathies in DHs as per NLED |  |  |  |  |
| Comprehensive Primary Healthcare (CPHC) |  |  |  |  |  |  |  |  |
| Output | Number of functional Health & Wellness Centers | Numerator: Total functional AB-HWCs Denominator: Total existing facilities (PHC+SHC+UPHC) | Percentage | 100% | 100% | 100% | 100% | 100% |
| Output | Increase in footfalls at AB-HWCs | Numerator: Total footfalls at AB-HWCs in the reporting year Denominator: Total footfall at AB-HWCs reported in previous FY | Percentage | 30% annual increment |  |  |  |  |
| Output | Training on expanded service packages (ASHA, MPW, CHO, SN and MO | Numerator: Total number of health care functionaries trained on expanded service packages Denominator: Total of number of healthcare functionaries positioned at AB-HWCs | Percentage | 90% |  |  |  |  |
| Output | NCD services at AB-HWCs | Numerator: Individuals screened for NCD- Hypertension, Diabetes Denominator: Total population above 30 years | Percentage | 100% annually |  |  |  |  |
| Output |  | Numerator: Individuals screened for NCD- Oral cancer, Breast Cancer and Cervical Cancer Denominator: Target population for the year | Percentage | 100% |  |  |  |  |
| Output | Expanded service packages | Numerator: Total individuals screened for expanded service packages- Oral, Eye, ENT, MNS, Elderly and Palliative Denominator: Target population | Percentage | 30% annual increment |  |  |  |  |
| Output | Functional AB-HWCs providing wellness services | Numerator: Total wellness sessions conducted every month Denominator: Total wellness sessions planned per month (6 Wellness activities/month/AB-HWC) | Percentage | 100% |  |  |  |  |
| Output | Tele-consultations started at AB-HWCs | Numerator: No of facilities-initiated teleconsultation services Denominator: Total functional AB-HWCs | Percentage | 100% |  |  |  |  |
| Output | Monitoring upward and downward referrals | Numerator: Individuals reached the higher centers within 7 days of referral Denominator: Total individuals referred to the higher center (Hypertension, Diabetes, Oral cancer, Breast Cancer, Cervical Cancer, Oral, Eye, ENT, MNS, Emergency, Elderly and Palliative) | Percentage | 100% |  |  |  |  |
| Output |  | Numerator: Individuals who came for follow-up services at AB-HWC within 1 month of treatment initiation. Denominator: Individuals received treatment (Hypertension, Diabetes, Oral cancer, Breast Cancer, Cervical Cancer, Oral, Eye, ENT, MNS, Elderly and Palliative) | Percentage | 80% |  |  |  |  |
| Output | Treatment compliance | Numerator: Individuals received treatment for NCD- Hypertension, Diabetes, Oral cancer, Breast Cancer and Cervical Cancer regularly Denominator: Total individuals diagnosed for NCDs- Hypertension, Diabetes, Oral cancer, Breast Cancer and Cervical Cancer (1 follow up visit/individual/month) | Percentage | 70% |  |  |  |  |
| Output | JAS functioning | Numerator: Number of AB-HWCs conducted at least 10 meetings in a year Denominator: Total functional AB-HWCs (1 JAS meeting/month) | Percentage | 90% |  |  |  |  |
| Output | Utilisation of Untied Funds by JAS | Numerator: Number of JAS that have spent more than 80% of the amount of annual untied fund/amount released in the year (whichever is higher), in the last financial year Denominator: Total JAS of the area (block / district) | Percentage | 80% of JAS of the area (block/district) have spent more than 80% amount of annual untied fund/amount released in the year (whichever is higher), in the last FY. |  |  |  |  |
| Output | Functional AB-HWC awarded Kayakalp Awards | Numerator: Number of facilities awarded Kayakalp Denominator: Total number of functional AB-HWCs | Percentage | 70% |  |  |  |  |
| Output | NQAS certified Functional AB-HWC | Numerator: Number of facilities NQAS certified Denominator: Total number of functional AB-HWCs | Percentage | 30% |  |  |  |  |
| Output | HBNC services by ASHAs | Numerator – Number of children who received complete visits (as per schedule) as per HBNC schedule by ASHAs Denominator - Total number of newborns in the catchment area | Percentage | 80% of newborn received HBNC visits |  |  |  |  |
| Output | HBNC services for high-risk/sick newborns by ASHAs | Numerator – Number of high-risk/sick newborns referred by ASHAs to seek care at health institution Denominator – Number of newborns who were sick or at high risk | Percentage | 100% of high-risk/sick newborn received HBNC visits |  |  |  |  |
| Output | HBYC services by ASHAs | Numerator – Number of children who received complete visits (as per schedule) as per HBYC schedule by ASHAs Denominator - Total number of children due for HBYC services | Percentage | 50% of newborn received HBYC visits |  |  |  |  |
| Output | Child Immunization services by ASHAs | Numerator – Number of children mobilized by ASHAs who received immunization (as per schedule) in a month by ASHAs Denominator - Total number of registered children whose immunization was due that month | Percentage | 90% of children received immunization as per schedule |  |  |  |  |
| Output | Training of ASHAs in ASHA Module 6 and 7 | Numerator – Number of ASHAs trained in all four rounds (Round 1, 2, 3 and 4) in ASHA Module 6 and 7 Denominator - Total number of ASHAs in-position since last one year or more | Percentage | 90% of ASHAs trained in each four rounds |  |  |  |  |
| Output | Training of ASHAs in HBYC | Numerator – Number of ASHAs trained in HBYC Denominator - Total number of ASHAs in-position | Percentage | 50% of ASHAs trained in HBYC |  |  |  |  |
| Outcome | Improved utilization of primary care services and screening and management of NCDs | Number of 30+ population screened for NCDs (in Cr.) | Nos. |  |  |  |  |  |
| Output | Functioning of VHSNC (in rural areas) | Numerator: Number of VHSNCs that conducted at least 8 monthly meetings in the last financial year (against the norm of minimum one meeting every month) Denominator: Total VHSNCs of the area (block / district) | Percentage | 80% of VHSNCs of the area (block/district) have conducted minimum 8 monthly meetings in the last FY. |  |  |  |  |
| Output | Utilisation of Untied Funds by VHSNCs | Numerator: Number of VHSNCs that have spent more than 80% of the amount of annual untied fund/amount released in the year (whichever is higher), in the last financial year Denominator: Total VHSNCs of the area (block / district | Percentage | 80% of VHSNCs of the area (block/district) have spent more than 80% amount of annual untied fund/amount released in the year |  |  |  |  |
| Output | Functioning of MAS (in urban areas) | Numerator: Number of MAS that conducted at least 10 monthly meetings in the last financial year (against the norm of minimum one meeting every month) Denominator: Total MAS of the city | Percentage | 80% of VHSNCs of the area (block/district) have conducted minimum 10 monthly meetings in the last FY. |  |  |  |  |
| Output | Utilisation of Untied Funds by MAS | Numerator: Number of MAS that have spent more than 80% of the amount of annual untied fund/amount released in the year (whichever is higher), in the last financial year Denominator: Total MAS of the area (block / district) | Percentage | 80% of MAS of the area (block/district) have spent more than 80% amount of annual untied fund/amount released in the year (whichever is higher), in the last FY. |  |  |  |  |
| Output | Payment of Routine and Recurring Incentives | Numerator: Number of ASHAs who have received complete Routine and Recurring Incentives (against the activities performed) Denominator: Total number of ASHAs in-position | Percentage | 100% of ASHAs receiving Routine and Recurring Incentives |  |  |  |  |
| Output | Performance based incentives | Numerator: Number of ASHAs who have received performance-based incentives (against the activities performed) Denominator: Total number of ASHAs in-position | Percentage | 100% of ASHAs receiving performance-based incentives |  |  |  |  |
| AYUSH |  |  |  |  |  |  |  |  |
| Output | Co-location of AYUSH facilities | Number of Co-located AYUSH facilities operationalised | Nos | 2 | 2 | 2 |  |  |
| Output | AYUSH HR | Percentage of In-position AYUSH doctor against the approved number in NHM ROP | Percentage | 100% |  |  |  |  |
| Output | AYUSH HR | Percentage of In –position AYUSH pharmacists against the approved number in NHM ROP | Percentage | 100% |  |  |  |  |
| Healthcare Technology (HCT) |  |  |  |  |  |  |  |  |
| Output | Functional equipment | Total number of functional equipment available at the health facility | Nos. |  |  |  |  |  |
| Output | Non-Functional equipment | Number of equipment not functional for more than 7 days | Nos. |  |  |  |  |  |
| Output | Breakdown calls | Number of breakdown calls attended | Nos. |  |  |  |  |  |
| Output | Critical equipment up-time less than 95% | Number of critical equipment up-time less than 95% | Percentage |  |  |  |  |  |
| Output | AERB certified facilities | Total number of AERB certified facilities in the state (in-house/PPP) | Nos. |  |  |  |  |  |