Block Health Action Plan Format/Framework

- Name of the Block/Villages: 				Tizit Block

- Geographical Location (District): 			Mon

- Total Population of the Block:			 27396

- Road connectivity & Transport/referral systems: 	YES(POOR)

- No./Name of  Health Units & HR status:		 10(2 PHC,8 SC)

- Socio-economic status/main Occupation: 		AGRICULTURE

- Anganwadi Centres	              :					49

- Water Supply: 					YES(POOR)

- Sanitation Status:					 YES/AVERAGE

- No. of Village Health Committees/VHSNCs: 	10 VHC,19 VHSNC.

- SBI Account status:					YES

- No. of Schools (Public/Pvt.): 				55 (37-GOVT. 18-PRIVATE)

- VHND status:						YES(GOOD)

- Eligible Couple: 					4376

- ANC and Immunization Status:  			YES(GOOD)

- Main Health concerns:  				FOCUS MORE IMPORTANCE IN ANC,IMMNIZATION AND  SANITATION.

| SL | PRIORITY ISSUES | ACTIONS TO BE TAKEN/DONE BY THE BLOCK LOCAL LEADERS | COMMUNITY PARTICIPATION/ROLE OF COMMUNITY | SUPPORT/CONTRIBUTION FROM THE BLOCK | SUPPORT REQUIRED FROM HEALTH & OTHER DEPARTMENTS | TIMELINE |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | REQUIREMENT OF FURNITURE,EQUIPMENTS TO THE NEWLY SC CREATION JABOKA SC |  | Need to take care/maintain the Sub centre bythe community |  | Provide fund,drugs and other furniture as per Sub centre norms | 4th Quarter of 2020-2021 |
| 2 | REQUIREMENT OF FURNITURE,EQUIPMENTS TO THE NEWLY SC CREATION JABOKA SC |  | Need to take care/maintain the Sub centre bythe community |  | Provide fund,drugs and other furniture as per sub centre norms | 4th Quarter of 2020-2021 |
| 3 | More health camps should be conducted to far flung areas/villages |  |  |  | Sufficient funds and drugs should be release in time to conduct such conductsuch camps |  |
| 4 | More monitoring and evaluation to all the health units. |  |  | Monitoring and evaluation by Block Medical officer along with BPMU | Need funds/pol for monitoring from the concern dept. | To be conducted every quarter. |
| 5 | Tizit phc is 24*7 Phc,there is no proper/adequate drugs,equipment,and other requirement facilities. | Need help/contribution/donation from the civil societies/NGOs For minor repairing of the old phc | Need voluntary assist from the Community such as social work and other manual works if required |  | To provide adequate equipment,drugs and other requirement services(facilities)as per Government norms. | 2nd quarterof 2021-2022 |
| 6 | Existing building/phc is very old so Need major repairing of the phc |  |  |  | Need funds for major repairing of the phc with all necessary amenities | Financial year 2021-2022 |
| 7 |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |

# Officials & Stakeholders/community involved in the planning: