Annexure - 2: Key Deliverables under NHM 2022-24

# RCH flexipool including Routine Immunization Programme, Pulse Polio Immunization Programme

| Indicator Type | Indicator Statement | Indicator | Unit | Target 2021-22 | Progress 2021-22 | Likely achievement 2021-22 | Target 2022-23 | Target 2023-24 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Maternal Health |  |  |  |  |  |  |  |  |
| Output | Percentage of pregnant women received Skilled Birth attendant during deliveries (Institutional + home) | % of SBA (Skilled Birth Attendant) deliveries to total reported deliveries | Percentage | 1245 | 46% | 70% | 75% | 80% |
| Output | Pregnant women given 180 Iron Folic Acid (IFA) tablets | % of pregnant women given 180 IFA tablets as against pregnant women registered for ANC | Percentage | 1245 | 60% | 75% | 80% | 90% |
| Output | LaQshya certified units (labour rooms) | Number of nationally certified LaQshya units (Labour rooms) | nos. | 1 | 0 | 0 | 1 | 1 |
| Output | LaQshya certified units (operation theaters) | Number of nationally certified LaQshya units (Operation Theatre) | nos. | 1 | 0 | 0 | 1 | 1 |
| Output | Public facilities notified under SUMAN | Number of public facilities notified under SUMAN | nos. | 1 | 1 | 1 | - | - |
| Output | ANC registration | Percentage ANC registered within 1st trimester (within 12 weeks) | Percentage | 75% | 31% | 40% | 40% | 45% |
| Output | ANC check-ups | Percentage PW received 4 or more ANC check ups | Percentage | 80% | 20% | 25% | 25% | 30% |
| Output | Institutional Deliveries | Institutional deliveries % | Percentage | Maintain at least 95% | 36% | 45% | 50% | 60% |
| Output | PMSMA | % of Pregnant Women who attended PMSMA session out of Total ANC registered | Percentage | At least 25% | 15% | 20% | 20% | 25% |
| Routine Immunization |  |  |  |  |  |  |  |  |
| Output | Full immunization coverage | Percentage Full Immunization Coverage (FIC) | Percentage | 1131 | 73% | 75% | 77% | 80% |
| Output | Coverage of birth dose Hepatitis B | Improvement in % of children receiving birth dose Hepatitis B as against institutional deliveries | Percentage | 1131 | 35% | 40% | 45% | 50% |
| Output | Dropout % of children | Decrease in dropout % of children from penta 1 to penta 3 | Percentage |  | 9.98% | 9.98% |  |  |
| Output | Dropout % of children | Decrease in dropout % of children Pentavalent 1 to MR 1 | Percentage |  | 11.52% | 11.52% |  |  |
| Output | Dropout % of children | Decrease in dropout % of Children MR 1 to MR 2 | Percentage |  | 33.81% | 33.81% |  |  |
| Output | TT10 coverage | Improvement in % of Children receiving TT10 | Percentage | 1131 | 19% | 20% | 25% | 30% |
| Child Health |  |  |  |  |  |  |  |  |
| Output | SNCU successful discharge rate | SNCU successful discharge rate (minimum benchmark: sustained above 80%) | Percentage | - | - | - | - | - |
| Output | Districts with SNCU | No. of Districts with functional SNCU | nos | Minimum Benchmark: 90% | - | - | - | - |
| Output | Functional NBSUs at CHC-FRU | No. of Functional NBSUs at CHC-FRU Level | nos | Minimum Benchmark: 90% | 1 | 1 | - | - |
| Output | HR training in FBNC | No. of HR trained in FBNC Module (NSSK, FBNC Observership, NBSU) | nos | Minimum Benchmark: 90% | 3 | 2 more to be trained | 90% | 90% |
| Output | Equipment functionality | No. of functional Equipment at SNCU/ NICU | nos | Minimum Benchmark: 90% | - | - | - | - |
| Output | HR in-position | No. of HR in-position as per FBNC Guideline | nos | Atleast 80% | 1 | 1 | - | - |
| Output | Child Death Reporting | No. of Child Death Reported against Estimated deaths | nos | Atleast 80% | - | - |  | - |
| Output | Child Death Review | No. of Child Death Reviewed at Block & District Level | nos | Atleast 6 per block for community level deaths and 100% Child Death Review at Facility level with 500 deliveries annually) | - | - | - | - |
| Output | Districts with Skill Station | No. of Districts with established Skill Station (Atleast 80%) | Percentage | Atleast 80% | - | - | - | - |
| Output | SAANS implementation in districts | No. of Districts implemented SAANS IEC/ BCC Campaign (100%) | Percentage | 100% | 100% | 100% | 100% | 100% |
| Output | SAANS trainings | No. of District level ToTs& Block level training under SAANS (CHOs, ANMs, MOs) | Percentage | Minimum Benchmark: 90% - District level and 50% at block level | 100% | 100% | 100% | 100% |
| Output | Handheld Pulse Oximeter availability | No. of DH/ SDH with Handheld Pulse Oximeter | Percentage | Minimum Benchmark: 90% | 100% | 100% | 100% | 100% |
| Output | ASHA/AF training | No. of batches completed for module 6 & 7 training against planned for newly deployed ASHAs/AFs | Percentage | Atleast 80% ASHAS trained | 0% | 0% | 100% | 100% |
| Output | HBNC kits procurement for new ASHAs | No. of new HBNC kits procured against required for newly deployed ASHAs | Percentage | Expected Achievement: 100% | 33% | 33% | 100% | 100% |
| Output | Home visits by ASHAs for Newborns | No. of newborns received complete schedule of home visits against target newborns (live births) in ASHA catchment area | Percentage | Expected Achievement: 90% | 90% | 90% | 90% | 90% |
| Output | HBYC training of ASHAs, FLWs | Atleast 50% of ASHAs, FLWs trained under HBYC in implemented Districts (90% Districts) | Percentage | Expected Achievement: 90% | NA | NA | NA | NA |
| Output | HBYC-ECD kits procurement | No. of new HBYC-ECD kits procured against required for ASHAs/AFs who are trained in HBYC | Percentage | Expected Achievement: 100% | NA | NA | NA | NA |
| Output | Paediatric HDU/ ICU unit | No. of Districts with functional Paediatric HDU/ ICU unit | Percentage | Expected Achievement: 80% | NA | NA | NA | NA |
| Output | Paediatric Ward | No. of District Hospital with functional Paediatric Ward | Percentage | Expected Achievement: 80% | 1 | 1 | - | - |
| Output | CoE | Functional CoE with HUB-SPOKE Model | nos |  | - | - | - | - |
| Output | F-IMNCI and Critical Care trained staff | No of staff posted in Paediatric Care Units trained in F-IMNCI and Critical Care | Percentage | Expected Achievement: 80% | - | - | - | - |
| Output | Equipment at Paediatric Care Units | No of equipment functional at Paediatric Care Units | Percentage | Expected Achievement: 80% | 50% | 50% | 60% | 80% |
| Nutrition |  |  |  |  |  |  |  |  |
| Output | Nutrition Rehabilitation Centre (NRC) | Bed occupancy rate and Cure rate | Percentage | Expected Achievement: Bed occupancy rate: 75% Cure rate: 90% | NA | NA | NA | NA |
| Output | Mothers’ Absolute Affection Programme (MAA) | Delivery points completely saturated with 4 days IYCF training | Percentage | Expected Achievement: 75% | NA | NA | 25% | 50% |
| Output | Intensified Diarrhoea Control Fortnight (IDCF) | Prepositioning of ORS at household having under-five children for awareness generation | Percentage | ORS Prepositioning: > 75% of the total under five children | 60% | 60% | 70% | 80% |
| Output | Vitamin-A Supplementation programme | Procurement and availability of Vitamin-A solution in all facilities and with ANMs | Percentage |  | 100% | 100% | 100% | 100% |
| Output | Lactation Management Centres (LMCs) | Establishment of LMUs at all DH having functional 12 bedded SNCUs and CLMCs at high load MCs and DHs | nos |  | - | - | - | - |
| Comprehensive Abortion Care |  |  |  |  |  |  |  |  |
| Output | CAC services | Number of public health facilities CHC and above equipped (Drugs (MMA Combipack/ Mifepristone & Misoprostol), Equipment (MVA/EVA) and Trained Provider (MTP Trained MO/OBGYN)) for providing CAC services | Percentage | Expected Achievement: 100% | 20% | 20% | 50% | 80% |
| Output | MO training | Number of MO trained as per the target set in ROP | Percentage | Expected Achievement: 100% | - | - | 50% | 100% |
| Rashtriya Bal Swasthya Karyakram (RBSK) |  |  |  |  |  |  |  |  |
| Output | Newborn Screening | No of Delivery points conducting Newborn Screening | Percentage | Expected Achievement: 90% | 100% | 100% | 100% | 100% |
| Output | Functional DEICs | Functional DEIC with Infrastructure, Essential Equipment and HR as per Guidelines (atleast 50% of districts having functional DEICs) | Percentage | Expected Achievement: 100% | NA | NA | NA | NA |
| Output | RBSK MHTs - | RBSK MHTs fully operational for community screening (100% blocks) | Percentage | Expected Achievement: 100% | 30% | 100% | 100% | 100% |
| Output | RBSK MHTs | Atleast 80% Public Schools and Anganwadi Centre covered by RBSK MHTs | Percentage | Expected Achievement: 80% | 7%(12 Schools covered) | 80% | 100% | 100% |
| Output | Secondary/ Territory management of Conditions | Secondary/ Territory management of Conditions specified under RBSK |  |  | 3 Cleft lip/palate cases managed at tertiary level | - | - | - |
| Family Planning |  |  |  |  |  |  |  |  |
| Output | PPIUCD | PPIUCD acceptance % | Percentage |  | 0 | 0 | 0 | 0 |
| Output | Injectable MPA | Injectable MPA users % | Percentage |  | 0 | 0 | 0 | 0 |
| Output | FPLMIS | % of Facilities indenting and issuing the stock in FPLMIS | Percentage | 57 | 28% | 28% | 80% | 100% |
| Adolescent Health/ Rashtriya Kishore Swasthya Karyakram(RKSK) |  |  |  |  |  |  |  |  |
| Output | Client load at AFHC | Average monthly Client load of atleast 150 Clients / AFHC/month in PE Districts at DH/SDH /CHC level. (HMIS) | nos | Functional AFHC with atleast 150 clients per month | 10 clients | 10 | 20 clients | 30 |
| Output | WIFS coverage | At least 60% coverage of in-school beneficiaries and 50% coverage of out-of-school (girls) under WIFS Programme (HMIS) | Percentage | 60% coverage of in-school beneficiaries and 50% coverage of out-of-school (girls) | 10% | 10% | 75% | 75% |
| Output | Selection and training of PEs | 100% selection of the targeted Peer Educators (PEs) and training of atleast 75% of the Selected PEs. | Percentage | Selection of all targeted PE s and training for atleast 75% of the selected PE in the FY 2021-22. | 0 % | 0% | 75% | 75% |
| Output | Menstrual Hygiene Scheme coverage | 75% coverage of the targeted AGs / month under Menstrual Hygiene Scheme (HMIS) | Percentage | Coverage of 75 % of Adolescent girls targeted under MHS | 0% | 0% | 75% | 75% |
| Output | School Health & Wellness Programme implementation | 100% of the selected Districts implementing School Health & Wellness Programme as per approvals in RoP 2021-22 | Percentage | All selected districts implementing SHP | 10% | 10% | 50% | 50% |
| Output | Adolescent pregnancy | Percentage of women aged 15-19 years who were already mothers or pregnant | Percentage | 7 | NA | NA | NA | NA |
| Output | Women aged 20-24 years who were married by age 18 years | Percentage of women aged 20-24 years who were married by exact age 18 years | Percentage | 25 | NA | NA | NA | NA |
| Output | Married women age 15-19 with unmet need for family planning | Percentage of currently married women age 15-19 with unmet need for family planning | Percentage | 20% | NA | NA | NA | NA |
| Output | Prevalence of Iron Deficiency Anaemia (IDA) among adolescents | Reduce prevalence of Iron Deficiency Anaemia (IDA) among adolescent’s girls and boys. | Percentage | Girls - 52% Boys - 28% | 10% | 10% | 20% | 25% |
| Output | tobacco users ( 13 to 19 yrs ) | Percentage of tobacco users ( 13 to 19 yrs ) |  | 8.5% | 10% | 10% | 10% | 10% |
| PCPNDT |  |  |  |  |  |  |  |  |
| Output | Constitution and regular meetings of statutory bodies | Constitution and regular meetings of statutory bodies as mandated by Law (SAA,SSB, SAC, DAA, DAC) | Percentage | 100% | 100% | 100% | 100% | 100% |
| National Iodine Deficiency Disorders Control Programme |  |  |  |  |  |  |  |  |
| Output | Review of implementation of NIDDCP | No. of States /UTs Reviewed for Programme implementation n | nos. | -- | - | - | - | - |
| Output | Monitoring of availability and consumption of adequately iodized salt in all States/UTs | Availability of adequately Iodized salt in the country (greater than 30 ppm at production level, greater than 15ppm at consumption level | nos. | - | - | - | - | - |
| Output | Testing of salt samples | Number of salt samples tested using Salt Testing Kits (Qualitative testing) | Nos. | Minimum 50 samples per district per month | 26694 | 35592 | 35599 | 35606 |
| Output | Testing of salt samples | Number of salt samples tested for estimation of iodine content i.e Volumetric testing | Nos. | Minimum 25 samples per district per month | -above15ppm=26525, Below15ppm=71 -Nil-98 | -35,386 -88 -118 | -35595 -100 -120 | -35600 -103 -123 |
| Output | Testing of Urine samples | Number of urine samples tested for Urinary iodine estimation | Nos. | Minimum 25 samples per district per month | 205 | 255 | 255 | 255 |
| Output | Testing of Urine samples | Urinary iodine estimation of urine samples has not been done by the State |  |  | - | - | - | - |
| Output | IDD surveys/resurveys | Number of district IDD surveys/ resurveys conducted in State/UT |  | 4 | 3 | 4 | 5 | 6 |

# NDCP Flexi Pool

| Indicator Type | Indicator Statement | Indicator | Unit | Target 2021-22 | Progress 2021-22 | Likely achievement 2021-22 | Target 2022-23 | Target 2023-24 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| National Tuberculosis Elimination Programme (NTEP) |  |  |  |  |  |  |  |  |
| Output | Total TB cases notified (Both public and private sectors) | % of cases notified against target Numerator: No. of TB cases notified (public+private) Denominator: Target approved by GoI | Percentage | 130 | 130 |  | 130 | 130 |
| Output | Expansion of rapid molecular diagnostics for TB | Number of blocks with rapid molecular diagnostics | Nos. | 3 | 0 |  | 3 | 3 |
| Output | Expansion of rapid molecular diagnostics for TB | % of eligible TB patients tested for Rifampicin resistance | Nos. | 130 | 103 |  | 130 | 130 |
| Output | State TB Score | % improvement in Annual TB Score Numerator: (State Annual TB Score in Current Yr- State Annual TB Score in last yr) Denominator: State Annual TB Score in last yr | Percentage | NA |  |  |  |  |
| Output | NikshayPoshanYojana | % of eligible patients receiving at least first installment of DBT Numerator: No. of eligible patients receiving at least first installment of DBT Denominator: No. of eligible patients | Percentage | 130 | 130 |  | 130 | 130 |
| Output | Districts with TB free Status | No. of districts to achieve TB free Status # Bronze # Silver # Gold #TB Free district/City | No. | NA | NA | NA | NA | NA |
| Output | Rabies Vaccine and Rabies Immunoglobulins | Availability of Rabies Vaccine and Rabies Immunoglobulins | Percentage | Availability of Stock as per EML at 100% health Facilities | - | - | - | - |
| Output | Rabies Post Exposure Prophylaxis Services | Strengthening of Rabies Post Exposure Prophylaxis Services | Percentage | As per Approval in ROP | - | - | - | - |
| Output | Capacity building of HR | Improved Capacity of States and district level manpower for prevention and control of rabies | Nos. | 1 each at State & 1 District Level | - | - | - | - |
| Output | Capacity building of HR | Improving capacity of health professionals with respect to diagnosis, case management, prevention & control of Leptospirosis | Nos. | 1 training at state level and 1 training at district level) | - | - | - | - |
| Output | Diagnostic services for Leptospirosis | Strengthening Diagnostic services for Leptospirosis | Percentage | 100% | - | - | - | - |
| Output | Hepatitis C - Functional labs reporting under the program | No of serological tests done for diagnosis of viral hepatitis C | Nos. |  | 347 |  |  |  |
| Output | Hepatitis C - Functional treatment sites reporting under the program | No of new patients initiated on treatment of hepatitis C | Nos. |  | 2 |  |  |  |
| Output | Hepatitis B- Functional labs reporting under the program | No of serological tests done for diagnosis of viral hepatitis B | Nos. |  | 347 |  |  |  |
| Output | Hepatitis B-Functional treatment sites reporting under the program | No of new patients initiated on treatment of hepatitis B | Nos. |  | 5 |  |  |  |
| Output | Treatment site in each district | To establish at least one Treatment site in each district | Nos. | 1 | 1 | 1 |  |  |
| Output | Screening during ANC for HBsAg | Screening during ANC for HBsAg (Hepatitis B surface antigen) of 100% pregnant women subjected to ANCs | Percentage |  | 173 |  |  |  |
| Output | Institutional delivery of HBsAg positive pregnant women | To ensure 100% institutional delivery of HBsAg positive pregnant women who test during ANCs | Percentage | 1245 | 46% | 50% | 60% | 80% |
| Output | Hepatitis B birth dose | Administration of Hepatitis B birth dose to all Newborns | Percentage | 1131 | 51% | 60% | 80% | 100% |
| Output | NVHCP Portal | NVHCP MIS portal usage | Percentage |  |  |  |  |  |
| Output | Improved capacity of Districts to detect and respond to disease outbreaks | District Public Health Labs (DPHLs) strengthened for diagnosis/testing of epidemic prone diseases | Nos. | - | - | - | - | - |
| Outcome | Laboratory confirmation of outbreak prone diseases under IDSP | Number of Laboratory generating L (Laboratory) form under IDSP | Nos. | - | - | - | - | - |
| Output | Decline in Percentage of Grade II Disability (G2D) cases among new cases | Reduction in Percentage of detection of new Grade II (G2D) disability cases among new cases at the national level | Percentage | - | - | - | - | - |
| Output | Malaria | Percentages of reduction in Malaria Cases | Percentage | 100% | 0% | 0% | 0% | 0% |
|  |  | Zero Indigenous Malaria Cases | Nos. | 0 | 0 | 0 | 0 | 0 |
|  |  | Number of districts to achieve Disease Free Status – Malaria | Nos. | 0 | 0 | 0 | 0 | 0 |
|  |  | Notification of Malaria | Nos. | 0 | 0 | 0 | 0 | 0 |
| Output | Lymphatic Filariasis | Conduct annual Mass Drug Administration (MDA) in eligible districts | Nos. | DA IDA | NA | Na | NA | NA |
|  |  | The proportion of districts/IUs with coverage >65% for DA and 85% for IDA of the total population (admin coverage/independent assessment) | Percentage | DA districts IDA districts | NA | NA | NA | NA |
|  |  | Morbidity management and disease prevention (MMDP) services for hydrocele and Lymphoedema cases | Nos. | Lymphedema cases Hydrocele cases | NA | NA | NA | NA |
|  |  | % of PHCs in the endemic districts providing MMDP care (lymphoedema and ADL management and Hydrocele) | Percentage |  | NA | NA | NA | NA |
|  |  | % of total lymphoedema cases provided with MMDP kits | Percentage | Total Lymphoedema | NA | NA | NA | NA |
|  |  | % of hydrocele surgeries conducted | Percentage | Total Hydrocelectomy | NA | NA | NA | NA |
|  |  | sustain <1% Mf rate in LF endemic districts validated by TAS during the year | Percentage | Number of districts targeted for TAS 1 TAS 2 TAS 3 | NA | NA | NA | NA |
|  |  | Cumulative number of endemic districts which have achieved mf rate <1% verified by TAS 1 (%) | Nos. |  | NA | NA | NA | NA |
|  |  | Cumulative number of districts to achieve Disease Free Status- LF as per TAS 3 Clearance (%) | Nos. |  | NA | NA | NA | NA |
| Output | Dengue & Chikungunya | Reduce/sustain case fatality rate for Dengue at <1% | Percentage |  | NA | NA | NA | NA |
|  |  | Number of Sentinel site hospitals set up (1 per district) against total no. of districts/Functional | Nos. |  | NA | NA | NA | NA |
|  |  | Notification of Dengue | Nos. |  | NA | NA | NA | NA |
| Output | Japanese Encephalitis | JE vaccination Coverage under routine Immunization | Percentage | >80% | NA | NA | NA | NA |
|  |  | Reduce case fatality rate due to JE | Percentage | NA | NA | NA | NA |  |
|  |  | Number of Sentinel site hospitals set up (1 per district) against total no. of endemic districts/Functional | Nos. | NA | NA | NA | NA |  |

# NCD Flexi Pool

| Indicator Type | Indicator Statement | Indicator | Unit | Target 2021-22 | Progress 2021-22 | Likely achievement 2021-22 | Target 2022-23 | Target 2023-24 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| National Tobacco Control Programme (NTCP) |  |  |  |  |  |  |  |  |
| Output | Increase in availability of Tobacco Cessation Services available | Additional No. of districts with Tobacco Cessation Centers | Nos. | 1 | 1 | 1 | 0 | 0 |
| Outcome | Improved access for Tobacco Cessation Services | No. of People availed tobacco cessation services in 2022-24 | Nos. |  | 85 | 95 | - | - |
| National Mental Health Programme (NMHP) |  |  |  |  |  |  |  |  |
| Output | Improved coverage of mental health services | Number of District Mental Health Units operationalized | Nos. | 1 | 1 | 1 | 0 | 0 |
| Output | Improved coverage of mental health services | Number of districts with a District Mental Health Programme | Nos. | 1 | 1 | 1 | 0 | 0 |
| Outcome | Improved coverage of Mental Health Services | % Increased registrations of people with mental disorders at District Mental Health Units | Percentage | - | - | - | - | - |
| National Programme for Health Care of Elderly |  |  |  |  |  |  |  |  |
| Output | Provision of primary and secondary Geriatric health care services at District Hospital and below | No. of District Hospitals with geriatric OPD services | Nos. | 1 | 1 | 1 | - | - |
| Output | Provision of primary and secondary Geriatric health care services at District Hospital and below | Number of DH with at least 10beds reserved for elderly patients | Nos. | 1 | 1 | 1 | - | - |
| Output | Provision of primary and secondary Geriatric health care services at District Hospital and below | Number of District Hospitals with physiotherapy services | Nos. | 1 | 1 | 1 | - |  |
| Output | Provision of primary and secondary Geriatric health care services at District Hospital and below | Number of district hospitals with laboratory services | Nos. | 1 | 1 | 1 | - | - |
| Output | Provision of primary and secondary Geriatric health care services at District Hospital and below | No. of CHCs with geriatric OPD services | Nos. | 1 | 1 | 1 | - | - |
| Output | Provision of primary and secondary Geriatric health care services at District Hospital and below | No. of CHCs with geriatric physiotherapy services | Nos. | - | - | - | - | - |
| Outcome | Geriatric patients provided treatment at District Hospitals and CHCs | % increase in no. of geriatric OPD, in-patient care, physiotherapy and laboratory services in district hospitals | Percentage |  | - | - | - | - |
| Outcome | Geriatric patients provided treatment at District Hospitals and CHCs | % increase in the no. of geriatric patients in geriatric OPD, physiotherapy services in CHCs | Percentage |  | - | - | - | - |
| Outcome | Provision of Geriatric health care services at CHCs | No. of CHCs where Physiotherapy services has been rolled out, have worked out mechanism for regular home visits by the designated personnel in their catchment areas | Nos. |  | - | - | CHC Bhandari | CHC Bhandari |
| Outcome | Provision of Geriatric health care services at CHCs | No. of CHCs where Physiotherapy Services has been rolled out against total no. of CHCs | Nos. | - | - | - | CHC Bhandari | CHC Bhandari |
| National Programme for Prevention and Control of Cancer, diabetes, cardiovascular diseases and Stroke (NPCDCS) |  |  |  |  |  |  |  |  |
| Output | Additional NCD clinics to be set up at CHCs | NCD Clinics to be set up at CHCs | nos. | 1 | 1 | 1 | 1 CHC Sanis | 1 CHC Sanis |
| Output | Screening for High Blood pressure and High Blood Sugar. | No. of Persons Screened for High blood pressure and High Blood Sugar (% increase) | nos. | 9908 | 57% | 60% | 65% | 70% |
| Output | Setting up of NCD Clinics at District Hospitals | No. of NCD Clinics set up at District hospitals | nos. | 1 | 1 | 1 | - | - |
| Outcome | Improved access to NCD health services | No. of persons availing facilities at NCD clinic (% increase) | nos. | 1558 | 80% | 80% | 85% | 85% |
| Outcome | Early Diagnosis | Patients under treatment on diabetes and hypertension (% increase) Data Source AB-HWC | Nos. | 1313 | 90% | 90% | 90% | 90% |
| National Programme for Control of Blindness and Vision Impairment (NPCBVI) |  |  |  |  |  |  |  |  |
| Output | Eye care services under NPCB and VI provided at primary, secondary at District level and below level | Cataract Surgeries (in Lacs) | nos. | - | - | - | - | - |
| Output | Eye care services under NPCB and VI provided at primary, secondary at District level and below level | Collection of donated eyes for corneal transplant ion | nos. | - | - | - | - | - |
| Output | Eye care services under NPCB and VI provided at primary, secondary and district level and below level | No. of free spectacles to school children suffering from refractive errors (in Lacs) | nos. | 21 | 21 | - | - | - |
| Output | Eye care services under NPCB and VI | Treatment of other eye diseases specially for Diabetic Retinopathy | nos. | 8 | 8 | - | - | - |
| # Pradhan Mantri National Dialysis Program (PMNDP) |  |  |  |  |  |  |  |  |
| Output | New patients registered for dialysis | Average number of fresh cases registered for dialysis at the centres (monthly) | Percentage | - | - | - | - | - |
| Output | Old cases of dialysis | Average number of old cases | Percentage | - | - | - | - | - |
| Output | Dialysis Sessions held | Average number of sessions held per month | Percentage | - | - | - | - | - |
| Output | Hemodialysis machine utilisation | Utilisation of Hemodialysis Machines (Numerator: No. of H.D. sessions conducted. Denominator: Max No. of HD sessions that can be performed ideally 40 sessions per machine per month) | Percentage | - | - | - | - | - |
| Output | Waiting list for dialysis services | Number of patients waiting for dialysis | Nos. | - | - | - | - | - |
| Output | Drop out patients of hemodialysis services | Number of drop out patients of hemodialysis services at the end of reporting month | Percentage | - | - | - | - | - |
| Output | BPL patients provided services | Number of BPL patients provided services | Nos. | - | - | - | - | - |
| Output | APL patients provided services | Number of APL patients provided services | Nos. | - | - | - | - | - |
| Output | Peritoneal dialysis | Number of patients started Peritoneal dialysis under PMNDP | Nos. | - | - | - | - | - |
| Output | Patients shifted from Hemodialysis to Peritoneal dialysis | Number of patients shifted from Hemodialysis to Peritoneal dialysis | Nos. | - | - | - | - | - |
| Output | Peritonitis during Peritoneal dialysis | Number of patients suffered with Peritonitis during Peritoneal dialysis | Nos. | - | - | - | - | - |
| # National Programme for Prevention & Control of Deafness (NPPCD) |  |  |  |  |  |  |  |  |
| Output | NPPCD implementation | No. of District implemented NPPCD | Nos. | 1 | 1 | - | - | - |
| Output | Examination under NPPCD | No. of Persons Examined with Deafness. | Nos. |  | 150 | - | - | - |
| Output | Hearing Aid | Total No. of Hearing Aid fitted | Nos. | - | - | - | - | - |
| National Programme on Climate Change and Human Health |  |  |  |  |  |  |  |  |
| Output | Strengthening of State level organizational structure | Whether the State has appointed State Nodal Officer-Climate Change (SNO-CC) (Yes/No) |  |  |  |  |  |  |
| Output | Strengthening of State level organizational structure | Whether the State has constituted Governing Body under Hon’ble Health Ministers of State (Yes/No) |  |  |  |  |  |  |
| Output | Strengthening of State level organizational structure | Whether the State has set up multi-sectoral Task Force under Principal Secretary (Health) (Yes/No) |  |  |  |  |  |  |
| Output | Strengthening of State level organizational structure | Whether the State has established Environment Health Cell (Yes/No) |  |  |  |  |  |  |
| Output | Strengthening of District level organizational structure | No. of Districts appointed District Nodal Officer-Climate Change (DNO-CC) Numerator: No. of Districts with DNO-CC Denominator: No. of Districts in the State | Nos. |  |  |  |  |  |
| Output | Strengthening of District level organizational structure | No. of Districts set up multi-sectoral Task Force under District Collector Numerator: No. of District level with multi-sectoral Task Force Denominator: No. of Districts in the State |  |  |  |  |  |  |
| Output | Consultant Climate Change and Health | Whether the State has appointed Consultant Climate Change and Health as per posts approved in ROP |  |  |  |  |  |  |
| Output | State Action Plan Climate Change and Human Health (SAPCCHH) inclusive of air pollution and heat action plans | a. Whether the State has submitted the First draft of SAPCCHH? b. Whether the State has published the approved version of SAPCCHH? |  |  |  |  |  |  |
| National Programme for Palliative Care (NPPC) |  |  |  |  |  |  |  |  |
| Output | Strengthening palliative care service | Cumulative number of districts covered and providing services under NPPC, as per framework, against total no of districts approved under the program | Nos |  |  |  |  |  |
| National Oral Health Programme (NOHP) |  |  |  |  |  |  |  |  |
| Output | Strengthening Oral Health Services | Cumulative no. of functional dental care units at public health facilities till PHC level against total public health facilities till PHC level (DH/SDH/CHC/PHC) | Nos | 0 | 0 | 0 | 2 (PHC Chukitong & PHC Wozhuro) | 2 (PHC Nyiro & PHC Ralan) |

# National Urban Health Mission

| Indicator Type | Indicator Statement | Indicator | Unit | Target 2021-22 | Progress 2021-22 | Likely achievement 2021-22 | Target 2022-23 | Target 2023-24 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Output | Improving access to healthcare in urban India | No. of OPDs carried out at health facilities in urban India (% increase) | Percentage | 27147 | 16% | 20% | 30% | 50% |
| Output | Improving access to healthcare in urban India | No. of operational health and wellness centres (HWCs) increased) | nos. |  | 6 | - | - | - |
| Output | Providing quality healthcare services in Urban India | Number of children getting full immunization at all Urban Health Facilities (% increase) | Percentage | 423 | 12% | 20% | 30% | 50% |
| Output | Providing quality healthcare services in Urban India | Number of women getting at least 4 ANCs at all Urban Health Facilities (% increase) | Percentage |  | 0 |  |  |  |
| Outcome | Reduction in Infant Mortality Rate (IMR) | Infant Mortality Rate (IMR) | nos. | - | - |  |  |  |
| Outcome | Reduction in Maternal Mortality Ratio (MMR) | Maternal Mortality Ratio (MMR) | nos. | - |  |  |  |  |
| Output | Improving access to healthcare in urban India | Number of Cities where identification/ mapping of urban slums completed/to be completed | nos |  | 100% | 100% | 100% | 100% |
| Output | Improving access to healthcare in urban India | Number of cities where vulnerability mapping completed/to be completed | nos |  | 100% | 100% | 100% | 100% |
| Output | Providing quality healthcare services inProviding quality healthcare services in Urban India Urban India | Number of monthly UHNDs held/ to be held | Percentage | 108 (12 UHNDs in a month) 3 ANMs | 10% | 20% | 50% | 80% |
| Output | Providing quality healthcare services in Urban India | Number of Special Outreach sessions held/to be held | Percentage | 18 | 45% | 50% | 60% | 70% |
| Output | Providing quality healthcare services in Urban India | Number of Mahila Aarogya Samiti (MAS) formed/to be formed | Percentage | 15 formed/15 approved. | 100% | 100% | 100% | 100% |
| Output | Providing quality healthcare services in Urban India | Number of MAS trained/to be trained | Percentage | 100% | 30% | 70% | 100% | 100% |
| Output | Improving access to healthcare in urban India | Number of UPHCs providing Telemedicine services | nos | 1 | 1 | 1 | 1 | 1 |
| Output | Improving access to healthcare in urban India | Number of HWC-UPHC providing Lab test ( Minimum 63 lab test In House/ Hub Spoke/PPP mode) | nos | 1 | 1 | 1 | 1 | 1 |
| Output | Improving access to healthcare in urban India | Number of HWC- UPHC providing drugs as per EDL | nos | 1 | 1 | 1 | 1 | 1 |

# Health Systems Strengthening (HSS)

| Indicator Type | Indicator Statement | Indicator | Unit | Target 2021-22 | Progress 2021-22 | Likely achievement 2021-22 | Target 2022-23 | Target 2023-24 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Quality Assurance |  |  |  |  |  |  |  |  |
| Output | NQAS certified public health facilities | Number of NQAS certified public health facilities (% increase) Annual | Percentage | 1 | 1 | 0 | 1 | 1 |
| Output | Public health facilities with Kayakalp score greater than 70% | Number of public health facilities with Kayakalp score more than 70% (% increase) | Percentage | 8 | 8 | 8 | 10 | 10 |
| Output | Implementation of DVDMS in PHCs | Percentage of PHCs implementing the DVDMS | Percentage |  |  |  | 100% | 100% |
| Outcome | Increased availability of drugs and diagnostics at public health facilities | Increase in annual footfall (no. of OPD) in public health facilities (% increase) | Percentage |  | 20% | 20% | 25% | 30% |
| Outcome | Improved utilization of public health facilities | Increase in annual footfall in public health facilities (% increase) | Percentage |  | 20% | 25% | 30% | 35% |
| Output | Bio-medical waste management authorization | At all health facilities | Nos. | 16 | 12 | 12 | 16 | 16 |
| Outcome | Strengthening of public health facilities to provide quality healthcare services Improved utilization of NQAS/ LaQshya certified public health facilities | Increase in annual footfalls (no. of OPD) in NQAS certified public health facilities (% increase) | Percentage | - | - | - | - | - |
| Output | Free Diagnostics Services | Number of tests performed at public health facilities | Nos. |  | 6561 |  | - | - |
| Output | Free Diagnostics Services | Number of hub labs in the state | Nos. | 1 | 1 | 1 | - | - |
| Output | Generic medicines availability | Availability of quality generic medicines as per States/UTs EMLs. | Nos. | NA | NA | NA | NA | NA |
| Output | Free Diagnostics Services | Number of high-end tests (not included in the list of tests in FDSI guidelines) done per month | Nos. | NA | NA | NA | NA | NA |
| Blood Service & Disorders |  |  |  |  |  |  |  |  |
| Output | Number of FRUs having Blood Banks/ Blood Storage Units | Cumulative number of FRUs (including DHs) having Blood Banks/ Blood Storage Units against total no. of FRUs (DH/SDH/CHC) | Nos. | Each District Hospital to have a Blood bank integrated with E-Raktkosh | - | - | - | - |
| Output | Voluntary blood donation | Voluntary blood donation against the blood collection units targeted for replacement/ donation | Nos. | Each CHC/FRU to have a BSU linked with BB | - | - | - | - |
| Output | Number of patients requiring blood transfusion | No. of patients received blood transfusion against the no. of patients requiring blood transfusion at FRUs (DH/SDH/CHC) | Nos. | Free blood to patients admitted in Govt Hospitals | - | - | - | - |
| Output | No of ICHH centres in the state | Number of integrated centres for hemoglobinopathies& hemophilia in the district against no. of identified districts with high prevalence of hemoglobinopathies& hemophilia | Nos. | Provision for drugs for Hemoglobinopathies in DHs as per NLED | - | - | - | - |
| Comprehensive Primary Healthcare (CPHC) |  |  |  |  |  |  |  |  |
| Output | Number of functional Health & Wellness Centers | Numerator: Total functional AB-HWCs Denominator: Total existing facilities (PHC+SHC+UPHC) | Percentage | 100% | 46% | 46% | 50% | 50% |
| Output | Increase in footfalls at AB-HWCs | Numerator: Total footfalls at AB-HWCs in the reporting year Denominator: Total footfall at AB-HWCs reported in previous FY | Percentage | 30% annual increment | 125% | 125% | 100% | 100% |
| Output | Training on expanded service packages (ASHA, MPW, CHO, SN and MO | Numerator: Total number of health care functionaries trained on expanded service packages Denominator: Total of number of healthcare functionaries positioned at AB-HWCs | Percentage | 90% | 50% | 50% | 60% | 80% |
| Output | NCD services at AB-HWCs | Numerator: Individuals screened for NCD- Hypertension, Diabetes Denominator: Total population above 30 years | Percentage | 100% annually | 9% | 20% | 30% | 50% |
| Output |  | Numerator: Individuals screened for NCD- Oral cancer, Breast Cancer and Cervical Cancer Denominator: Target population for the year | Percentage | 100% | 9% | 10% | 30% | 50% |
| Output | Expanded service packages | Numerator: Total individuals screened for expanded service packages- Oral, Eye, ENT, MNS, Elderly and Palliative Denominator: Target population | Percentage | 30% annual increment |  |  |  |  |
| Output | Functional AB-HWCs providing wellness services | Numerator: Total wellness sessions conducted every month Denominator: Total wellness sessions planned per month (6 Wellness activities/month/AB-HWC) | Percentage | 100% |  |  |  |  |
| Output | Tele-consultations started at AB-HWCs | Numerator: No of facilities-initiated teleconsultation services Denominator: Total functional AB-HWCs | Percentage | 100% | 53% | 60% | 75% | 80% |
| Output | Monitoring upward and downward referrals | Numerator: Individuals reached the higher centers within 7 days of referral Denominator: Total individuals referred to the higher center (Hypertension, Diabetes, Oral cancer, Breast Cancer, Cervical Cancer, Oral, Eye, ENT, MNS, Emergency, Elderly and Palliative) | Percentage | 100% | NA | NA | NA | NA |
| Output |  | Numerator: Individuals who came for follow-up services at AB-HWC within 1 month of treatment initiation. Denominator: Individuals received treatment (Hypertension, Diabetes, Oral cancer, Breast Cancer, Cervical Cancer, Oral, Eye, ENT, MNS, Elderly and Palliative) | Percentage | 80% | 58% | 60% |  |  |
| Output | Treatment compliance | Numerator: Individuals received treatment for NCD- Hypertension, Diabetes, Oral cancer, Breast Cancer and Cervical Cancer regularly Denominator: Total individuals diagnosed for NCDs- Hypertension, Diabetes, Oral cancer, Breast Cancer and Cervical Cancer (1 follow up visit/individual/month) | Percentage | 70% | 9% |  |  |  |
| Output | JAS functioning | Numerator: Number of AB-HWCs conducted at least 10 meetings in a year Denominator: Total functional AB-HWCs (1 JAS meeting/month) | Percentage | 90% | - | - | - | - |
| Output | Utilisation of Untied Funds by JAS | Numerator: Number of JAS that have spent more than 80% of the amount of annual untied fund/amount released in the year (whichever is higher), in the last financial year Denominator: Total JAS of the area (block / district) | Percentage | 80% of JAS of the area (block/district) have spent more than 80% amount of annual untied fund/amount released in the year (whichever is higher), in the last FY. | - | - | - | - |
| Output | Functional AB-HWC awarded Kayakalp Awards | Numerator: Number of facilities awarded Kayakalp Denominator: Total number of functional AB-HWCs | Percentage | 70% | 12% | 12% | 22% | 27% |
| Output | NQAS certified Functional AB-HWC | Numerator: Number of facilities NQAS certified Denominator: Total number of functional AB-HWCs | Percentage | 30% | - | - | - | - |
| Output | HBNC services by ASHAs | Numerator – Number of children who received complete visits (as per schedule) as per HBNC schedule by ASHAs Denominator - Total number of newborns in the catchment area | Percentage | 80% of newborn received HBNC visits | 95% | 95% | 90% | 90% |
| Output | HBNC services for high-risk/sick newborns by ASHAs | Numerator – Number of high-risk/sick newborns referred by ASHAs to seek care at health institution Denominator – Number of newborns who were sick or at high risk | Percentage | 100% of high-risk/sick newborn received HBNC visits | - | - | - | - |
| Output | HBYC services by ASHAs | Numerator – Number of children who received complete visits (as per schedule) as per HBYC schedule by ASHAs Denominator - Total number of children due for HBYC services | Percentage | 50% of newborn received HBYC visits | - | - | - | - |
| Output | Child Immunization services by ASHAs | Numerator – Number of children mobilized by ASHAs who received immunization (as per schedule) in a month by ASHAs Denominator - Total number of registered children whose immunization was due that month | Percentage | 90% of children received immunization as per schedule | 60% | 80% | 90% | 90% |
| Output | Training of ASHAs in ASHA Module 6 and 7 | Numerator – Number of ASHAs trained in all four rounds (Round 1, 2, 3 and 4) in ASHA Module 6 and 7 Denominator - Total number of ASHAs in-position since last one year or more | Percentage | 90% of ASHAs trained in each four rounds | 85% | 90% | 100% | 100% |
| Output | Training of ASHAs in HBYC | Numerator – Number of ASHAs trained in HBYC Denominator - Total number of ASHAs in-position | Percentage | 50% of ASHAs trained in HBYC | NA | NA |  |  |
| Outcome | Improved utilization of primary care services and screening and management of NCDs | Number of 30+ population screened for NCDs (in Cr.) | Nos. |  |  |  |  |  |
| Output | Functioning of VHSNC (in rural areas) | Numerator: Number of VHSNCs that conducted at least 8 monthly meetings in the last financial year (against the norm of minimum one meeting every month) Denominator: Total VHSNCs of the area (block / district) | Percentage | 80% of VHSNCs of the area (block/district) have conducted minimum 8 monthly meetings in the last FY. | 92% | 95% | 90% | 90% |
| Output | Utilisation of Untied Funds by VHSNCs | Numerator: Number of VHSNCs that have spent more than 80% of the amount of annual untied fund/amount released in the year (whichever is higher), in the last financial year Denominator: Total VHSNCs of the area (block / district | Percentage | 80% of VHSNCs of the area (block/district) have spent more than 80% amount of annual untied fund/amount released in the year | 0% | 0% |  |  |
| Output | Functioning of MAS (in urban areas) | Numerator: Number of MAS that conducted at least 10 monthly meetings in the last financial year (against the norm of minimum one meeting every month) Denominator: Total MAS of the city | Percentage | 80% of VHSNCs of the area (block/district) have conducted minimum 10 monthly meetings in the last FY. | 80% | 80% | 90% | 90% |
| Output | Utilisation of Untied Funds by MAS | Numerator: Number of MAS that have spent more than 80% of the amount of annual untied fund/amount released in the year (whichever is higher), in the last financial year Denominator: Total MAS of the area (block / district) | Percentage | 80% of MAS of the area (block/district) have spent more than 80% amount of annual untied fund/amount released in the year (whichever is higher), in the last FY. | 80% | 80% | 90% | 90% |
| Output | Payment of Routine and Recurring Incentives | Numerator: Number of ASHAs who have received complete Routine and Recurring Incentives (against the activities performed) Denominator: Total number of ASHAs in-position | Percentage | 100% of ASHAs receiving Routine and Recurring Incentives | 70% | 80% | 100% | 100% |
| Output | Performance based incentives | Numerator: Number of ASHAs who have received performance-based incentives (against the activities performed) Denominator: Total number of ASHAs in-position | Percentage | 100% of ASHAs receiving performance-based incentives | 100% | 100% |  |  |
| AYUSH |  |  |  |  |  |  |  |  |
| Output | Co-location of AYUSH facilities | Number of Co-located AYUSH facilities operationalised | Nos |  | 1 | 1 | - | - |
| Output | AYUSH HR | Percentage of In-position AYUSH doctor against the approved number in NHM ROP | Percentage |  | 100% | 100% | - | - |
| Output | AYUSH HR | Percentage of In –position AYUSH pharmacists against the approved number in NHM ROP | Percentage |  | NA | NA | NA | NA |
| Healthcare Technology (HCT) |  |  |  |  |  |  |  |  |
| Output | Functional equipment | Total number of functional equipment available at the health facility | Nos. | - | - | - | - | - |
| Output | Non-Functional equipment | Number of equipment not functional for more than 7 days | Nos. | - | - | - | - | - |
| Output | Breakdown calls | Number of breakdown calls attended | Nos. | - | - | - | - | - |
| Output | Critical equipment up-time less than 95% | Number of critical equipment up-time less than 95% | Percentage | - | - | - | - | - |
| Output | AERB certified facilities | Total number of AERB certified facilities in the state (in-house/PPP) | Nos. | - | - | - | - | - |

| Health Management Information System (HMIS) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Output | HMIS Block level Reporting | Ensuring reporting by facilities by 10th of following month | Percentage | 100% | 100% | 100% | >90% reporting (Health Facilities under the Block) | >90% reporting (Health Facilities under the Block) |
| Output | HMIS District level Reporting | Ensuring reporting, data quality validation checks and analytical reports by the District Data manager M&E/HMIS personnel and submit it to State by 15th of the following month | Percentage | 100% | 70% | 90% | >95% reporting (HealthFacilities underthe District) | >95% reporting (HealthFacilities underthe District) |
| Output | HMIS State level Reporting | Ensuring reporting, data quality validationchecks andanalytical reportsbythe State Data Manager/M&E/HMISpersonnelandsubmit it to State NHMMissionDirectorwithcopytoStatistics Division (HMIS), MOHFW by20thof following month | Percentage |  |  |  | >97% reporting (Health Facilities undertheState) | >97% reporting (Health Facilities undertheState) |
| Output | HMIS State level Reporting | OrganizationofHMIStrainingas perapprovedPIPnormsandfurnishquarterly reportonphysical and financial achievements against the approved target toStatistics Division(HMIS), MOHFW | Percentage |  |  |  | >97% reporting (Health Facilities undertheState) | >97% reporting (Health Facilities undertheState) |
| Output | HMISmonitoring and supervision at State and District level | To undertake monitoring and supervision visit to health facilities every month by State and District level HMIS staff and furnish monthly report to State NHM MD with copy to Statistics Division(HMIS), MOHFW | Percentage | 100% |  |  | StateLevel Minimum: 3 health facilitiesvisits/month District LevelMinimum: 5 health facilitiesvisits/month | StateLevel Minimum: 3 health facilitiesvisits/month District LevelMinimum: 5 health facilitiesvisits/month |